## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-24 |  |  | APPROVED OUTAGE LIST FOR DTD.24.08.25
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-21 15:38 | MR2508/0277 | Daily | 220KV_220 kV Anuppur-Kotmikala Circuit II | 220KV_ANUPPUR | NON-OCCM-MP | For resagging work of low ground Clearance mainten | 22-08-2025 08:00:00 | 25-08-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
2 | 2025-08-21 14:08 | MR2508/0268 |  | 132KV_132 KV Main bus at Bairad | 132KV_BAIRAD | NON-OCCM-MP | To connect main bus to isolator | 24-08-2025 11:00:00 | 24-08-2025 15:00:00 | Er. Sunny Kumar | 9425806888 | sub ld
3 | 2025-08-12 17:39 | MR2508/0176 | Daily | 220KV_220KV South Zone (Indore) â¿¿ Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
4 | 2025-08-23 15:00 | MR2508/0304 |  | 132KV_132 kV Mandideep-Interconnector Ckt II | 220KV_MANDIDEEP | NON-OCCM-MP | Disc replacement work | 24-08-2025 11:00:00 | 24-08-2025 15:00:00 | Ankit Mehroliya | 9425804506 | sub ld
5 | 2025-08-12 17:23 | MR2508/0175 | Daily | 220KV_220KV Mangliya -Jaitpura Line. | 220KV_MANGLIA2 | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
6 | 2025-07-22 16:42 | MR2507/0344 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Installation of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | sub ld
7 | 2025-07-22 16:47 | MR2507/0345 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installatin of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
8 | 2025-08-23 14:26 | MR2508/0303 |  | 132KV_132 kV Nepa â¿¿ Bahadarpur Tap Nepa Mill Ckt-1st | 220KV_NEPANAGAR | NON-OCCM-MP | For Jumper Cone Tightening & Other Line Maintenanc | 24-08-2025 09:00:00 | 24-08-2025 14:00:00 | C.H. NAMDEV | 9425802377 | sub ld
9 | 2025-08-23 13:45 | MR2508/0302 |  | 220KV_220 kv Satna (MPPTCL) â¿¿ Ajaygarh line | 220KV_SATNA | NON-OCCM-MP | line maintenance work | 24-08-2025 09:30:00 | 24-08-2025 18:30:00 | Mr. RK Prajapati | 9407070182 | ok
10 | 2025-08-23 10:45 | MR2508/0301 |  | 132KV_132kv shivpuri bairad line | 220KV_SHIVPURI | NON-OCCM-MP | line maintenance work | 24-08-2025 11:00:00 | 24-08-2025 15:00:00 | suraj pawar | 9425814079 | sub ld