## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-31
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-25 15:08 | MR2508/0326 | Daily | 220KV_220KV Anuppur Kotmikala ckt-1 | 220KV_ANUPPUR | NON-OCCM-MP | For Re-sagging work due to Low Ground clearance ma | 31-08-2025 08:00:00 | 08-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
2 | 2025-08-30 14:24 | MR2508/0416 |  | 220KV_220 KV Chhatarpur- Tikamgarh CKT | 220KV_CHATARPUR | NON-OCCM-MP | for CT Tan delta Measurement work | 31-08-2025 09:30:00 | 31-08-2025 13:30:00 | Brajendra Soni | 9131327770 | ok
3 | 2025-08-30 14:28 | MR2508/0417 |  | 132KV_132 KV Chhatarpur-Khajuraho CKT-2 | 220KV_CHATARPUR | NON-OCCM-MP | for CT Tan Delta Measurement work | 31-08-2025 14:00:00 | 31-08-2025 17:30:00 | Brajendra Soni | 9131327770 | ok, 132kv chhatarpur-khajuraho tap lavkushnagar Ckt should be in service
4 | 2025-08-12 17:39 | MR2508/0176 | Daily | 220KV_220KV South Zone (Indore) â¿¿ Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok line to be in service through sub ld
5 | 2025-08-12 17:20 | MR2508/0174 | Daily | 220KV_220KV South Zone (Indore) â¿¿ Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | . Replacement existing of 24 Fibre OPGW by 48 Fibr | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok line to be in service through sub ld
6 | 2025-08-29 11:42 | MR2508/0399 | Daily | 220KV_220KV Indore (400KV â¿¿ Mangliya Line. | 220KV_INDORE-SZ | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre | 29-08-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217 | data rerouting and confirmation from communication required
7 | 2025-08-30 10:24 | MR2508/0413 | Daily | 220KV_220KV Indore (400KV) â¿¿ South Zone (I/C- 3) Line | 220KV_INDORE-SZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 30-08-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217 | data rerouting and confirmation from communication required
8 | 2025-08-29 13:01 | MR2508/0403 | Daily | 220KV_220KV Indore (400KV â¿¿ Mangliya Line. | 220KV_INDORE-SZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 29-08-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217 | data rerouting and confirmation from communication required
9 | 2025-08-26 18:22 | MR2508/0354 | Continuous | 132KV_132 KV JBP-SAHPURA DP LINE | 220KV_JABALPUR | OCCM-MP | REPLACEMENT OF TOWER LOC NO 5 | 28-08-2025 10:00:00 | 02-09-2025 19:00:00 | RAJESH TIWARI | 7898239595 | continue
10 | 2025-08-12 17:42 | MR2508/0177 | Daily | 220KV_220KV Mangliya -Jaitpura Line | 220KV_MANGLIA2 | NON-OCCM-MP | 24 Fibre OPGW by 48 Fibre OPGW work | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok line to be in service through sub ld
11 | 2025-08-12 17:23 | MR2508/0175 | Daily | 220KV_220KV Mangliya -Jaitpura Line. | 220KV_MANGLIA2 | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok line to be in service through sub ld
12 | 2025-08-29 11:47 | MR2508/0400 | Daily | 220KV_220KV Indore (400KV) â¿¿ South Zone (I/C- 3) Line | 220KV_MANGLIA2 | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre | 29-08-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217 | data rerouting and confirmation from communication required
13 | 2025-08-29 13:05 | MR2508/0404 | Daily | 220KV_220KV Indore (400KV) â¿¿ South Zone (I/C- 3) Line | 220KV_MANGLIA2 | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 29-08-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217 | data rerouting and confirmation from communication required
14 | 2025-08-30 10:28 | MR2508/0414 | Daily | 220KV_220KV Indore (400KV â¿¿ Mangliya Line. | 220KV_MANGLIA2 | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 30-08-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217
15 | 2025-08-30 14:52 | MR2508/0418 |  | 132KV_40 MVA Transformer -I | 132KV_MEGHNAGAR | NON-OCCM-MP | for replacement of Y-Phase damaged conductor from | 31-08-2025 09:00:00 | 31-08-2025 11:00:00 | Er.Manoj Randa | 9425820034 | sub ld
16 | 2025-08-28 14:51 | MR2508/0384 |  | 220KV_220 KV MAIN BUS | 220KV_UJJAIN | NON-OCCM-MP | Hot point & Main bus maintanance work | 31-08-2025 09:00:00 | 31-08-2025 17:00:00 | B.C JOSHI | 7587951137 | WRLDC Consent required for 220kv PGCIL ckt I&II And if emergency can s/d should be applied in emergency formet for submission to WRLDC
17 | 2025-08-28 14:51 | MR2508/0385 |  | 220KV_220 KV MAIN BUS | 220KV_UJJAIN | NON-OCCM-MP | Hot point & Main bus maintanance work | 31-08-2025 09:00:00 | 31-08-2025 17:00:00 | B.C JOSHI | 7587951137
18 |  |  |  | MANDSAUR-MP - 400KV - BUS 1 |  | MADHYA PRADESH | for jumpering work of new bay of upcoming 500MVA ICT | 2025-08-31 08:00 | 2025-08-31 18:00 |  |  | OK T SUB LD
19 |  |  |  | SAGAR - 400KV - BUS 1 |  | MADHYA PRADESH | For Erection work of Pantograph Isolator beneath the bus in the existing bay for 125 MVAR reactor | 2025-08-31 08:00 | 2025-08-31 18:00 |  |  | ok
20 |  |  |  | BIRSINGPUR - 400KV - BUS 2 |  | MADHYA PRADESH | Bus outage is required to avoid the induction, as activities related to IPS tube connection is going on | 2025-08-31 08:00 | 2025-08-31 17:00 |  |  | ok
21 |  |  |  | 400KV-BINA-MP-BINA-4 |  | POWERGRID_WR2 | Simultaneous ouatge of 765KV/400KV BINA-ICT-1 & 400KV-BINA-MP-BINA-4 required for Bay-423 LBB Testing.Dia to be kept open at both ends. | 2025-08-31 08:00 | 2025-08-31 15:00 |  |  | OK
22 |  |  |  | 220KV-ANNUPUR-KOTMIKALA-1 |  | MADHYA PRADESH,CHATTISGARH | FOR LINE MAINTENANCE WORK | 2025-08-31 08:00 | 2025-08-31 18:00 |  |  | OK