## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
Control Area : | ALL | Circle : | ALL | 2025-09-12 15:06
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-09-11 15:06 | MR2509/0268 |  | 132KV_132 KV Markendey (WRD) bay only | 132KV_AMARPATAN | NON-OCCM-MP | for wiring in take of gantry to dead end | 12-09-2025 10:00:00 | 12-09-2025 16:00:00 | Arun Kol | 9425426476 | OK, NO BAY SHIFTING & NO NEW ELEMENT TO BE CHARGED
2 | 2025-09-11 15:07 | MR2509/0269 |  | 132KV_132 KV Markendey (WRD) bay only | 132KV_AMARPATAN | NON-OCCM-MP | for wiring in take of gantry to dead end | 12-09-2025 10:00:00 | 12-09-2025 16:00:00 | Arun Kol | 9425426476 | OK, NO BAY SHIFTING & NO NEW ELEMENT TO BE CHARGED
3 | 2025-09-11 14:19 | MR2509/0260 |  | 132KV_Shutdown (H/T) of 132 KV Amarpatan-Jhinna DCSS line | 132KV_AMARPATAN | NON-OCCM-MP | Jumper tightening & other maintenance work | 12-09-2025 09:00:00 | 12-09-2025 17:00:00 | Mr. Ajay Kumar Chaurasia | 9425805081 | OK, NO BAY SHIFTING & NO NEW ELEMENT TO BE CHARGED
4 | 2025-09-11 11:10 | MR2509/0254 |  | 132KV_SEONI-AMARWARA_Ckt | 132KV_AMARWARA | NON-OCCM-MP | LA shifting work. | 12-09-2025 10:00:00 | 12-09-2025 17:00:00 | S.K.Okte | 7587951132 | OK
5 | 2025-08-25 15:12 | MR2508/0327 | Daily | 220KV_220KV Anuppur Kotmikala ckt-I | 220KV_ANUPPUR | NON-OCCM-MP | Low Ground clearance maintenance work at loc. 371- | 09-09-2025 08:00:00 | 17-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
6 | 2025-09-11 14:38 | MR2509/0262 |  | 220KV_220 KV ASHTA-CHAPDA | 400KV_ASHTA4 | NON-OCCM-MP | TAN DELTA MEASUREMENTS OF CT | 12-09-2025 13:00:00 | 12-09-2025 16:00:00 | JITENDRA LOHANA | 9425804978 | OK THROUGH SUB LD
7 | 2025-09-11 14:35 | MR2509/0261 |  | 220KV_220 KV ASHTA-DEWAS | 400KV_ASHTA4 | NON-OCCM-MP | TAN DELTA MEASUREMENT OF CT | 12-09-2025 09:00:00 | 12-09-2025 12:00:00 | JITENDRA LOHANA | 9425804978 | OK THROUGH USB LD
8 | 2025-09-06 15:08 | MR2509/0153 | Daily | 132KV_132 kV Shahdol-Birsingpur Circuit I | 220KV_BIRSINGHPUR | NON-OCCM-MP | Replacement of damaged OPGW | 07-09-2025 09:00:00 | 13-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
9 | 2025-09-11 17:00 | MR2509/0277 |  | 132KV_132KV Mandsaur Budha Line | 132KV_BUDHA | NON-OCCM-MP | For Maintenance work | 12-09-2025 11:00:00 | 12-09-2025 16:00:00 | Gaurav Goyal | 9425805120 | SUB LD
10 | 2025-09-11 13:03 | MR2509/0256 |  | 220KV_160 MVA-I X-Mer (AREVA) | 400KV_CHHEGAON4 | NON-OCCM-MP | Post monsoon maintenance | 12-09-2025 10:00:00 | 12-09-2025 18:00:00 | Shri Ganesh Mansare | 9425802441 | OK THROUGH SUB LD
11 | 2025-09-11 15:38 | MR2509/0273 |  | 132KV_50 MVA BBL X-mer | 132KV_DAMOH1 | NON-OCCM-MP | Post monsoon maintenance | 12-09-2025 10:00:00 | 12-09-2025 17:00:00 | B K Sahu | 9425801433 | OK O&M TO BE INTIMATED
12 | 2025-09-06 15:08 | MR2509/0154 | Daily | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | Replacement of damaged OPGW | 07-09-2025 09:00:00 | 13-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
13 | 2025-09-07 13:02 | MR2509/0161 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-2 | 220KV_INDORE NORTH | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
14 | 2025-09-07 12:51 | MR2509/0159 | Daily | 132KV_132KV North Zone- Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
15 | 2025-09-07 12:45 | MR2509/0158 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
16 | 2025-06-30 16:18 | MR2506/0637 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 08-09-2025 09:00:00 | 13-09-2025 18:00:00 | PANKAJ YADAV | 9406713326 | DEFERRED
17 | 2025-06-30 15:35 | MR2506/0627 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 08-09-2025 09:00:00 | 13-09-2025 08:00:00 | PANKAJ YADAV | 9406713326 | DEFERRED
18 | 2025-09-11 14:54 | MR2509/0267 |  | 132KV_132 KV Khurai-Sagar Ckt | 132KV_KHURAI | NON-OCCM-MP | For line maintenance work. | 12-09-2025 09:00:00 | 12-09-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | OK
19 | 2025-09-11 16:15 | MR2509/0274 |  | 132KV_50mva x-mer BBL | 132KV_KOTHIYA | NON-OCCM-MP | post mansoon maintenance | 12-09-2025 11:00:00 | 12-09-2025 17:00:00 | RAKESH SUMAN | 7587951093 | SUB LD
20 | 2025-09-11 14:42 | MR2509/0263 |  | 33KV_33 KV Main bus and both x-mer | 220KV_MAIHAR | NON-OCCM-MP | attending 33 kv main bus sec.isolator hot point | 12-09-2025 09:00:00 | 12-09-2025 12:00:00 | Arun kumar | 9425802368 | OK ONLY IF O&M CONSENT PROVIDED
21 | 2025-09-11 14:42 | MR2509/0264 |  | 33KV_33 KV Main bus and both x-mer | 220KV_MAIHAR | NON-OCCM-MP | attending 33 kv main bus sec.isolator hot point | 12-09-2025 09:00:00 | 12-09-2025 12:00:00 | Arun kumar | 9425802368 | OK ONLY IF O&M CONSENT PROVIDED
22 | 2025-09-11 16:57 | MR2509/0276 |  | 132KV_132KV Mandsaur(400KV)- Malharagarh | 132KV_MALHARGARH | NON-OCCM-MP | for Maintenance work | 12-09-2025 10:00:00 | 12-09-2025 18:00:00 | Gaurav Goyal | 9425805120 | SUB LD
23 | 2025-09-11 14:47 | MR2509/0266 |  | 220KV_220KV Mehgaon Auraiya line | 220KV_MEHGAON | OCCM-MP | Line Maintenanace Work | 12-09-2025 09:00:00 | 12-09-2025 17:00:00 | Baidyanath Bhattacharya | 6265588473 | OK THROUGH SUB LD
24 | 2025-09-11 14:47 | MR2509/0265 |  | 132KV_132/33 kv 63 MVA BBL X-MER no.II | 220KV_NARSINGHPUR | NON-OCCM-MP | post monsoon maintenance work | 12-09-2025 10:30:00 | 12-09-2025 18:00:00 | Dinesh Kumar kushwaha | 9425801319 | OK O&M TO BE INTIMATED
25 | 2025-09-11 15:35 | MR2509/0272 |  | 220KV_220KV Neemuch Mandsaur Circuit IInd | 220KV_NEEMUCH | NON-OCCM-MP | For Maintenance work | 12-09-2025 12:00:00 | 12-09-2025 16:00:00 | Gaurav Goyal | 9425805120 | DEFERRED FROM SITE
26 | 2025-09-11 15:32 | MR2509/0271 |  | 220KV_220KV Neemuch-Mandsaur Circuit Ist | 220KV_NEEMUCH | NON-OCCM-MP | For Maintenance work | 12-09-2025 10:00:00 | 12-09-2025 18:00:00 | Gaurav Goyal | 9425805120 | DEFERRED FROM SITE
27 | 2025-09-07 12:39 | MR2509/0157 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line. | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
28 | 2025-09-07 12:57 | MR2509/0160 | Daily | 132KV_132KV Niranjanpur - Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
29 | 2025-09-02 18:36 | MR2509/0064 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line.&132KV Niranjanpur - Jaitpura Line &132KV North Zone- Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
30 | 2025-09-11 15:17 | MR2509/0270 |  | 220KV_220 kV Panagar- Amarkantak | 220KV_PANAGAR | NON-OCCM-MP | Disc Replacement work at loc. 218 T Ph & 235 T Ph | 12-09-2025 10:00:00 | 12-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
31 | 2025-09-11 14:02 | MR2509/0258 |  | 132KV_132 kv bus-coupler | 132KV_RATLAM1 | NON-OCCM-MP | for safety purpose | 12-09-2025 09:00:00 | 12-09-2025 18:00:00 | NIKHIL DUNGE | 9425801487 | SUB LD
32 | 2025-09-11 13:57 | MR2509/0257 |  | 132KV_50 MVA X-MER-II nd (BBL) | 132KV_RATLAM1 | NON-OCCM-MP | For post monsoon maintenance & testing work | 12-09-2025 09:00:00 | 12-09-2025 18:00:00 | NIKHIL DUNGE | 9425801487 | SUB LD
33 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | CONTINUE
34 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | RAJESH TIWARI | 7898239595 | CONTINUE
35 | 2025-09-11 14:12 | MR2509/0259 |  | 20MVA_132/33KV_CGL_X'mer_2 | 132KV_WAIDHAN | OCCM-MP | Replacement of all 03 phase CT due to high tan del | 12-09-2025 09:00:00 | 12-09-2025 17:00:00 | R.B. Singh | 9907230394 | OK O&M TO BE INTIMATED
36 |  | 260552 |  | 400KV-BHOPAL-MP-BHOPAL-BDTCL-2 |  | WR-OCCM | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 12-09-2025 09:00:00 | 12-09-2025 18:00:00 |  |  | OK THROUGH SUB LD, .400kV BHOPAL-MP -BHOPAL-BDTCL -Q1 Sensitivity of 91.87% and All other lines at BHOPAL-MP - 400KV and BHOPAL-BDTCL - 400KV to be in service with A/R Enabled
37 |  | 260588 |  | 220KV-HOSHANGABAD-ITARSI-2 |  | WR-OCCM | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 12-09-2025 09:00:00 | 12-09-2025 18:00:00 |  |  | OK THROUGH SUB LD All other 220KV lines at HOSHANGABAD will be in service. Load will be managed by SLDC MP. WR-2 to be informed.
38 |  | 260589 |  | 220KV-MEHGAON-AURIYA-1 |  | WR-OCCM | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 12-09-2025 09:00:00 | 12-09-2025 17:00:00 |  |  | OK THROUGH SUB LD All other circuits from Mehgaon & Auriya to be inservice. NLDC consent required.
39 |  | 262505 |  | 220KV-ANNUPUR-KOTMIKALA-1 |  | WR-OCCM | For Re-sagging work due to Low Ground clearance at loc. 371-379 & 464- 475 | 12-09-2025 08:00:00 | 12-09-2025 17:59:00 |  |  | OK All other lines at Annuppur/Kotmikala to be in service with AR enabled. Load to be managed by SLDC MP/CG
40 |  | 265822 |  | 220KV-INDORE-INDORE NORTH ZONE-1 |  | WR-OCCM | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO | 12-09-2025 07:00:00 | 12-09-2025 23:59:00 |  |  | OK LINE TO BE IN SERVICE A/R in N/A, Line will be in service.
41 |  | 265842 |  | 220KV-INDORE-INDORE NORTH ZONE-2 |  | WR-OCCM | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO | 12-09-2025 07:00:00 | 12-09-2025 19:59:00 |  |  | OK LINE TO BE IN SERVICE A/R in N/A, Line will be in service.