## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-09 |  |  | APPROVED OUTAGE LIST FOR DTD.09.10.25
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-03 12:03 | MR2510/0056 | Daily | 220KV_220 kV Adampur-Hoshangabad line | 220KV_ADAMPUR | NON-OCCM-MP | Defective Disc replacement work | 04-10-2025 09:00:00 | 14-10-2025 17:00:00 | Ankit Mehroliya | 9425804506 | ok, through sub ld
2 | 2025-10-08 12:05 | MR2510/0202 |  | 132KV_63 MVA and 40 MVA Xmer | 132KV_AMARPATAN | NON-OCCM-MP | Station Xmer jumper removing and shifting | 09-10-2025 09:00:00 | 09-10-2025 11:00:00 | Arun Kumar | 9131207339 | OK
3 | 2025-10-08 14:49 | MR2510/0224 |  | 220KV_220kV AShoknagar- Guna line | 220KV_ASHOKNAGAR | NON-OCCM-MP | Post Mansoon Bay Maintenance | 09-10-2025 10:00:00 | 09-10-2025 17:00:00 | Rakesh Suman | 7587951093 | ok, through sub ld
4 | 2025-10-08 16:18 | MR2510/0238 |  | 220KV_220 KV Badnagar â¿¿ Indore line | 220KV_BADNAGAR | NON-OCCM-MP | for Line maintenance work | 09-10-2025 09:00:00 | 09-10-2025 17:00:00 | Kumar Vishal | 9425805018 | deffered due to sd on Badnawar ICT
5 | 2025-10-08 14:16 | MR2510/0217 |  | 220KV_220/132kv 160mva xmer cgl | 220KV_BADNAGAR | OCCM-MP | For Post maintenance work & testing work | 09-10-2025 00:00:00 | 09-10-2025 18:00:00 | Poshkar kushwaha | 9425813990 | ok, through sub ld
6 | 2025-10-08 14:44 | MR2510/0222 |  | 400KV_315MVA ICT -2ND T&R | 400KV_BADNAWAR | NON-OCCM-MP | POST MANSOON MAINTENANCE & TESTING WORK | 09-10-2025 08:00:00 | 09-10-2025 18:00:00 | ABHISHEK VERMA | 9340855901 | ok, through sub ld
7 | 2025-10-08 10:02 | MR2510/0195 |  | 220KV_160MVA XMER-I AREVA | 220KV_BADOD | NON-OCCM-WR | TRANSFORMER TESTING & PMM WORK | 09-10-2025 09:00:00 | 09-10-2025 17:30:00 | ER Y K RATHORE | 9425804968 | ok, through sub ld
8 | 2025-10-08 10:04 | MR2510/0196 |  | 220KV_220KV BAROD-UJJAIN CKT-I | 220KV_BADOD | NON-OCCM-WR | DPR RELAY SETTING WORK & HAND TRIP ONLY BAROD END | 09-10-2025 12:30:00 | 09-10-2025 14:30:00 | ER Y K RATHORE | 9425804968 | ok, through sub ld
9 | 2025-10-08 14:51 | MR2510/0225 |  | 220KV_220KV Main Bus section-l | 220KV_BARWAHA | NON-OCCM-MP | for Hot point attending work | 09-10-2025 09:00:00 | 09-10-2025 15:00:00 | Er.Imran Beg | 9425805200 | deferred due to high isp and osp generation
10 | 2025-10-08 15:32 | MR2510/0234 |  | 132KV_20 MVA GEC _X-MER | 220KV_BETUL | NON-OCCM-MP | Erection work of new 63 MVA TAL X-mer | 09-10-2025 10:00:00 | 09-10-2025 17:00:00 | Vishal kumar Malviya | 9425804955 | sub ld
11 | 2025-10-01 12:35 | MR2510/0006 | Continuous | 400KV_315 MVA X-MER NO-3BHEL | 400KV_BHOPAL4 | NON-OCCM-MP | Post Monsoon Maintenance & Testing work | 08-10-2025 09:00:00 | 09-10-2025 18:00:00 | Er. Akram Khan | 9425804695 | ok, through sub ld
12 | 2025-10-08 11:13 | MR2510/0199 |  | 132KV_50 MVA BBL x-mer | 132KV_BICHHIYA | NON-OCCM-MP | Post monsoon maintenance work | 09-10-2025 11:00:00 | 09-10-2025 18:00:00 | S. k. Jain | 9425385281 | OK
13 | 2025-10-08 15:16 | MR2510/0229 |  | 132KV_40 MVA (BBL) X-mer | 132KV_CHANDERI | NON-OCCM-MP | Post Monsoon Maintenance work. | 09-10-2025 10:00:00 | 09-10-2025 17:00:00 | Lalit singh | 9425806845 | o & m consent required
14 | 2025-10-08 14:48 | MR2510/0223 |  | 220KV_160 MVA tranformer-I make BBL | 220KV_DALODA | NON-OCCM-MP | Post monsoon maintenance work. | 09-10-2025 10:00:00 | 09-10-2025 17:00:00 | Er. Shailendra Bourasi | 9907246485 | ok, through sub ld
15 | 2025-09-18 17:16 | MR2509/0453 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 06-10-2025 09:00:00 | 11-10-2025 18:00:00 | SHRI M. M. BAIG | 9425805067 | deferred
16 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | deferred
17 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | deferred
18 | 2025-10-08 12:36 | MR2510/0206 |  | 220KV_160MVAX-MER 1 ALSTOM | 220KV_GANJBASODA | NON-OCCM-MP | POST MANSOON MAINTANCE | 09-10-2025 08:00:00 | 09-10-2025 17:00:00 | P K VERMA | 9425804364 | ok, through sub ld
19 | 2025-10-08 15:33 | MR2510/0235 |  | 132KV_40MVA XMER BBL | 132KV_GOURJHAMAR | NON-OCCM-MP | POST MANSOON MAINTENANCE AND TESTING WORK | 09-10-2025 11:00:00 | 09-10-2025 18:00:00 | PD GOUTAM | 9425808329 | OK
20 | 2025-10-08 13:15 | MR2510/0210 |  | 160MVA_220/132KV_BHEL_X'mer_3 | 220KV_HANDIYA | NON-OCCM-MP | Post monsoon Maint. & Testing Work | 09-10-2025 10:00:00 | 09-10-2025 17:00:00 | K.R. Dongre | 9424430754 | real time
21 | 2025-10-04 12:27 | MR2510/0086 | Daily | 220KV_220 KV Hoshangabad-Adampur | 220KV_HOSHANGABAD | NON-OCCM-MP | Resagging work b/w loc.no. 20 of lilo to 71 | 05-10-2025 09:00:00 | 10-10-2025 17:00:00 | Ashutosh Rai | 9425806902 | as opportunity shutdown
22 | 2025-10-08 13:37 | MR2510/0213 | Continuous | 132KV_132 Kv North Zone- Chambal ckt -2 Line | 220KV_INDORE-NZ | NON-OCCM-MP | Conductor Replacement Work | 08-10-2025 21:30:00 | 09-10-2025 06:00:00 | A.R. Kanel | 9425805217 | sub ld
23 | 2025-10-06 10:09 | MR2510/0124 |  | 220KV_220KV INDORE BADNAGAR LINE | 400KV_INDORE4 | NON-OCCM-MP | POST MONSOON MAINTENANCE | 09-10-2025 09:00:00 | 09-10-2025 17:00:00 | ATUL PARADKAR | 9425804929 | deffered due to sd on Badnawar ICT
24 | 2025-10-06 14:03 | MR2510/0134 |  | 132KV_132/33KV 40 MVA IMP-1 X-MER | 132KV_KARAPGAON | NON-OCCM-MP | SD For Post monsoon maintenance and testing work | 09-10-2025 11:00:00 | 09-10-2025 17:00:00 | Ranjeet kumar Kori | 9425806701 | o & m consent required
25 | 2025-09-18 12:55 | MR2509/0410 | Continuous | 400KV_400KV DAMOH - KATNI LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 06-10-2025 09:00:00 | 11-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | deferred
26 | 2025-10-08 14:43 | MR2510/0221 |  | 132KV_40MVA BBL X-MER | 400KV_KATNI4 | NON-OCCM-MP | Replacement of 33kv ct & 33kv half bus maintenance | 09-10-2025 10:00:00 | 09-10-2025 14:00:00 | SK Chaturvedi | 9425806938 | O&M CONSENT REQUIRED
27 | 2025-10-08 12:47 | MR2510/0207 |  | 63MVA_132/33KV_EMCO_X'mer_2 | 132KV_KHAPASWAMI | NON-OCCM-MP | Post monsoon maint.work | 09-10-2025 11:00:00 | 09-10-2025 17:00:00 | Er Sk OKTE | 7587951132 | OK
28 | 2025-10-08 13:48 | MR2510/0215 |  | 132KV_132 KV Khurai-Sagar Ckt | 132KV_KHURAI | NON-OCCM-MP | for F/o disc replacement & other line mainte | 09-10-2025 10:00:00 | 09-10-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | ok
29 | 2025-10-08 15:28 | MR2510/0233 |  | 132KV_132 Aux. Bus | 132KV_MADWAS | NON-OCCM-MP | Isolator to Aux. Bus Jumpring work | 09-10-2025 09:00:00 | 09-10-2025 18:00:00 | J N Singh | 9425802388 | ok
30 | 2025-10-08 15:11 | MR2510/0227 |  | 220KV_160 MVA X-MER MAKE BBL | 220KV_MALANPUR | NON-OCCM-MP | POST MONSOON MAINTENANCE WORK | 09-10-2025 10:00:00 | 09-10-2025 17:00:00 | VIKRAM AHIRWAR | 9425805415 | ok, through sub ld
31 | 2025-10-05 10:37 | MR2510/0101 | Daily | 132KV_132KV Neemuch Manasa Line | 132KV_MANASA | NON-OCCM-MP | Re sagging and line maintanence work | 06-10-2025 08:00:00 | 12-10-2025 18:00:00 | Gaurav goyal | 9425805120 | sub ld
32 | 2025-10-08 11:00 | MR2510/0197 |  | 132KV_40 MVA BBL-I X-MER | 132KV_MANGAWAN | NON-OCCM-MP | FOR POST MONSOON MAINT.&TESTING WORK | 09-10-2025 10:00:00 | 09-10-2025 17:00:00 | KANISHKA SINGH | 9425804656 | OK
33 | 2025-10-08 14:06 | MR2510/0216 |  | 132KV_40MVA Transformer-I Emco | 132KV_MEGHNAGAR | NON-OCCM-MP | For Post monsoon maintenance work | 09-10-2025 10:00:00 | 09-10-2025 18:00:00 | Er.Kamesh Ninama | 9713485920 | sub ld
34 | 2025-10-08 13:20 | MR2510/0211 |  | 400KV_400KV Nagda-ISP Line | 400KV_NAGDA4 | OCCM-MP | Line Maintenance work. | 09-10-2025 10:00:00 | 09-10-2025 18:00:00 | Kamal Solanki | 9425806262 | deferred due to high isp generation
35 | 2025-10-08 14:37 | MR2510/0219 |  | 400KV_50MVAR line reactor Of ISP ckt | 400KV_NAGDA4 | NON-OCCM-MP | Post monsoon maintenance and testing work | 09-10-2025 10:30:00 | 09-10-2025 17:00:00 | Sunil Bamniya | 9425820045 | as per voltage profile
36 | 2025-10-08 16:05 | MR2510/0237 |  | 220KV_220 KV Narsinghpur-Chichli Line | 220KV_NARSINGHPUR | NON-OCCM-MP | Flashover disc replacement work at loc.No.283/B-Ph | 09-10-2025 10:00:00 | 09-10-2025 18:00:00 | Ashish Kumar | 9425805935 | ok
37 | 2025-10-08 11:24 | MR2510/0201 |  | 132KV_132 KV Pichhore Shivpuri Line | 220KV_PICHHORE | NON-OCCM-MP | Flash over disc replacement work | 09-10-2025 09:30:00 | 09-10-2025 17:30:00 | Satish Kumar Bhagat | 9425806916 | sub ld
38 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | deferred
39 | 2025-10-08 11:10 | MR2510/0198 |  | 220KV_220/132KV 160MAV BHEL X-MER | 220KV_RATANGARH | NON-OCCM-WR | Post Monsoon Maintenance work | 09-10-2025 10:00:00 | 09-10-2025 17:00:00 | Sh. S.H. Mansuri | 7587951068 | ok, through sub ld
40 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | deferred
41 | 2025-10-08 15:12 | MR2510/0228 |  | 132KV_Shutdown (H/T) of 132 kv Rewa Interconnector Ckt-1 Feeder | 220KV_REWA | NON-OCCM-MP | Jumper tightening & other maintenance work | 09-10-2025 11:00:00 | 09-10-2025 17:00:00 | Mr. Ajay Kumar Chaurasia | 9425805081 | deferred
42 | 2025-10-07 11:47 | MR2510/0163 |  | 220KV_220kv Sabalgarh Adanil Ckt | 220KV_SABALGARH | OCCM-MP | Line Maintenance work | 09-10-2025 09:00:00 | 09-10-2025 17:00:00 | SURAJ PAWAR | 9425814079 | ok, through sub ld
43 | 2025-10-08 15:28 | MR2510/0232 |  | 400KV_400/220KV 315MVA TRANSFORMER CGL-2 | 400KV_SAGAR | NON-OCCM-MP | POSTMANSOON MAINTENANCE AND TESTING WORK | 09-10-2025 09:00:00 | 09-10-2025 18:00:00 | SRAJAN SISODIYA | 7879960163 | real time
44 | 2025-10-08 13:42 | MR2510/0214 |  | 132KV_132/33 KV 20 MVA GEC X-MER | 220KV_SIDHI | NON-OCCM-MP | 132 KV SIDE Y-PHASE C.T. REPLECE DUE TO HIGH TAN D | 09-10-2025 09:00:00 | 09-10-2025 18:00:00 | S.K. SHAHU | 9425613436 | OK
45 | 2025-10-04 17:53 | MR2510/0097 |  | 400KV_400KV Pithampura-I for PMU commissioning work by MPPTCL | 400KV_SINGHAJI TPS | NON-OCCM-MP | commissioning of PMU at SSTPP PH-I | 09-10-2025 10:00:00 | 09-10-2025 18:00:00 | Deepak Sharma | 8005696855 | ok, through sub ld
46 | 2025-10-08 12:09 | MR2510/0203 |  | 220KV_220/33KV 50MVA BHEL X-MER-1 | 220KV_SUKHA | NON-OCCM-MP | POSTMONSOON MAINT.AND TESTING WORK | 09-10-2025 10:00:00 | 09-10-2025 17:00:00 | ASHISH SONKESHARIYA | 7587951153 | OK
47 | 2025-10-08 16:32 | MR2510/0239 |  | 220KV_160 MVA 1st Emco make transformer | 220KV_TIKAMGARH | NON-OCCM-MP | Post mansoon maintenance | 09-10-2025 09:00:00 | 09-10-2025 17:00:00 | Pushpendra Kumar soni | 9425806398 | ok
48 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | continuous
49 | 2025-10-08 13:07 | MR2510/0208 |  | 40MVA_132/33KV_BBL_Xmer_2 | 132KV_UMRETH | NON-OCCM-MP | POST MANSOON MAINTENANCE WORK | 09-10-2025 08:00:00 | 09-10-2025 14:00:00 | A A QURESHI | 9425804318 | OK
50 | 2025-10-08 13:34 | MR2510/0212 |  | 132KV_50 MVA X-mer-2 (BBL) | 132KV_WARASEONI | NON-OCCM-MP | Post monsoon maint. Work | 09-10-2025 09:00:00 | 09-10-2025 17:00:00 | Swati Bisen | 9425801737 | OK
51 | 2025-10-08 13:34 |  |  | 400KV-BINA-MP-GUNA-MP-2 |  | OCCM-WR | AMP work. | 09-Oct-2025 | 09:00 | 09-Oct-2025 | 18:00 | ok, shall be given only of testing of NHPTL gets completed
52 | 2025-10-08 13:34 |  |  | 400KV-BADNAWAR-RAJGARH-2 |  | OCCM-WR | For R-Phase CVT Replaement of Line, Non auto mode of ckt 1 is required for opportunity work in line . Dia to be kept open at both ends. | 09-Oct-2025 | 09:30 | 09-Oct-2025 | 18:00 | ok, through sub ld
53 | 2025-10-08 13:34 |  |  | 400KV-SSP-RAJGARH-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 09-Oct-2025 | 08:00 | 09-Oct-2025 | 18:00 | real time
54 | 2025-10-08 13:34 |  |  | 220KV-GWALIOR-GWALIOR-II-1 |  | OCCM-WR | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 09-Oct-2025 | 09:00 | 09-Oct-2025 | 17:00 | real time
55 | 2025-10-08 13:34 |  |  | 220KV-KHANDWA-CHHANERA-2 |  | OCCM-WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 09-Oct-2025 | 08:00 | 09-Oct-2025 | 18:00 | real time
56 | 2025-10-08 13:34 |  |  | 220KV-MORENA-SABALGARH-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 09-Oct-2025 | 09:00 | 09-Oct-2025 | 17:00 | ok, through sub ld
57 | 2025-10-08 13:34 |  |  | 132KV-SHEOPUR-KHANDAR-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 09-Oct-2025 | 09:00 | 09-Oct-2025 | 17:00 | real time
58 | 2025-10-08 13:34 |  |  | 132KV-KIRNAPUR-DONGARGARH-1 |  | OCCM-WR | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 09-Oct-2025 | 09:00 | 09-Oct-2025 | 17:00 | real time
S/I ,SLDC MPPTCL JABALPUR.