## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-16
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-15 15:59 | MR2510/0462 |  | 132KV_132kv 40mva xmer make bbl | 220KV_BADNAGAR | OCCM-MP | For Transformer painting work | 16-10-2025 09:00:00 | 16-10-2025 17:00:00 | Poshkar kushwaha | 9425813990 | sub ld
2 | 2025-10-13 10:21 | MR2510/0350 | Continuous | 400KV_315 MVA X-MER NO.-4 | 400KV_BHOPAL4 | NON-OCCM-MP | FOR POST-MONSOON MAINT. & TESTING WORK | 15-10-2025 09:00:00 | 16-10-2025 18:00:00 | AKRAM KHAN | 9425804695 | Deffered due to s/d on 220 KV Itarsi(PGCIL)-Hoshangabad Ckt-II
3 | 2025-10-15 14:49 | MR2510/0457 |  | 132KV_BADA MALHERA-BIJAWAR_Ckt | 132KV_BIJAWAR | NON-OCCM-MP | FOR DAMAGED CONDUCTOR REPLACEMENT WORK | 16-10-2025 14:00:00 | 16-10-2025 17:00:00 | BRAJENDRA SONI | 9131327770 | ok
4 | 2025-10-15 14:58 | MR2510/0458 |  | 132KV_132 KV CHHATARPUR-BIJAWAR-TAP NOWGAON | 132KV_BIJAWAR | NON-OCCM-MP | FOR DAMAGED CONDUCTOR REPLACEMENT WORK | 16-10-2025 10:00:00 | 16-10-2025 13:00:00 | BRAJENDRA SONI | 9131327770 | ok
5 | 2025-10-08 16:46 | MR2510/0240 |  | 400KV_400 KV main bus-1 | 400KV_BINA4 | NON-OCCM-MP | for stringing and extension of main bus-1 | 16-10-2025 09:00:00 | 16-10-2025 17:00:00 | Anil mahor | 9425805149 | Deffered due to non approval in WR list and also due to SC test of NHPTL
6 | 2025-10-15 14:03 | MR2510/0456 |  | 400KV_400KV Guna-II 80MVAr(CGL) Line Reactor | 400KV_BINA4 | NON-OCCM-MP | Post-monsoon maintenance & testing work | 16-10-2025 09:00:00 | 16-10-2025 14:00:00 | P.N. namdeo | 9039472058 | Deffered due to SC test of NHPTL
7 | 2025-10-15 13:26 | MR2510/0454 |  | 220KV_220 kV Chhegaon - Khandwa (PGCIL) Ckt 1st | 400KV_CHHEGAON4 | OCCM-WR | For Flashover Disc Replacement & Other Line Maint. | 16-10-2025 08:00:00 | 16-10-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, through sub ld
8 | 2025-09-18 17:20 | MR2509/0454 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 13-10-2025 09:00:00 | 18-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deffered
9 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
10 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
11 | 2025-10-15 13:31 | MR2510/0455 |  | 132KV_132kV Anuppur - Dongrital Ckt | 132KV_DONGRITAL | NON-OCCM-MP | Disc Replacement Work. | 16-10-2025 08:00:00 | 16-10-2025 17:00:00 | G.L Sahu | 9425805102 | ok
12 | 2025-10-13 16:19 | MR2510/0397 |  | 220KV_220 KV HOSHANGABAD - PGCIL NO. 2 FEEDER | 220KV_HOSHANGABAD | NON-OCCM-MP | POST MANSOON MAINTENANCE & TESTING WORK | 16-10-2025 09:00:00 | 16-10-2025 17:00:00 | V.P.DWIVEDI | 9425804799 | as opportunity s/d
13 | 2025-10-13 16:47 | MR2510/0401 |  | 220KV_220 KV Itarsi(PGCIL)-Hoshangabad Ckt-II | 220KV_HOSHANGABAD | OCCM-MP | Disc washing & etc work(OCCM Approved) | 16-10-2025 09:00:00 | 16-10-2025 17:00:00 | Ashutosh Rai | 9425806902 | ok, through sub ld, ckt shall be normalised by 15 hrs positively looking to increasing load.
14 | 2025-10-14 11:30 | MR2510/0405 |  | 220KV_220KV Indore-South zone-2 | 400KV_INDORE4 | NON-OCCM-MP | For post monsoon maintenance work and ten delta me | 16-10-2025 09:00:00 | 16-10-2025 17:00:00 | Er.ATUL PARADKAR | 9425804929 | ok, through sub ld
15 | 2025-10-15 11:21 | MR2510/0450 |  | 220KV_220KV TBC breaker & bay | 400KV_INDORE4 | NON-OCCM-MP | for post monsoon maintenance work | 16-10-2025 10:00:00 | 16-10-2025 17:00:00 | Er.ATUL PARADKAR | 9425804929 | ok, through sub ld
16 | 2025-10-15 11:40 | MR2510/0451 | Daily | 220KV_220 KV Itarsi-Handia II | 220KV_ITARSI | NON-OCCM-MP | Replacement of Single to Double dis insul.string | 16-10-2025 09:00:00 | 17-10-2025 18:00:00 | Ashutosh Rai | 9425806902 | ok, through sub ld
17 | 2025-09-04 18:22 | MR2509/0116 |  | 400KV_400 kv JP BINA -BINA PG CKT. | 400KV_JP BINA | NON-OCCM-WR | low line to line clearance | 16-10-2025 07:00:00 | 16-10-2025 19:00:00 | Krishna Singh Thakur | 7987976012 | Deffered by site
18 | 2025-09-18 13:00 | MR2509/0411 | Continuous | 400KV_400KV DAMOH - KATNI LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 13-10-2025 09:00:00 | 18-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deffered
19 | 2025-10-15 15:52 | MR2510/0460 |  | 220KV_160MVA EMCO X-MER | 220KV_MAIHAR | NON-OCCM-MP | Replacement of 220KV RYB phase CT due to high tand | 16-10-2025 09:00:00 | 16-10-2025 17:00:00 | ARUN KUMAR KOL | 9425802368 | ok
20 | 2025-10-15 11:00 | MR2510/0449 |  | 132KV_132kV Mandla-Maneri Line | 132KV_MANDLA | NON-OCCM-MP | Jumper Cone Tightening & Other Maint. Work | 16-10-2025 10:00:00 | 16-10-2025 18:00:00 | S.K. BHALADHARE | 9425807264 | ok
21 | 2025-10-15 13:03 | MR2510/0453 |  | 220KV_220 KV Datia Pichhore Line | 220KV_PICHHORE | NON-OCCM-MP | F/o disc replacement and other line maintenance wo | 16-10-2025 09:00:00 | 16-10-2025 18:00:00 | SATISH KUMAR BHAGAT | 9425806916 | ok, through sub ld
22 | 2025-10-09 11:27 | MR2510/0244 | Daily | 125MVAR_LINE_Reactor__Of_1886 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Radiator oil leakage attend work | 15-10-2025 10:00:00 | 16-10-2025 17:00:00 | Rajudas bairagi | 9425801532 | ok, through sub ld
23 | 2025-10-15 08:29 | MR2510/0447 |  | 132KV_50MVA X-MER BBL | 132KV_PRATAPPURA | NON-OCCM-MP | Post Monsoon maintenance | 16-10-2025 11:00:00 | 16-10-2025 17:00:00 | Vikram Ahirwar | 9425805415 | sub ld
24 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
25 | 2025-10-15 16:16 | MR2510/0463 |  | 132KV_132KV Neemuch Ratangarh line | 220KV_RATANGARH | NON-OCCM-MP | For line maintanence work | 16-10-2025 10:00:00 | 16-10-2025 18:00:00 | Gaurav Goyal | 9425805120 | sub ld
26 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
27 | 2025-10-15 12:38 | MR2510/0452 |  | 132KV_40 mva x-mer NGEF | 220KV_REWA | NON-OCCM-MP | POST MONSOON MAINT & tESTING WORK | 16-10-2025 10:00:00 | 16-10-2025 17:00:00 | KANISHKA SINGH | 9425804656 | ok
28 | 2025-10-14 12:31 | MR2510/0411 |  | 132KV_132kv Sagar-Gourjhamar 2nd Ckt. Line | 400KV_SAGAR | NON-OCCM-MP | Line maintenance work | 16-10-2025 10:00:00 | 16-10-2025 18:00:00 | J.P. Asati | 9424445533 | ok
29 | 2025-10-15 15:57 | MR2510/0461 |  | 132KV_33 kV Main Bus | 220KV_SATNA | NON-OCCM-MP | For attending damaged conductor of R phase of 63 M | 16-10-2025 11:00:00 | 16-10-2025 13:00:00 | Ravi Pandey | 9425805296 | o&m consent required
24 | 2025-10-15 15:27 | MR2510/0459 |  | 220KV_220KV 160MVA 220/132KV BBL X-MER-1 | 220KV_SUWASRA2 | NON-OCCM-MP | POST MONSOON MAINTNANCE & TESTING WORK | 16-10-2025 10:00:00 | 16-10-2025 18:00:00 | SUNIL PAWAR | 9425804939
25 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137
26 |  |  |  | NHPTL-TESTING-of 100 MVA, 220 kV 3 ph Transformer | NHPTL |  | Expected short circuit current: 1.5 kA +/- 10% Expected fault current: 2.5 kA Time duration: 250 ms +/- 10% No. of shots to be taken: | 00:00:00 | 24:00:00 |  |  | ok, all the instructions of WRLDC shall be passed to JP BINA and MP BINA; Bypass arrangement to be done. Bypass arrangement details: 1)JB Bina (400kV) to POWER GRID Bina diverted to SATNA PG. 2)JP Bina (400kV) to MPPTCL Bina diverted to Guna(MP). The Bypass arrangement at Bina (PG) and Bina (MP) shall be done early morning between 05:00 Hrs and 06:00Hrs
27 |  |  |  | 400KV-BINA-MP-GUNA-MP-2 | POWERGRID_WR2 |  | AMP work. | 09:00:00 | 18:00:00 |  |  | Deffered, in view of NHPTL testing; SLDC MP consent to be taken.400kV BINA-MP-GUNA PBGTL-Q1 (sensitivity of 73%) and and all other lines at 400kV Bina-MP (Except 400kV Bhopal-MP Bina-MP-1) to be in service.In case of contingency load at 220kV Guna-MP to be managed by SLDC MP
28 |  |  |  | SATNA - 220KV - BUS 2 | POWERGRID_WR2 |  | For integration of relays of upcoming 220kV bays in existing system | 09:00:00 | 18:00:00 |  |  | OK, All elements will be in service with Bus-1. SLDC MP consent required. In case of N-1, Chattarpur line will out and all other elements would be in service via tie bay. SLDC to be informed.
29 |  |  |  | 400KV-KIRNAPUR-BHILAI-1 | MP_SLDC |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 09:00:00 | 18:00:00 |  |  | real time; 400kV Seoni-Kirnapur to be in service with A/R enabled. SLDC CG to be informed. load to be managed by SLDC MP in case of n-1 contingency.
30 |  |  |  | 220KV-HOSHANGABAD-ITARSI-2 | MP_SLDC |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 09:00:00 | 17:00:00 |  |  | ok, through sub ld, ckt shall be normalised by 15 hrs positively looking to increasing load.; All other 220KV lines at HOSHANGABAD will be in service. Sensitivity on the other ckt is 65 %. Load will be managed by SLDC MP. WR-2 to be informed.
31 |  |  |  | 220KV-KHANDWA-CHHEGAON-1 | MP_SLDC |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 08:00:00 | 17:00:00 |  |  | ok, through sub ld; Ok, ckt-2(sensitivity is 22%) to be in service. All other 220KV ckt at chhegoan to be in service load to be managed by SLDC MP.
32 |  |  |  | 220KV-INDORE-INDORE NORTH ZONE-1 | MP_SLDC |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 08:00:00 | 18:00:00 |  |  | real time; ckt-2 will be in service. load to be managed by SLDC MP. WR-2 to be informed.