## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-06-24 |  |  | APPROVED OUTAGE LIST FOR DTD.24.06.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-23 15:07 | MR2506/0473 |  | 220KV_220kv Amarkantak-Birshinghpur TPS CKT | 220KV_AMARKANTAK | NON-OCCM-MP | for flash over disc replacement & other line maint | 24-06-2025 10:00:00 | 24-06-2025 17:00:00 | JITENDRA TIWARI | 9425805298 | ok
2 | 2025-06-16 18:55 | MR2506/0355 | Daily | 220KV_220 KV BAIRAGARH MUGALIYACHAP LINE | 220KV_BAIRAGARH | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-06-16 19:00 | MR2506/0357 | Daily | 220KV_220 KV BHOPAL BAIRAGARH LINE-3 | 220KV_BAIRAGARH | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
4 | 2025-06-23 09:45 | MR2506/0456 | Daily | 220KV_220 kv Bairagarh Ashta | 220KV_BAIRAGARH | NON-OCCM-MP | OPGW MAINTENANCE WORK | 23-06-2025 09:00:00 | 30-06-2025 09:00:00 | Nitin Reshwal | 9425804890 | ok, line to be in service
5 | 2025-05-02 13:52 | MR2505/0038 | Continuous | 132KV_20 MVA Emco-i | 132KV_BARWANI | NON-OCCM-WR | augmentation of new 63 MVA transformer | 03-05-2025 11:00:00 | 30-06-2025 19:00:00 | vijay chand saiyam | 9425820043 | sub ld
6 | 2025-06-23 15:35 | MR2506/0477 |  | 132KV_20 MVA GEC_X-mer | 220KV_BETUL | NON-OCCM-MP | SFRA testing work | 24-06-2025 11:00:00 | 24-06-2025 13:00:00 | Vishal Kumar Malviya | 9425804955 | sub ld
7 | 2025-06-22 12:03 | MR2506/0444 | Continuous | 132KV_20 MVA GEC_X-mer | 220KV_BETUL | NON-OCCM-MP | X-mer shifting from existing location to Wooden sl | 23-06-2025 10:00:00 | 27-06-2025 17:00:00 | Vishal Kumar Malviya | 9425804955 | sub ld
8 | 2025-06-23 14:52 | MR2506/0471 |  | 220KV_160 MVA X-MER No 1 | 220KV_BHOPAL | NON-OCCM-MP | for Testing work | 24-06-2025 10:00:00 | 24-06-2025 17:00:00 | A. K. Jain | 9425806899 | ok, through sub ld
9 | 2025-06-23 15:20 | MR2506/0476 |  | 132KV_132 KV Bina-Khurai Ckt-2 | 220KV_BINA | NON-OCCM-MP | For F/o disc replace & line maint work | 24-06-2025 10:00:00 | 24-06-2025 17:00:00 | Sanjay Singh Thakur | 9425806936 | ok
10 | 2025-06-23 09:15 | MR2506/0455 | Continuous | 220KV_220 KV BUSCOUPLER & 220 MAIN BUS -2 | 400KV_BINA4 | NON-OCCM-MP | FOR ERECTION OF STRUCTURE AND STRINGING | 24-06-2025 10:00:00 | 27-06-2025 17:00:00 | ANIL MAHOR | 9425805149 | Deffered due to s/d on Damoh PG 220kv bus
11 | 2025-06-23 10:15 | MR2506/0457 |  | 400KV_400kv Main Bus - Ist | 400KV_CHHEGAON4 | NON-OCCM-MP | R-Phase damaged dropper jumper repairing work | 24-06-2025 10:00:00 | 24-06-2025 18:00:00 | Shri Ganesh Mansare | 9425802441 | WRLDC emeregency approval required
12 | 2025-04-28 13:05 | MR2504/0766 | Continuous | 20MVA_132/33KV_BHEL_X'mer_4 | 220KV_DAMOH | OCCM-MP | augmantation of 20 MVA transformer by 63 mva trans | 28-04-2025 14:00:00 | 30-06-2025 16:00:00 | MK Choubey | 8959559657 | Continuous
13 | 2025-06-23 14:37 | MR2506/0468 |  | 132KV_Change over to Bus coupler of 132KV Tejgarh Breaker | 220KV_DAMOH | NON-OCCM-MP | DPR Relay Replacement work | 24-06-2025 11:00:00 | 24-06-2025 18:00:00 | M.K.Choubey | 9425801424 | ok, line to be in service through TBC
14 | 2025-06-23 15:08 | MR2506/0474 |  | 132KV_132 KV Gadarwara - Barman Line | 132KV_GADARWARA | NON-OCCM-MP | Loc.No.95/R-01 No.F/O disc & Other line maintenanc | 24-06-2025 10:00:00 | 24-06-2025 14:00:00 | Ashish Kumar | 9425805935 | ok
15 | 2025-05-07 15:18 | MR2505/0133 | Continuous | 160MVA_220/132KV_BHEL_X'mer_1 | 220KV_HANDIYA | NON-OCCM-MP | for Replacement of Transformer | 08-05-2025 10:00:00 | 08-07-2025 17:00:00 | J.D.Khoria | 9425804975 | Continuous
16 | 2025-06-17 21:54 | MR2506/0387 | Continuous | 400KV_UNIT - 7 | 400KV_INDIRASAGAR | NON-OCCM-WR | ANNUAL MAINTENANCE | 18-06-2025 06:00:00 | 30-06-2025 18:00:00 | Vinay Mishra | 9575074321 | as per system requirement
17 | 2025-06-20 19:03 | MR2506/0431 | Continuous | 400KV_400 KV BUS 2 | 400KV_INDIRASAGAR | NON-OCCM-MP | SF 6 CB maintenance work | 24-06-2025 10:00:00 | 28-06-2025 17:00:00 | SANJAY PATEL | 9424050443 | ok
18 | 2025-06-17 18:03 | MR2506/0376 | Daily | 220KV_NORTHZONE - HATUNIYA (PGCIL) CKT -2 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF 24F OPGW BY 48F OPGW | 21-06-2025 07:00:00 | 26-06-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
19 | 2025-06-17 18:13 | MR2506/0378 | Daily | 132KV_NORTHZONE - NIRANJANPUR LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF 24F OPGW BY 48F OPGW | 21-06-2025 07:00:00 | 26-06-2025 19:00:00 | A.R. KANEL | 9425805217 | Deffered
20 | 2025-06-17 18:05 | MR2506/0377 | Daily | 132KV_NORTHZONE - JETPURA LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF 24F OPGW BY 48F OPGW | 21-06-2025 07:00:00 | 26-06-2025 19:00:00 | A.R. KANEL | 9425805217 | Deffered
21 | 2025-06-12 15:54 | MR2506/0282 | Daily | 220KV_NORTH ZONE - HATUNIYA CKT-1 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF EXISTING E/W BY 24F OPGW | 15-06-2025 07:00:00 | 25-06-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
22 | 2025-06-23 12:11 | MR2506/0459 |  | 220KV_220 KV Sarni-Itarsi II line | 220KV_ITARSI | NON-OCCM-MP | Resagging work loc.no. 192-213 | 24-06-2025 09:00:00 | 24-06-2025 18:00:00 | Ashutosh Rai | 9425806902 | ok, through sub ld
23 | 2025-06-23 11:21 | MR2506/0458 |  | 132KV_132 kV Jabalpur- VFJ ckt-I | 220KV_JABALPUR | NON-OCCM-MP | Disc F/o change at loc. 40 B Ph | 24-06-2025 10:00:00 | 24-06-2025 13:00:00 | Jitendra Tiwari | 9425805298 | o&m consent required
24 | 2024-11-20 16:32 | MR2411/0430 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 23-06-2025 09:00:00 | 28-06-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Continuous
25 | 2024-11-20 16:36 | MR2411/0431 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 23-06-2025 09:00:00 | 28-06-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Continuous
26 | 2025-06-23 14:46 | MR2506/0469 |  | 220KV_220KV Kukshi-Julwaniya-II ckt | 220KV_KUKSHI | NON-OCCM-MP | for Commissioning of second DPR & testing purpose | 24-06-2025 11:00:00 | 24-06-2025 17:00:00 | Er. Manoj Randha | 9425820034 | ok, through sub ld
27 | 2025-06-23 14:49 | MR2506/0470 |  | 132KV_50MVA BHEL X-MER | 132KV_KYMORE | NON-OCCM-MP | For Pre-Monsoon Maintenance | 24-06-2025 10:00:00 | 24-06-2025 17:00:00 | Shivam patel | 9893109071 | o&m consent required
28 | 2025-06-23 13:28 | MR2506/0462 |  | 132KV_132 KV KYMORE AMEHTA ACC LINE | 132KV_KYMORE | NON-OCCM-MP | line maintenance work of Consumer End. | 24-06-2025 06:00:00 | 24-06-2025 18:00:00 | PANKAJ YADAV | 9406713326 | ACC consent required
29 | 2025-06-16 18:57 | MR2506/0356 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA LINE | 220KV_MUGALIYACHAAP | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | communication consent required for data outage
30 | 2025-06-20 11:59 | MR2506/0420 | Daily | 220KV_220 KV BHOPAL MUGALIYACHAAP | 220KV_MUGALIYACHAAP | NON-OCCM-MP | OPGW MAINTENANCE WORK | 21-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
31 | 2025-06-23 15:14 | MR2506/0475 |  | 220KV_220 KV Chichli - Narsinghpur Line | 220KV_NARSINGHPUR | NON-OCCM-MP | Loc.No.276/R-01 No.F/O disc & Other line maintenan | 24-06-2025 14:00:00 | 24-06-2025 18:00:00 | Ashish Kumar | 9425805935 | ok
32 | 2025-06-09 15:58 | MR2506/0188 | Continuous | 220KV_Generating Unit No. 06 | 220KV_OMKARESHWAR | NON-OCCM-WR | Annual maintenance | 10-06-2025 10:00:00 | 24-06-2025 18:00:00 | Sh. Pankaj Sharma | 7898703187 | as per system requirement
33 | 2025-05-08 17:07 | MR2505/0173 | Continuous | 400KV_400kV SSTPH-Pithampur Line Ckt-2 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered
34 | 2025-05-08 16:57 | MR2505/0172 | Continuous | 400KV_400kVSSTPH-Pithampur Ckt-1 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered
35 | 2025-06-23 13:31 | MR2506/0464 |  | 132KV_132KV RAJMILAN-BARGAWAN(TBCB) CKT. | 132KV_RAJMILAN | NON-OCCM-MP | FLASH OVER DISC REPLACEMENT WORK | 24-06-2025 11:00:00 | 24-06-2025 16:00:00 | G.L SAHU | 9425805102 | ok, adani shall be informed
36 | 2025-06-23 14:19 | MR2506/0467 |  | 220KV_220/132/33 kv, 160 MVA X-MER-I st (BHEL) | 220KV_RATLAM | NON-OCCM-MP | for backup relay replacement work. | 24-06-2025 10:00:00 | 24-06-2025 17:00:00 | NIKHIL DUNGE | 9425801487 | ok, through sub ld
37 | 2025-06-23 13:53 | MR2506/0466 |  | 132KV_Shutdown (H/T) of 132 kv Rewa Interconnector Ckt-I line | 220KV_REWA | NON-OCCM-WR | Pre- monsoon maintenance work | 24-06-2025 10:00:00 | 24-06-2025 16:00:00 | Mr. Ajay Kumar Chaurasia | 9425805081 | ok
38 | 2025-06-23 15:49 | MR2506/0478 |  | 132KV_132kv Sabalgarh Beerpur (TBCB) Ckt | 220KV_SABALGARH | NON-OCCM-MP | Line Maintenance work | 24-06-2025 10:00:00 | 24-06-2025 17:00:00 | SURAJ PAWAR | 9425814079 | sub ld
39 | 2025-06-13 14:38 | MR2506/0294 | Daily | 132KV_132KV SAGAR-SAGAR IC 1 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | OPGW Work installation (Hot Line Permit | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
40 | 2025-06-13 14:42 | MR2506/0295 | Daily | 132KV_132kv SAGAR-SAGAR IC 3 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | Work installation of OPGW | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
41 | 2025-05-03 11:32 | MR2505/0054 | Continuous | 220KV_100 MVA X-mer Make CGL | 220KV_SARNI | NON-OCCM-MP | X-mer Augmentation work by 160 MVA X-mer AREVA | 05-05-2025 10:00:00 | 10-07-2025 17:00:00 | Er K.K. Choure | 9425801357 | Continuous
42 | 2025-05-21 18:37 | MR2505/0453 |  | 400KV_400 KV SARNI- ISP | 400KV_SATPURA TPS | NON-OCCM-MP | Work of routine testing general checking & mainten | 24-06-2025 09:00:00 | 24-06-2025 18:00:00 | S.S. THAKUR | 9425611244 | ok
43 | 2025-06-20 12:24 | MR2506/0422 | Continuous | 220KV_Bay no 21 tie cum bus coupler breaker | 400KV_SGTPS | NON-OCCM-MP | For overhauling of 220 kv circuit breaker | 23-06-2025 08:00:00 | 26-06-2025 16:00:00 | S Banerjee | 9424352880 | ok
44 | 2025-06-23 16:01 | MR2506/0479 |  | 220KV_220 KV INOX-I | 220KV_SHAJAPUR | NON-OCCM-MP | TAN DELTA | 24-06-2025 08:00:00 | 24-06-2025 12:00:00 | VIJAY OJHA | 9755836908 | ok, through sub ld
45 | 2025-06-23 16:04 | MR2506/0480 |  | 220KV_220 KV INOX-II | 220KV_SHAJAPUR | NON-OCCM-MP | TAN DELTA | 24-06-2025 12:00:00 | 24-06-2025 17:00:00 | Er VIJAY OJHA | 9755836908 | ok, through sub ld
46 | 2025-06-22 13:36 | MR2506/0448 | Continuous | 132KV_132KV SIDHI-MAUGANJ CKT-1&2 | 220KV_SIDHI | NON-OCCM-MP | TOWER MODIFICATION &SHIFTING WORK | 23-06-2025 08:00:00 | 26-06-2025 18:00:00 | G.L SAHU | 9425805102 | Continuous
47 | 2025-06-23 14:59 | MR2506/0472 |  | 132KV_132kV Sidhi - Deosar Ckt - I | 220KV_SIDHI | NON-OCCM-MP | Line maintenance work. | 24-06-2025 09:00:00 | 24-06-2025 16:00:00 | G.L Sahu | 9425805102 | ok, o&m shall be informed
48 | 2025-06-17 17:47 | MR2506/0373 | Daily | 132KV_132 kV Tikamgarh-Badamalhera line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW installation work | 20-06-2025 07:00:00 | 30-06-2025 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
49 | 2025-06-17 17:49 | MR2506/0374 | Daily | 132KV_132 kV Tikamgarh IC 1st line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW installation work | 20-06-2025 07:00:00 | 30-06-2025 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
50 | 2025-06-23 13:25 | MR2506/0461 |  | 220KV_220kv UJJAIN -Barod ckt-IST | 400KV_UJJAIN4 | NON-OCCM-MP | DPR Relay installation and pre monsoon maint. | 24-06-2025 10:00:00 | 24-06-2025 17:00:00 | Santosh chavrasia | 9425804677 | ok, through sub ld
51 | 2025-06-21 09:53 | MR2506/0433 | Daily | 400KV_400 KV ASHTA-UJJAIN LINE DCDS(CKT 1&2) | 400KV_UJJAIN4 | OCCM-WR | ONLINE PERMIT WORK | 21-06-2025 10:00:00 | 25-06-2025 19:00:00 | KUMAR SACHINDRA SHARMA | 7415651054 | ok, line to be in service
52 | 2025-06-21 09:53 |  |  | DAMOH - 220KV - BUS 1 |  |  | AMP work of 220KV BUS 1, BUS will be out. All bay is to be out one by one for maintenance of 89A of all bay. During outage of bay one by one, their lines or equipments is to be transfer through TBC. | 24-Jun-2025 | 09:00 | 24-Jun-2025 | 18:00 | ok
53 | 2025-06-21 09:53 |  |  | 220KV-MORENA-MALANPUR-1 |  |  | FOR LINE MAINTENANCE WORK | 24-Jun-2025 | 09:00 | 24-Jun-2025 | 17:00 | real time
54 | 2025-06-21 09:53 |  |  | 400KV-DAMOH-KATNI-1 |  |  | TOWER STRENGTHENING WORK | 23-Jun-2025 | 09:00 | 28-Jun-2025 | 18:00 | Continous
55 | 2025-06-21 09:53 |  |  | 220KV-INDORE-INDORE NORTH ZONE-1 |  |  | AR from auto to non auto mode for replacement of existing earth wire by 24 Fibre OPGW work | 24-Jun-2025 | 07:00 | 24-Jun-2025 | 18:59
56 | 2025-06-21 09:53 |  |  | 220KV-INDORE-INDORE NORTH ZONE-2 |  |  | AR from auto to non auto mode for replacement of existing earth wire by 24 Fibre OPGW work | 24-Jun-2025 | 07:00 | 24-Jun-2025 | 18:59
S/I, SLDC MPPTCL JABALPUR