## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-14 |  |  | APPROVED OUTAGE LIST FOR DATED 14.09.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-25 15:12 | MR2508/0327 | Daily | 220KV_220KV Anuppur Kotmikala ckt-I | 220KV_ANUPPUR | NON-OCCM-MP | Low Ground clearance maintenance work at loc. 371- | 09-09-2025 08:00:00 | 17-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
2 | 2025-09-13 14:59 | MR2509/0301 |  | 132KV_40MVA X-MER-1 ABB | 220KV_ASHOKNAGAR | NON-OCCM-MP | SHIELD WIRE STRINGING WORK | 14-09-2025 11:00:00 | 14-09-2025 15:00:00 | RAKESH SUMAN | 7587951093 | SUB LD
3 | 2025-09-07 13:02 | MR2509/0161 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-2 | 220KV_INDORE NORTH | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
4 | 2025-09-07 12:51 | MR2509/0159 | Daily | 132KV_132KV North Zone- Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
5 | 2025-09-07 12:45 | MR2509/0158 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
6 | 2025-09-02 18:32 | MR2509/0063 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1& ckt-2 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | RESCHEDULED FRO 11.09.2025 TO 30.09.2025
7 | 2025-09-13 13:35 | MR2509/0298 |  | 132KV_shutdown on 132KV main bus at 132KV substation katni. | 132KV_KATNI | NON-OCCM-MP | 132kv katni-panagar main bus isolator Y-ph Jaw | 14-09-2025 08:00:00 | 14-09-2025 10:00:00 | Abhishek Mishra | 9425801440 | OK, TIME LINE SHALL STRICTLY BE FOLLOWED, SEPERATE REQUEST SHALL BE SUBMITTED FOR VARIOUS ELEMENTS LIKE 132KV KATNI-PANAGAR CKT, 132KV KATNI I/C - 1
8 | 2025-09-07 12:39 | MR2509/0157 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line. | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
9 | 2025-09-07 12:57 | MR2509/0160 | Daily | 132KV_132KV Niranjanpur - Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
10 | 2025-09-02 18:36 | MR2509/0064 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line.&132KV Niranjanpur - Jaitpura Line &132KV North Zone- Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
11 | 2025-09-13 14:58 | MR2509/0300 |  | 132KV_132kV Rajmilan - janakpur | 132KV_RAJMILAN | NON-OCCM-MP | Disc Replacement Work. | 14-09-2025 09:00:00 | 14-09-2025 17:00:00 | G.L Sahu | 9425805102 | OK, JANAKPUR SHALL BE INFORMED AND ITS SUPPLY SHOULD BE THROUGH ANUPPUR
12
13 | 2025-09-13 11:29 | MR2509/0295 |  | 132KV_40 MVA BBL TRANSFORMER | 220KV_SHAHDOL | NON-OCCM-MP | Replacement of 03 Nos 33KV CT | 14-09-2025 09:00:00 | 14-09-2025 17:00:00 | Vijay Kumar Sahu | 9425814035 | OK
14 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | OK, FTC TO BE SUBMITTED
15 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | RAJESH TIWARI | 7898239595 | CONTINUE
16 |  |  |  | 220KV-ANNUPUR-KOTMIKALA-1 | MP_SLDC |  | For Re-sagging work due to Low Ground clearance at loc. 371-379 & 464- 475 |  |  |  |  | OK, All other lines at Annuppur/Kotmikala to be in service with AR enabled. Load to be managed by SLDC MP/CG
17 |  |  |  | 220KV-INDORE-INDORE NORTH ZONE-1 | MP_SLDC |  | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO |  |  |  |  | OK LINE TO BE IN SERVICE
18 |  |  |  | 220KV-INDORE-INDORE NORTH ZONE-2 | MP_SLDC |  | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO |  |  |  |  | OK LINE TO BE IN SERVICE