## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-03 |  |  | APPROVED OUTAGE LIST FOR DTD.03.10.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-02 15:21 | MR2510/0049 |  | 220KV_100 MVA X- MER Make AREVA | 400KV_ASHTA4 | NON-OCCM-MP | Post Monsoon Maintenance & testing work. | 03-10-2025 08:00:00 | 03-10-2025 17:00:00 | Jitendra Lohana | 9425804978 | ok, through sub ld, o&m shall be informed
2 | 2025-10-01 16:21 | MR2510/0012 | Continuous | 220KV_220 kV Bus bar | 220KV_BHOPAL | NON-OCCM-MP | Repeated False alarm in Busbar Pannel | 01-10-2025 16:30:00 | 03-10-2025 15:00:00 | A K Jain | 9425806899 | work completed
3 | 2025-10-02 12:58 | MR2510/0029 |  | 220KV_200 MVA X-mer (T&R) | 220KV_BINA | NON-OCCM-MP | post monsoon maintenance work | 03-10-2025 09:30:00 | 03-10-2025 18:00:00 | Lalit singh | 9425806845 | Deffered, due to s/d on Sagar x-mer
4 | 2025-10-02 12:05 | MR2510/0024 |  | 132KV_132 KV 40 MVA X-MER -1,BHEL | 220KV_DATIA | NON-OCCM-WR | Post monsoon maintenance & testing work | 03-10-2025 10:00:00 | 03-10-2025 17:00:00 | Raksha Chhapariya | 6265080313 | sub ld
5 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | please confirm the availability of telemetry from communication
6 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | please confirm the availability of telemetry from communication
7 | 2025-10-02 13:12 | MR2510/0036 |  | 132KV_132kv Dongrital-Anuppur Feeder bay | 132KV_DONGRITAL | OCCM-MP | DPR relay testing work. | 03-10-2025 11:00:00 | 03-10-2025 17:00:00 | Mr.SABHAPATI PRAJAPATI | 9039634660 | ok, line to be in service through TBC
8 | 2025-10-01 09:35 | MR2510/0001 | Daily | 132KV_132 kV Jabalpur Bargi (MPPTCL) | 220KV_JABALPUR | NON-OCCM-MP | Installation of Joint Box at loc no 29/4 | 02-10-2025 08:00:00 | 04-10-2025 19:00:00 | Jitendra Tiwari | 9425805298 | ok
9 | 2025-10-02 14:59 | MR2510/0048 |  | 132KV_132 kv katni sleemnabad ckt 1 | 400KV_KATNI4 | NON-OCCM-MP | line maintenance work | 03-10-2025 10:00:00 | 03-10-2025 18:00:00 | pankaj yadav | 9406713326 | ok
10 | 2025-10-02 14:45 | MR2510/0047 |  | 132KV_132kV Lalbarra Samnapur RTS | 132KV_LALBARRA | NON-OCCM-MP | The Dismantling of ABT Meter at 132kV HV side | 03-10-2025 11:00:00 | 03-10-2025 14:00:00 | S.K. Nadekar | 9425806848 | ABT confirmation required for meter work
11 | 2025-10-02 13:48 | MR2510/0039 |  | 160MVA_220/132KV_BBL_Xmer_2 | 400KV_MANDSOUR4 | NON-OCCM-MP | Post monsoon maintenance and testing work | 03-10-2025 09:00:00 | 03-10-2025 17:00:00 | Prakash Chandra Dhakad | 7587951067 | ok, through sub ld
12 | 2025-10-02 15:27 | MR2510/0050 | Continuous | 220KV_220/132 Kv 160MVA BHEL 3 X-mer | 220KV_NARSINGHPUR | NON-OCCM-MP | Replacement of CB,PI&Mainbus isolator erection | 03-10-2025 09:00:00 | 08-10-2025 17:00:00 | Dinesh Kumar Kushwaha | 9425182413 | ok
13 | 2025-10-02 13:01 | MR2510/0031 |  | 220KV_220 Kv Nimrani Julwaniya | 220KV_NIMRANI | NON-OCCM-MP | S/d On 220 kV Main Bus For Hot Point attending | 03-10-2025 10:00:00 | 03-10-2025 17:00:00 | Pradip Patidar | 9981046192 | real time, omkareshwar HPS is running on full load, so 220kv Barwaha-Nimrani tap OSP shall only be kept off at Nimrani end so that power evacuation at OSP may not be hampered, O&M shall be informed
14 | 2025-10-02 12:49 | MR2510/0025 |  | 220KV_220/132KV 160MVA X-Mer-I CGL | 220KV_NIMRANI | NON-OCCM-MP | S/d On 220 kV Main Bus For Hot Point attending | 03-10-2025 10:00:00 | 03-10-2025 17:00:00 | Pradip Patidar | 9981046192
15 | 2025-10-02 12:52 | MR2510/0026 |  | 220KV_220/132KV 160MVA X-Mer-II BHEL | 220KV_NIMRANI | NON-OCCM-MP | S/d On 220 kV Main Bus For Hot Point attending | 03-10-2025 10:00:00 | 03-10-2025 17:00:00 | Pradip Patidar | 9981046192
16 | 2025-10-02 12:55 | MR2510/0027 |  | 220KV_220/132KV 160MVA X-Mer-III BBL | 220KV_NIMRANI | NON-OCCM-MP | S/d On 220 kV Main Bus For Hot Point attending | 03-10-2025 10:00:00 | 03-10-2025 17:00:00 | Pradip Patidar | 9981046192
17 | 2025-10-02 12:57 | MR2510/0028 |  | 220KV_220 Kv Nimrani Chhegaon-I | 220KV_NIMRANI | NON-OCCM-MP | S/d On 220 kV Main Bus For Hot Point attending | 03-10-2025 10:00:00 | 03-10-2025 17:00:00 | Pradip Patidar | 9981046192
18 | 2025-10-02 12:59 | MR2510/0030 |  | 220KV_220 Kv Nimrani-Chhegaon -II | 220KV_NIMRANI | NON-OCCM-MP | S/d On 220 kV Main Bus For Hot Point attending | 03-10-2025 10:00:00 | 03-10-2025 17:00:00 | Pradip Patidar | 9981046192
19 | 2025-10-02 13:03 | MR2510/0032 |  | 220KV_220 Kv Nimrani Barwaha | 220KV_NIMRANI | NON-OCCM-MP | S/d On 220 kV Main Bus For Hot Point attending | 03-10-2025 10:00:00 | 03-10-2025 17:00:00 | Pradip Patidar | 9981046192
20 | 2025-10-02 13:05 | MR2510/0033 |  | 220KV_220 Kv Nimrani Maheshwer-I | 220KV_NIMRANI | NON-OCCM-MP | S/d On 220 kV Main Bus For Hot Point attending | 03-10-2025 10:00:00 | 03-10-2025 17:00:00 | Pradip Patidar | 9981046192
21 | 2025-10-02 13:08 | MR2510/0034 |  | 220KV_220 Kv Nimrani Maheshhwer-II | 220KV_NIMRANI | NON-OCCM-MP | S/d On 220 kV Main Bus For Hot Point attending | 03-10-2025 10:00:00 | 03-10-2025 17:00:00 | Pradip Patidar | 9981046192
22 | 2025-10-02 13:10 | MR2510/0035 |  | 220KV_220 Kv PT | 220KV_NIMRANI | NON-OCCM-MP | S/d On 220 kV Main Bus For Hot Point attending | 03-10-2025 10:00:00 | 03-10-2025 17:00:00 | Pradip Patidar | 9981046192
23 | 2025-10-02 15:37 | MR2510/0051 |  | 132KV_40MVA TRANSFORMER TAL | 132KV_PETLAWAD | NON-OCCM-MP | For hot point attend on on LV side bushing clamp | 03-10-2025 12:00:00 | 03-10-2025 14:00:00 | Er varsingh mohoniya | 9425803496 | sub ld
24 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | please confirm the availability of telemetry from communication
25 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | please confirm the availability of telemetry from communication
26 | 2025-10-01 14:06 | MR2510/0008 |  | 220KV_160mva 220/132kv BHEL X-MER | 400KV_SAGAR | NON-OCCM-MP | POST MANSOON MAINTENANCE & TESTING WORK | 03-10-2025 09:30:00 | 03-10-2025 17:00:00 | Srajan Sisodiya | 7879960164 | ok
27 | 2025-10-02 14:36 | MR2510/0046 |  | 132KV_132KV Seoni -Gopalganj feeder | 132KV_SEONI1 | NON-OCCM-MP | Rph CT replacement work due to high Tan-delta | 03-10-2025 09:00:00 | 03-10-2025 17:00:00 | Ramkumar Meshram | 7587951054 | ok
28 | 2025-10-01 15:08 | MR2510/0011 |  | 132KV_132kV Seoni Katangi Feeder | 132KV_SEONI1 | NON-OCCM-MP | Replacement of broken disc insulator | 03-10-2025 10:00:00 | 03-10-2025 17:00:00 | S.K. Nadekar | 9425806848 | ok
29 | 2025-09-30 10:44 | MR2509/0785 |  | 220KV_Bay #04, 220 KV Birsinghpur pali I/C-II | 400KV_SGTPS | NON-OCCM-MP | for the closing circuit checking work | 03-10-2025 09:00:00 | 03-10-2025 17:00:00 | KIRAN SINGH | 9425826084 | ok
30 | 2025-10-02 14:14 | MR2510/0041 |  | 220KV_220KV Main Bus-II alongwith connected feeder Chhegaon-II , ST-3,ICT-1,Bus-coupler for protection circuit checking work | 400KV_SINGHAJI TPS | NON-OCCM-MP | Protection circuit checking / BCU checking work | 03-10-2025 10:00:00 | 03-10-2025 18:00:00 | Deepak Sharma | 8005696855 | ok
31 | 2025-09-29 17:32 | MR2509/0780 |  | 400KV_400KV Chhegaon-I for PMU commissioning | 400KV_SINGHAJI TPS | NON-OCCM-MP | commissioning of PMU at SSTPP PH-I | 03-10-2025 10:00:00 | 03-10-2025 17:00:00 | Deepak Sharma | 8005696855 | Deffered due to multiple outages in the region
32 | 2025-10-02 13:42 | MR2510/0037 |  | 132KV_40mva BBL-make-Make Transformer | 220KV_TIKAMGARH | NON-OCCM-MP | Post mansoon maintenance | 03-10-2025 09:00:00 | 03-10-2025 14:00:00 | Pushpendra Kumar soni | 9425806398 | ok
33 | 2025-10-02 13:44 | MR2510/0038 |  | 132KV_50 MVA TAl -make transformer | 220KV_TIKAMGARH | NON-OCCM-MP | Post mansoon maintenance | 03-10-2025 14:00:00 | 03-10-2025 18:00:00 | Pushpendra Kumar soni | 9425806398 | ok
34 | 2025-10-01 14:24 | MR2510/0009 |  | 220KV_160 MVA XMER BHEL -I | 220KV_UJJAIN | NON-OCCM-WR | Post Monsoon Maint & Testing work | 03-10-2025 09:00:00 | 03-10-2025 17:00:00 | B.C JOSHI | 7587951137 | ok, through sub ld
35 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
36 | 2025-09-02 14:10 |  |  | 400KV/220KV SATNA-ICT-3 |  | OCCM-MP | For excavation work related to construction of cable trench for 220 kV EHT cable associated with upcoming 400/220 kV ICT#4, Dia to be kept open at both sides. | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 |  |  | real time,
37 | 2025-09-02 14:10 |  |  | 132KV-DHARNI-NEPANAGAR-1 |  | OCCM-MP | For PID work, Shifting of auto reclose switch to non auto mode | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 |  |  | OK
S/I ,SLDC MPPTCL JABALPUR