## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-10
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-30 16:24 | MR2506/0639 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA | 400KV_ASHTA4 | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
2 | 2025-07-08 12:43 | MR2507/0105 |  | 400KV_Badnawar to Rajgarh (PGCIL) ckt-2 | 400KV_BADNAWAR | OCCM-MP | For line maintenance work | 10-07-2025 10:00:00 | 10-07-2025 18:00:00 | V.R. Panadia | 9425802330 | ok, through sub ld
3 | 2025-06-30 16:26 | MR2506/0640 | Daily | 220KV_220 KV BAIRAGARH-ASHTA | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
4 | 2025-06-30 16:13 | MR2506/0635 | Daily | 220KV_220 BHOPAL-BAIRAGARH CKT-3 | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
5 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
6 | 2025-06-26 14:17 | MR2506/0554 | Daily | 220KV_220 KV Bina-Guna Ckt & 220 KV Bina-Ashoknagar Ckt | 400KV_BINA4 | NON-OCCM-MP | Hot line PTW for OPGW resagging work BY M/s ZTT | 26-06-2025 07:00:00 | 10-07-2025 19:00:00 | Sanjay singh thakur | 9425806936 | ok, line to be in service
7 | 2025-07-09 11:18 | MR2507/0119 |  | 220KV_220 KV DATIA-PICHHORE CKT. | 220KV_DATIA | NON-OCCM-WR | 2nd DPR COMMISSIONING & Testing work | 10-07-2025 11:00:00 | 10-07-2025 17:00:00 | ATUL SHAKYA | 9425806928 | ok, through sub ld
8 | 2025-06-23 17:09 | MR2506/0482 | Daily | 220KV_220 KV South Zone - Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
9 | 2025-07-09 15:47 | MR2507/0129 |  | 400KV_400KV Indore - ISP-II line | 400KV_INDORE4 | NON-OCCM-MP | For 400KV new isolator alignment and PCC work by R | 10-07-2025 10:00:00 | 10-07-2025 17:00:00 | Sandeep Umredkar | 9425820035 | as per ISP generation in real time
10 | 2025-06-23 17:04 | MR2506/0481 | Daily | 220KV_220KV Indore (400KV) - Mangliya line | 400KV_INDORE4 | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
11 | 2025-07-09 11:38 | MR2507/0121 |  | 220KV_220 kV Jabalpur- Birsinghpur ckt-I | 220KV_JABALPUR | NON-OCCM-MP | Disc F/o at loc. 58, 36 | 10-07-2025 10:00:00 | 10-07-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
12 | 2025-07-09 15:55 | MR2507/0130 |  | 132KV_132kv 40mva xmer telk | 132KV_KANWAN | OCCM-MP | Differential relay replacement work | 10-07-2025 10:00:00 | 10-07-2025 18:00:00 | Poshkar kushwaha | 9425813990 | sub ld
13 | 2025-07-09 15:24 | MR2507/0128 |  | 132KV_132 kv sleemnabad katni line from 132 kv ss | 132KV_KATNI | NON-OCCM-MP | For line maintenance work . | 10-07-2025 10:00:00 | 10-07-2025 18:00:00 | pankaj yadav | 9406713326 | ok
14 | 2024-11-20 16:45 | MR2411/0434 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 07-07-2025 09:00:00 | 12-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Continuous
15 | 2024-11-20 16:47 | MR2411/0435 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 07-07-2025 09:00:00 | 12-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Continuous
16 | 2025-07-01 15:42 | MR2507/0010 | Continuous | 132KV_132 KV Khurai-Sagar | 132KV_KHURAI | NON-OCCM-MP | Modification/Shifting of 132 KV Khurai-Sagar | 02-07-2025 07:00:00 | 12-07-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | Continuous
17 | 2025-06-30 16:20 | MR2506/0638 | Daily | 220KV_220 KV BHOPAL-MUGALIYACHAP | 220KV_MUGALIYACHAAP | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
18 | 2025-06-26 14:57 | MR2506/0557 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | OCCM-WR | Hotline work For Installation OPGW by replace E/W | 26-06-2025 08:00:00 | 10-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
19 | 2025-06-26 15:04 | MR2506/0558 | Daily | 132KV_132 kV Nepa - Pipalpani | 220KV_NEPANAGAR | NON-OCCM-MP | Hotline work Installation OPGW Replaced by E/W | 26-06-2025 08:00:00 | 10-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
20 | 2025-07-09 16:55 | MR2507/0132 |  | 132KV_132kv bina- RAJGHAT | 132KV_RAJGHAT | OCCM-MP | TESTING OF CT, BREAKER AND CVT | 10-07-2025 09:00:00 | 10-07-2025 19:00:00 | NARENDRA SINGH TANDEL | 9630685929 | ok, through sub ld
21 | 2025-07-01 16:13 | MR2507/0015 | Continuous | 400KV_400 KV MAIN BUS 2 | 400KV_SAGAR | OCCM-MP | FOR EXTENSION OF MAIN BUS 2 | 10-07-2025 09:00:00 | 11-07-2025 17:00:00 | ANIL MAHOR | 9425805149 | Deffered, not in WRPC approval list
22 | 2025-05-03 11:32 | MR2505/0054 | Continuous | 220KV_100 MVA X-mer Make CGL | 220KV_SARNI | NON-OCCM-MP | X-mer Augmentation work by 160 MVA X-mer AREVA | 05-05-2025 10:00:00 | 10-07-2025 17:00:00 | Er K.K. Choure | 9425801357 | Continuous
23 | 2025-07-09 14:15 | MR2507/0126 |  | 132KV_132KV Satna-1 to Rampur Baghelan feeder | 132KV_SATNA1 | NON-OCCM-MP | for measurement tan delta of CT | 10-07-2025 10:00:00 | 10-07-2025 13:00:00 | Vishal bhaladhare | 9425804690 | ok
24 | 2025-07-09 14:21 | MR2507/0127 |  | 132KV_132KV Satna-1 to IC No.1 | 132KV_SATNA1 | NON-OCCM-MP | for measurement of tan delta of CT | 10-07-2025 14:00:00 | 10-07-2025 17:00:00 | Vishal bhaladhare | 9425804690 | ok
25 | 2025-07-09 12:44 | MR2507/0123 |  | 132KV_132kV Seoni Katangi Feeder | 132KV_SEONI1 | NON-OCCM-MP | Replacement of flashover disc insulator | 10-07-2025 14:00:00 | 10-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
26 | 2025-07-09 12:42 | MR2507/0122 |  | 132KV_132kV Seoni Lalbarra Feeder | 132KV_SEONI1 | NON-OCCM-MP | Replacement of flashover disc insulator | 10-07-2025 10:00:00 | 10-07-2025 13:00:00 | S.K. Nadekar | 9425806848 | ok
27 | 2025-07-09 16:06 | MR2507/0131 |  | 220KV_220KV SIRMOUR-TONS feeder | 220KV_SIRMOUR | NON-OCCM-MP | 2ND DPR relay installation | 10-07-2025 11:00:00 | 10-07-2025 17:00:00 | I.J.Singh | 9424734033 | ok
28 | 2025-07-09 13:02 | MR2507/0125 |  | 132KV_132 KV MAIN BUS 1 | 220KV_TIKAMGARH | NON-OCCM-MP | overhead stringing work and jumpering work | 10-07-2025 08:00:00 | 10-07-2025 17:00:00 | sameer parte | 9575673359 | ok
29 | 2025-07-09 11:22 | MR2507/0120 |  | 400KV_400 KV UJJAIN NAGDA CKT IIND | 400KV_UJJAIN4 | OCCM-WR | PRE MANSOON AND BAY MAINTENANCE WORK | 10-07-2025 10:00:00 | 10-07-2025 17:00:00 | SANTOSH CHAVRASIA | 9425804677 | ok, through sub ld
30 |  | 253291 |  | 400KV-BADNAWAR-RAJGARH-2 | 400 | MP_SLDC | FOR LINE MAINTENANCE WORK | 10-Jul-2025 | 08:00 | 10-Jul-2025 | 18:00 | ok, through sub ld
31 |  | 253320 |  | 220KV-GWALIOR-GWALIOR-II-2 | 220 | MP_SLDC | FOR BAY MAINTENANCE & TESTING WORK | 10-Jul-2025 | 09:00 | 10-Jul-2025 | 17:00 | real time
32 |  | 253707 |  | 132KV-DHARNI-NEPANAGAR-1 | 132 | MP_SLDC | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 10-Jul-2025 | 08:00 | 10-Jul-2025 | 17:59 | ok