## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-25
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-24 14:48 | MR2510/0566 |  | 132KV_132KV Aalot-Mandsaur Circuit Ist | 132KV_ALOT | NON-OCCM-MP | For OPGW Striging Work | 25-10-2025 14:00:00 | 25-10-2025 18:00:00 | Gaurav Goyal | 9425805120 | sub ld
2 | 2025-10-24 14:53 | MR2510/0567 |  | 132KV_132KV Aalot Mandsaur Circuit IInd | 132KV_ALOT | NON-OCCM-MP | For OPGW Stringing Work | 25-10-2025 14:00:00 | 25-10-2025 18:00:00 | Gaurav Goyal | 9425805120 | sub ld
3 | 2025-10-24 16:11 | MR2510/0573 |  | 132KV_40 MVA BBL Xmer | 132KV_AMARPATAN | NON-OCCM-MP | Erection o 40 MVA TELK Xmer | 25-10-2025 09:00:00 | 25-10-2025 17:00:00 | Arun kumar | 9131207339 | o&m consent required
4 | 2025-10-24 12:57 | MR2510/0562 |  | 400KV_315MVA Transformer Make BHEL | 400KV_BADNAWAR | NON-OCCM-MP | 33KV VCB replacement and testing work | 25-10-2025 10:00:00 | 25-10-2025 18:00:00 | Er. Abhishek Verma | 9340855901 | ok, through sub ld
5 | 2025-10-24 12:42 | MR2510/0561 |  | 400KV_400kV 50MVAR Bhopal-1 Line Reactor(BHEL) | 400KV_BINA4 | NON-OCCM-MP | Post Monsoon Maitenance Work. | 25-10-2025 09:00:00 | 25-10-2025 14:00:00 | Mr P.N, Namdeo | 7587951092 | ok, through sub ld
6 | 2025-10-24 16:25 | MR2510/0575 |  | 220KV_220 KV Bina-Sagar Ckt-1 | 400KV_BINA4 | NON-OCCM-MP | For f/o disc replacement & other line maint | 25-10-2025 10:00:00 | 25-10-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | ok
7 | 2025-09-18 17:24 | MR2509/0455 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 22-10-2025 09:00:00 | 25-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deferred
8 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
9 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
10 | 2025-10-24 10:50 | MR2510/0559 |  | 220KV_220 KV Gujarkhedi Mandsaur ( Sitamau) Ckt-1 line | 220KV_GUJARKHEDI | NON-OCCM-MP | For OPGW shifting work | 25-10-2025 10:00:00 | 25-10-2025 19:00:00 | Ravindra Kumar Marskole | 9425814080 | ok, through sub ld
11 | 2025-10-24 13:47 | MR2510/0564 |  | 220KV_100MVA TRANFORMER -1 IMP MAKE | 220KV_GUJARKHEDI | NON-OCCM-MP | POST MANSOON MAINTANENCE &TESTING WORK | 25-10-2025 14:00:00 | 25-10-2025 20:00:00 | SUNIL PAWAR | 9425804939 | ok, through sub ld
12 | 2025-10-24 15:11 | MR2510/0570 |  | 220KV_160 mva x mer - iii rd | 220KV_GUNA | NON-OCCM-MP | post mansoon maintenance work | 25-10-2025 10:00:00 | 25-10-2025 18:00:00 | sagar shingh dhakad | 9425809506 | ok, through sub ld
13 | 2025-10-23 16:50 | MR2510/0546 |  | 220KV_160 MVA TRANSFORMER 1 MAKE BBL | 220KV_INDORE-NZ | NON-OCCM-MP | POST MANSOON MAINTENANCE WORK | 25-10-2025 10:00:00 | 25-10-2025 17:00:00 | CHANDRAKANT KAUSHAL | 9425801530 | ok, through sub ld, s/d to be normalised by 16:00hrs
14 | 2025-09-18 13:08 | MR2509/0413 | Continuous | 400KV_400KV DAMOH - KATNI LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 22-10-2025 09:00:00 | 25-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deferred
15 | 2025-10-21 20:35 | MR2510/0506 | Daily | 220KV_MAIN BUS B AND BUS COUPLER | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual Maintenance | 24-10-2025 09:30:00 | 25-10-2025 18:00:00 | PANKAJ SHARMA | 7898703187 | ok
16 | 2025-10-21 20:11 | MR2510/0504 | Daily | 220KV_OMKARESHWAR-NIMRANI-Tap-BARWAHA_Ckt | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual maintenance | 23-10-2025 09:30:00 | 25-10-2025 18:00:00 | Pankaj Sharma | 7898703187 | ok, through sub ld
17 | 2025-10-24 11:58 | MR2510/0560 |  | 50MVA_132/33KV_BBL_Xmer | 220KV_PANAGAR | NON-OCCM-MP | POST MANSOON MAINTENANCE WORK | 25-10-2025 10:00:00 | 25-10-2025 18:00:00 | H L KOSHTA | 7587951105 | ok
18 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
19 | 2025-10-24 16:14 | MR2510/0574 |  | 132KV_40 MVA BHEL | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | POST MONSOON MAINTENANCE | 25-10-2025 11:00:00 | 25-10-2025 18:00:00 | KANISHKA SINGH | 9425804656 | ok
20 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
21 | 2025-10-24 14:19 | MR2510/0565 |  | 132KV_132KV Sabalgarh Motijheel line | 220KV_SABALGARH | NON-OCCM-MP | Line Maintenance work | 25-10-2025 09:00:00 | 25-10-2025 17:00:00 | SURAJ PAWAR | 9425814079 | sub ld
22 | 2025-10-24 15:52 | MR2510/0571 |  | 220KV_160 MVA Transformer | 220KV_SENDHWA2 | NON-OCCM-MP | oil leakage attending work from C-F-T tank | 25-10-2025 10:00:00 | 25-10-2025 16:00:00 | Kashiram khanna | 9826732087 | ok, through sub ld
23 | 2025-10-24 15:10 | MR2510/0568 |  | 132KV_50 MVA Atlanta make transformer | 132KV_TIKAMGARH1 | NON-OCCM-MP | Overhead conductor conductor replaced 33kv side | 25-10-2025 07:00:00 | 25-10-2025 20:00:00 | Pushpendra Kumar soni | 9425806398 | ok
24 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
25 |  | 272444 | Daily | 220KV-SHUJALPUR-RAJGARH-MP-1 | 220 | POWERGRID_WR2 | AMP WORK OF LINE BAY 203 L | 25-Oct-2025 | 08:00 | 25-Oct-2025 | 17:30 | ok
26 |  | 265238 | Continous | 400KV-SATPURA-ITARSI-1 | 400 | POWERGRID_WR2 | For replacemnet of Bus-2 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400kV Bus-1 is required at Sarni S/S of MPGENCO) And CT Replacement of 400KV-SATPURA-ITARSI-1 under ADD CAP at MPGENCO | 25-Oct-2025 | 09:00 | 28-Oct-2025 | 20:00 | ok
27 |  | 265980 | Daily | 220KV-GWALIOR-MALANPUR-2 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 25-Oct-2025 | 09:00 | 25-Oct-2025 | 17:00 | real time
28 |  | 265981 | Daily | 220KV-PANDURNA-KALMESHWAR-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 25-Oct-2025 | 09:00 | 25-Oct-2025 | 18:00 | real time