## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-07 |  | APPROVED OUTAGE LIST FOR DATED 07.09.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | LINE END (IN CASE OF LINE) | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Status | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-25 15:08 | MR2508/0326 | Daily | 220KV_220KV Anuppur Kotmikala ckt-2 | 220KV_ANUPPUR | NON-OCCM-MP | For Re-sagging work due to Low Ground clearance ma |  | 31-08-2025 08:00:00 | 08-09-2025 18:00:00 | Waiting | Jitendra Tiwari | 9425805298 | ok
2 | 2025-09-03 17:53 | MR2509/0085 |  | 220KV_220 KV Badnawar â¿¿Wonder Cement. | 400KV_BADNAWAR | NON-OCCM-MP | work at Wonder cement end |  | 07-09-2025 06:00:00 | 07-09-2025 17:00:00 | Waiting | Kumar Vishal | 9425805018 | ok only if wondercement consented
3 | 2025-09-06 15:08 | MR2509/0153 | Daily | 132KV_132 kV Shahdol-Birsingpur Circuit I | 220KV_BIRSINGHPUR | NON-OCCM-MP | Replacement of damaged OPGW |  | 07-09-2025 09:00:00 | 13-09-2025 18:00:00 | Waiting | Jitendra Tiwari | 9425805298 | ok
4 | 2025-08-31 14:58 | MR2508/0437 | Continuous | 132KV_132 KV Chhatarpur-khajuraho Tap Lavkushnagar | 220KV_CHATARPUR | NON-OCCM-MP | for CT Tan delta measurement work |  | 01-09-2025 14:00:00 | 30-09-2025 17:30:00 | Waiting | Brajendra Soni | 9131327770 | -
5 | 2025-09-06 15:08 | MR2509/0154 | Daily | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | Replacement of damaged OPGW |  | 07-09-2025 09:00:00 | 13-09-2025 18:00:00 | Waiting | Jitendra Tiwari | 9425805298 | data rerouting required & communication confirmation required
6 | 2025-09-02 18:32 | MR2509/0063 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1& ckt-2 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre |  | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | Waiting | A.R.KANEL | 9425805217 | deferred wrpc consent required
7 | 2025-09-05 21:39 | MR2509/0139 |  | 132KV_63MVA BBL NEW | 132KV_MANSAKRA | NON-OCCM-MP | 33KV SIDE CB REPLACEMENT WORK |  | 07-09-2025 10:00:00 | 07-09-2025 17:00:00 | Waiting | ABHISHEK MISHRA | 9425801440 | ok
8 | 2025-09-02 18:36 | MR2509/0064 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line.&132KV Niranjanpur - Jaitpura Line &132KV North Zone- Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre |  | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | Waiting | A.R.KANEL | 9425805217 | sub ld
9 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER |  | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | Accepted | B.C JOSHI | 7587951137 | continue
10 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER |  | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | Waiting | B.C JOSHI | 7587951137 | continue
11 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE |  | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | Accepted | RAJESH TIWARI | 7898239595 | continue
12 |  |  |  | 220KV-ANNUPUR-KOTMIKALA-2 | MADHYA PRADESH,CHATTISGARH |  | For Re-sagging work due to Low Ground clearance at loc. 371-379 & 464- 475 |  | 07-Sep-2025 | 08:00 | 07-Sep-2025 | 18:00 |  | OK
S/I SLDC JABALPUR