## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-28 |  |  | APPROVED OUTAGE LIST FOR DTD.28.07.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-07-27 18:58 | MR2507/0436 |  | 33KV_63 MVA BBL Xmer | 132KV_AMARPATAN | NON-OCCM-MP | 63 mva I/C high span coductor replacement | 28-07-2025 09:00:00 | 28-07-2025 10:30:00 | Arun Kol | 9131207339 | ok, for x-mers
2 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
3 | 2025-07-27 14:41 | MR2507/0431 |  | 220KV_220Kv Chhegaon-Khandwa(CTU) Ckt-II | 400KV_CHHEGAON4 | NON-OCCM-MP | For CVT Wiring Work | 28-07-2025 10:30:00 | 28-07-2025 16:30:00 | Shri Ganesh Mansare | 9425802441 | Deffered, not in WR list
4 | 2025-07-27 13:18 | MR2507/0427 |  | 220KV_220KV Barwaha Feeder Load Transfer TBC | 220KV_HANDIYA | NON-OCCM-MP | For Main-2 relay Commissioning & Main-1 DPR relay | 28-07-2025 11:00:00 | 28-07-2025 18:00:00 | J.D.Khoria | 9425804975 | ok, line to be in service through TBC, through sub ld
5 | 2025-07-27 13:29 | MR2507/0429 |  | 132KV_132KV Gopalpur Feeder Load Transfer TBC | 220KV_HANDIYA | NON-OCCM-MP | For DPR relay Testing work & 132 KV Bay Maint.Work | 28-07-2025 11:00:00 | 28-07-2025 15:00:00 | J.D.Khoria | 9425804975 | sub ld
6 | 2025-07-26 16:26 | MR2507/0425 |  | 220KV_220KV Auxiliary Bus | 220KV_ITARSI | NON-OCCM-MP | Single Zebra high bus span zebra conductor to Twin | 28-07-2025 09:00:00 | 28-07-2025 18:00:00 | J.D.Khoria | 9425804975 | ok, through sub ld
7 | 2025-06-30 15:05 | MR2506/0621 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 28-07-2025 09:00:00 | 02-08-2025 18:00:00 | SHRI PANKAJ YADAV | 9406713326 | Deffered, not in WR list
8 | 2025-06-30 15:54 | MR2506/0630 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 28-07-2025 09:00:00 | 02-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
9 | 2025-07-27 14:12 | MR2507/0430 | Continuous | 132KV_132 KV Khurai- Sagar ckt | 132KV_KHURAI | NON-OCCM-MP | For modification work of above line | 27-07-2025 07:00:00 | 03-08-2025 18:00:00 | Sanjay singh thakur | 9425806936 | Continuous
10 | 2025-07-27 13:28 | MR2507/0428 |  | 132KV_132 kv Maihar â¿¿ Maihar (Cement) line | 220KV_MAIHAR | NON-OCCM-MP | switch yard maintenance | 28-07-2025 11:30:00 | 28-07-2025 15:30:00 | Mr. M.M.Baig | 9425805067 | Maihar cement consent required
11 | 2025-07-24 12:20 | MR2507/0379 |  | 400KV_400 KV Main Bus -1st | 400KV_MANDSOUR4 | NON-OCCM-MP | Overhead stringing work. | 28-07-2025 09:00:00 | 28-07-2025 18:00:00 | J.P. parmar | 9425806919 | Deffered, not in WR list
12 | 2025-07-22 13:19 | MR2507/0315 | Continuous | 132KV_132KV Neemuch-Budha Line | 220KV_NEEMUCH | NON-OCCM-MP | For OPGW Testing & OPGW Splicing | 23-07-2025 08:30:00 | 30-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | sub ld
13 | 2025-07-27 16:04 | MR2507/0434 | Continuous | 220KV_220KV Neemuch Mandsaur circuit IInd | 220KV_NEEMUCH | NON-OCCM-MP | OPGW work | 27-07-2025 18:00:00 | 30-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | Continuous
14 | 2025-07-27 16:08 | MR2507/0435 | Daily | 220KV_220KV Neemuch-Mandsaur ciucuit Ist | 220KV_NEEMUCH | NON-OCCM-MP | Only hot line permit | 28-07-2025 08:00:00 | 30-07-2025 19:00:00 | Gaurav Goyal | 9425805120 | ok, line to be in service
15 | 2025-07-05 17:07 | MR2507/0079 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Insatallation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
16 | 2025-07-05 16:59 | MR2507/0078 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) LIne | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
17 | 2025-07-27 10:18 | MR2507/0426 |  | 160MVA_220/132KV_BHEL_X'mer | 220KV_NEPANAGAR | NON-OCCM-MP | OIL LEAKAGE ATTENDING WORK | 28-07-2025 11:00:00 | 28-07-2025 12:00:00 | MAHESH KUMAR PAWAR | 9425805191 | real time
18 | 2025-07-27 15:55 | MR2507/0432 |  | 132KV_132KV Ratlam - Petlawad tap Bamaniya RTS line | 220KV_RATLAM | NON-OCCM-MP | Work at Railway end | 28-07-2025 11:00:00 | 28-07-2025 17:00:00 | Kumar Vishal | 9425805018 | sub ld
19 | 2025-07-25 16:33 | MR2507/0413 | Continuous | 400KV_400 kv main bus-2 | 400KV_SAGAR | OCCM-MP | for extension of 400 kv main bus-2 | 28-07-2025 08:00:00 | 29-07-2025 17:00:00 | Anil mahor | 9425805149 | Deffered by WRLDC due to Bina PG s/d
20 | 2025-07-26 13:57 | MR2507/0418 | Daily | 132KV_132kV Seoni Nainpur Ckt-IInd | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section | 28-07-2025 10:00:00 | 29-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
21 | 2025-07-26 13:59 | MR2507/0419 | Daily | 132KV_132kV Seoni Keolari Line | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section | 28-07-2025 10:00:00 | 29-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
22 | 2025-07-16 11:01 | MR2507/0207 |  | 400KV_400 kv Brs- Katni Ckt 2 ( Bay 406) | 400KV_SGTPS | NON-OCCM-MP | DPR testing, DCRM of bkr, CT testing | 28-07-2025 08:00:00 | 28-07-2025 18:00:00 | Pramod Mishra | 8989973149 | ok
23 | 2025-07-16 11:19 | MR2507/0211 | Continuous | 220KV_63MVA 220KV/11&6.6 kV Station Trf-5A | 400KV_SGTPS | NON-OCCM-MP | Relay testing,DCRM,CT test,Aircell replacemen | 28-07-2025 08:00:00 | 30-07-2025 18:00:00 | Pramod Mishra | 8989973149 | ok, alternate station supply shall be availalble
24 | 2025-07-23 17:12 | MR2507/0374 | Continuous | 400KV_90MVA STATION TRANSFORMER-2 | 400KV_SINGHAJI TPS | NON-OCCM-MP | OVERHAULLING OF 90MVA STATION TRANSFORMER-2 | 28-07-2025 09:30:00 | 06-08-2025 17:30:00 | Yogesh Chouhan | 7999328631 | ok, alternate station supply shall be availalble
25 | 2025-07-26 14:54 | MR2507/0421 |  | 400KV_400KV Singaji Pithampura-I feeder | 400KV_SINGHAJI TPS | NON-OCCM-MP | Relay testing,CT testing,CVT testing etc. | 28-07-2025 10:00:00 | 28-07-2025 19:00:00 | Deepak Sharma | 8005696855 | ok, through sub ld
26 | 2025-07-27 16:03 | MR2507/0433 |  | 132KV_132 kV Tikamgarh-Badamalhera Line | 220KV_TIKAMGARH | NON-OCCM-MP | F/O disc replacement & other line maint. work | 28-07-2025 10:00:00 | 28-07-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
27 | 2025-07-27 16:03 |  |  | 220KV-REWA-REWA-MP-1 |  |  | FOR LINE MAINTENANCE WORK ( REWA RUMS) | 28-Jul-2025 | 10:00 | 28-Jul-2025 | 17:00 | real time
28 | 2025-07-27 16:03 |  |  | 132KV-SHEOPUR-KHANDAR-1 |  |  | LINE MAINTENANCE WORK | 28-Jul-2025 | 09:00 | 28-Jul-2025 | 17:00 | real time
29 | 2025-07-27 16:03 |  |  | 220KV-ANNUPUR-KOTMIKALA-2 |  |  | FOR LINE MAINTENANCE WORK | 28-Jul-2025 | 09:00 | 28-Jul-2025 | 18:00 | real time
30 | 2025-07-27 16:03 |  |  | 220KV-SATNA-MP-SATNA-1 |  |  | AMP Work & Line Terminal Equipment Tightness; | 28-Jul-2025 | 09:00 | 28-Jul-2025 | 18:00 | ok
S/I, SLDC MPPTCL JABALPUR