## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-21
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data availability confirmation required from communication
2 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data availability confirmation required from communication
3 | 2025-10-20 14:58 | MR2510/0492 |  | 220KV_160MVA X-MER IMP | 220KV_KOTAR | OCCM-MP | CTR DRAIN VALVE REPLACEMENT BY CTR REPRESENTATIVE | 21-10-2025 13:30:00 | 21-10-2025 17:00:00 | ARUN KUMAR KOL | 8319677721 | ok
4 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data availability confirmation required from communication
5 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data availability confirmation required from communication
6 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | OK, FTC TO BE SUBMITTED
7 |  |  |  | 132KV-VSTPS-WAIDHAN-2 | NTPC_VSTPS | MADHYA PRADESH,NTPC | Annual Bay Maitenanace/ replacement of CRP | 2025-09-03 08:00 | 2025-09-03 18:00 |  |  | ok, CKT 1 to be in service, discom to be informed ; SLDC MP Consent to be taken.Load to be managed by SLDC MP