## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-06-18 |  |  | APPROVED OUTAGE LIST FOR DTD. 18.06.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-17 14:09 | MR2506/0364 |  | 33KV_33 KV Main bus | 132KV_AMARPATAN | NON-OCCM-WR | Attend the hot points in 33 KV main bus | 18-06-2025 08:30:00 | 18-06-2025 10:30:00 | Akhilesh Singh | 9131207339 | ok
2 | 2025-06-16 18:36 | MR2506/0352 | Daily | 220KV_220 KV BHOPAL-ASHTA LINE | 400KV_ASHTA4 | NON-OCCM-MP | HOT LINE LIVE LINE PERMIT | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | consent of E&T awaited
3 | 2025-06-12 11:11 | MR2506/0261 | Daily | 400KV_400 KV ASHTA UJJAIN LINE-1, 2 | 400KV_ASHTA4 | NON-OCCM-MP | LIVE LINE PERMIT FOR FIBER MAINTENANCE SPLICING | 12-06-2025 09:00:00 | 20-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
4 | 2025-06-16 18:55 | MR2506/0355 | Daily | 220KV_220 KV BAIRAGARH MUGALIYACHAP LINE | 220KV_BAIRAGARH | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | consent of E&T awaited
5 | 2025-06-16 19:00 | MR2506/0357 | Daily | 220KV_220 KV BHOPAL BAIRAGARH LINE | 220KV_BAIRAGARH | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | consent of E&T awaited
6 | 2025-05-02 13:52 | MR2505/0038 | Continuous | 132KV_20 MVA Emco-i | 132KV_BARWANI | NON-OCCM-WR | augmentation of new 63 MVA transformer | 03-05-2025 11:00:00 | 30-06-2025 19:00:00 | vijay chand saiyam | 9425820043 | Continuous
7 | 2025-06-17 12:14 | MR2506/0359 |  | 132KV_132 KV Bina Rajghat line | 220KV_BINA | NON-OCCM-MP | Flash over disc replacement and other line mainten | 18-06-2025 10:00:00 | 18-06-2025 17:00:00 | Satish Kumar Bhagat | 9425806916 | ok
8 | 2025-06-17 15:38 | MR2506/0372 |  | 132KV_132 KV Bina-Mehaluwa Chouraha | 220KV_BINA | NON-OCCM-MP | Hot line work permit for F/o disc replacement | 18-06-2025 11:00:00 | 18-06-2025 13:00:00 | Sanjay Singh Thakur | 9425806936 | sub ld
9 | 2025-06-12 09:07 | MR2506/0260 | Daily | 220KV_220 KV Bina- Pichhore & 220 KV Bina- Datia Ckt | 400KV_BINA4 | NON-OCCM-MP | Hot line PTW for OPGW work By M/s ZTT | 12-06-2025 07:00:00 | 18-06-2025 19:00:00 | Satish Kumar Bhagat & Sanjay Singh Thakur | 9425806916 | ok, line to be in service
10 | 2025-06-12 17:15 | MR2506/0286 |  | 220KV_220KV Budhni-Pgcil (itarsi) - 2nd | 220KV_BUDHNI | NON-OCCM-WR | DTPC Commissioning & wiring , testing work | 18-06-2025 11:00:00 | 18-06-2025 17:00:00 | shri s.p.s. Tomar | 9425801629 | ok, through sub ld
11 | 2025-06-16 13:14 | MR2506/0341 | Daily | 132KV_132 kV Bijawar -Badamalhera Line | 220KV_CHATARPUR | NON-OCCM-MP | OPGW installation work | 17-06-2025 07:00:00 | 18-06-2025 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
12 | 2025-04-28 13:05 | MR2504/0766 | Continuous | 20MVA_132/33KV_BHEL_X'mer_4 | 220KV_DAMOH | OCCM-MP | augmantation of 20 MVA transformer by 63 mva trans | 28-04-2025 14:00:00 | 30-06-2025 16:00:00 | MK Choubey | 8959559657 | Continuous
13 | 2025-05-07 15:18 | MR2505/0133 | Continuous | 160MVA_220/132KV_BHEL_X'mer_1 | 220KV_HANDIYA | NON-OCCM-MP | for Replacement of Transformer | 08-05-2025 10:00:00 | 08-07-2025 17:00:00 | J.D.Khoria | 9425804975 | Continuous
14 | 2025-06-12 16:27 | MR2506/0283 | Daily | 220KV_NORTH ZONE - HATUNIYA CKT-2 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF EXISTING E/W BY 24F OPGW | 15-06-2025 07:00:00 | 25-06-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
15 | 2025-06-12 15:54 | MR2506/0282 | Daily | 220KV_NORTH ZONE - HATUNIYA CKT-1 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF EXISTING E/W BY 24F OPGW | 15-06-2025 07:00:00 | 25-06-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
16 | 2025-05-23 18:38 | MR2505/0487 | Continuous | 220KV_NARSINGHPUR-JABALPUR_Ckt_2 | 220KV_JABALPUR | NON-OCCM-MP | BUNCHING OF 132KV JBP SHAHPURA WITH220 KV JBP NSP | 26-05-2025 09:00:00 | 20-06-2025 18:00:00 | RAJESH TIWARI | 7898239595 | Deffered by site
17 | 2025-06-17 14:46 | MR2506/0366 |  | 132KV_132 kv Sleemnabad -Katni line ( from 132 kv ss katni) | 132KV_KATNI | NON-OCCM-MP | For FO disc replacement work at loc.no. 299 | 18-06-2025 10:00:00 | 18-06-2025 18:00:00 | Pankaj yadav | 9406713326 | ok
18 | 2024-11-20 16:15 | MR2411/0427 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 16-06-2025 09:00:00 | 21-06-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | approved from 19th
19 | 2024-11-20 16:18 | MR2411/0428 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 16-06-2025 09:00:00 | 21-06-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | approved from 19th
20 | 2025-06-17 15:14 | MR2506/0368 |  | 132KV_132 KV khurai-Sagar | 132KV_KHURAI | NON-OCCM-MP | for line maintenance work. | 18-06-2025 09:00:00 | 18-06-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | ok
21 | 2025-06-17 15:13 | MR2506/0367 |  | 400KV_400/132/33 KV 100 MVA X-MER no-02 BHEL | 400KV_KIRNAPUR | NON-OCCM-MP | For OLTC Oil filtration and Pre-monsoon maint work | 18-06-2025 07:00:00 | 18-06-2025 20:00:00 | D. S. Walkey | 9425804578 | ok
22 | 2025-06-17 12:49 | MR2506/0360 |  | 50MVA_132/33KV_BBL_X'mer_3 | 132KV_MORWA | NON-OCCM-MP | 132kv CT replacement work due to high tan delta v | 18-06-2025 10:00:00 | 18-06-2025 15:00:00 | S.B.Singh | 9039635859 | ok
23 | 2025-06-16 18:57 | MR2506/0356 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA LINE | 220KV_MUGALIYACHAAP | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | consent of E&T awaited
24 | 2025-06-17 13:20 | MR2506/0361 |  | 132KV_50 MVA ATLANTA X-MER | 132KV_NOWGAON | NON-OCCM-MP | FOR HOT POINT ATTENDING WORK OF LV SIDE BREKAR CLA | 18-06-2025 10:00:00 | 18-06-2025 12:00:00 | C.L. MALI | 9425806724 | ok
25 | 2025-06-09 15:58 | MR2506/0188 | Continuous | 220KV_Generating Unit No. 06 | 220KV_OMKARESHWAR | NON-OCCM-WR | Annual maintenance | 10-06-2025 10:00:00 | 24-06-2025 18:00:00 | Sh. Pankaj Sharma | 7898703187 | as per system erquirement
26 | 2025-06-16 12:02 | MR2506/0337 | Continuous | 132KV_132/33KV 50MVA BBL X-MER | 132KV_PATAN | NON-OCCM-MP | OIL LEAKAGE ATTENDING AND OTHER RELATED WORK | 17-06-2025 09:00:00 | 19-06-2025 17:00:00 | RAHUL GAJBHIYE | 9425801304 | Continuous
27 | 2025-04-28 16:55 | MR2504/0789 | Continuous | 132KV_PENCH-KANHAN_Ckt | 132KV_PENCH | OCCM-WR | Maintenance of SF6 CB | 17-06-2025 09:00:00 | 18-06-2025 20:00:00 | SE(O&M)Pench | 8329756200 | not in WR list
28 | 2025-04-28 17:02 | MR2504/0790 | Continuous | 132KV_132KV Pench Kanhan Line | 132KV_PENCH | OCCM-WR | Overhauling of 132KV SF6 CB | 17-06-2025 09:00:00 | 18-06-2025 20:00:00 | Arun Mungole | 8329756200 | not in WR list
29 | 2025-05-08 17:07 | MR2505/0173 | Continuous | 400KV_400kV SSTPH-Pithampur Line Ckt-2 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered
30 | 2025-05-08 16:57 | MR2505/0172 | Continuous | 400KV_400kVSSTPH-Pithampur Ckt-1 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered
31 | 2025-06-17 13:28 | MR2506/0363 |  | 220KV_220 kv Ratlam -Nagra Ckt-II | 220KV_RATLAM | NON-OCCM-MP | For Relay testing work | 18-06-2025 14:00:00 | 18-06-2025 17:00:00 | NIKHIL DUNGE | 9425801487 | ok, through sub ld
32 | 2025-06-17 13:24 | MR2506/0362 |  | 220KV_220 kv Ratlam -Nagra Ckt-I | 220KV_RATLAM | NON-OCCM-MP | For Relay testing work. | 18-06-2025 10:00:00 | 18-06-2025 13:00:00 | NIKHIL DUNGE | 9425801487 | ok, through sub ld
33 | 2025-06-17 11:36 | MR2506/0358 |  | 132KV_132kv Sabalgarh Motijheel Ckt | 220KV_SABALGARH | NON-OCCM-MP | LINE MAINTENANCE WORK | 18-06-2025 09:00:00 | 18-06-2025 17:00:00 | SURAJ PAWAR | 9425814079 | sub ld
34 | 2025-06-13 14:42 | MR2506/0295 | Daily | 132KV_132kv SAGAR-SAGAR IC 3 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | Work installation of OPGW | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
35 | 2025-06-13 14:38 | MR2506/0294 | Daily | 132KV_132KV SAGAR-SAGAR IC 1 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | OPGW Work installation (Hot Line Permit | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
36 | 2025-05-03 11:32 | MR2505/0054 | Continuous | 220KV_100 MVA X-mer Make CGL | 220KV_SARNI | NON-OCCM-MP | X-mer Augmentation work by 160 MVA X-mer AREVA | 05-05-2025 10:00:00 | 10-07-2025 17:00:00 | Er K.K. Choure | 9425801357 | Continuous
37 | 2025-06-15 13:13 | MR2506/0319 | Daily | 220KV_220 kv Sarni Handia | 220KV_SARNI | NON-OCCM-MP | Resagging work b/w loc.no. 192 to213 | 16-06-2025 09:00:00 | 18-06-2025 18:00:00 | Ashutosh rai | 9425806902 | ok, through sub ld
38 | 2025-05-21 18:20 | MR2505/0450 | Continuous | 400KV_400KV ASHTA LINE-I | 400KV_SATPURA TPS | NON-OCCM-MP | Maintenance & testing of bay Equipment | 16-06-2025 09:00:00 | 18-06-2025 18:00:00 | S.S THAKUR | 9425611244 | Deffered
39 | 2025-06-17 14:18 | MR2506/0365 |  | 132KV_132kV Seoni Lakhnadon SC | 220KV_SEONI | NON-OCCM-MP | Replacement of flashover disc insulator | 18-06-2025 10:00:00 | 18-06-2025 17:00:00 | S.K. Nadekar | 9425806848 | ok
40 | 2025-06-13 09:54 | MR2506/0287 | Continuous | 220KV_Birsinghpur- Manpur fdr. | 400KV_SGTPS | NON-OCCM-MP | For overhauling of 220 KV circuit breaker | 16-06-2025 08:00:00 | 19-06-2025 16:00:00 | s banerjee | 9424352880 | Continuous
41 | 2025-06-17 15:31 | MR2506/0370 |  | 132KV_132kV Sidhi - Deosar Ckt - I | 220KV_SIDHI | NON-OCCM-MP | Disc Replacement Work | 18-06-2025 09:00:00 | 18-06-2025 13:00:00 | G.L Sahu | 9425805102 | ok, o&m shall be informed
42 | 2025-06-17 15:34 | MR2506/0371 |  | 132KV_132kV Sidhi - Deosar Ckt - II | 220KV_SIDHI | NON-OCCM-MP | Disc Replacement | 18-06-2025 14:00:00 | 18-06-2025 18:00:00 | G.L Sahu | 9425805102 | ok, o&m shall be informed
43 | 2025-04-17 17:31 | MR2504/0478 | Daily | 132KV_132 kV Tikamgarh IC - 1st line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Installation work | 18-04-2025 07:00:00 | 19-06-2025 19:00:00 | MPPTCL Chhatarpur | 942580499 | ok, line to be in service
44 | 2025-04-17 17:34 | MR2504/0479 | Daily | 132KV_132 kV Tikamgarh-Badamalhera line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Installation work | 18-04-2025 07:00:00 | 19-06-2025 19:00:00 | Manoj Kumar Tiwari | 942580499 | ok, line to be in service
45 | 2025-06-17 15:14 | MR2506/0369 |  | 220KV_220 KV UJJAIN HATHUNIYA CKT1 | 220KV_UJJAIN | OCCM-WR | MAINTENNACE WORK | 18-06-2025 09:00:00 | 18-06-2025 16:00:00 | K SACHINDRA SHARMA | 7415651054 | ok, through sub ld
46 | 2025-06-17 15:14 |  |  | 220KV-PANDURNA-KALMESHWAR-1 |  | OCCM-WR | E/W Replacement & Routine Maint. Work | 18-Jun-2025 | 07:00 | 18-Jun-2025 | 18:00 | ok
47 | 2025-06-17 15:14 |  |  | 132KV-MANSAR-MS-KANHAN-1 |  | OCCM-WR | For routine maintenance work | 18-Jun-2025 | 07:00 | 18-Jun-2025 | 18:00 | ok
48 | 2025-06-17 15:14 |  |  | DAMOH - 400KV - BUS 1 |  | OCCM-WR | AMP work of 400KV Bus1 | 18-Jun-2025 | 09:00 | 18-Jun-2025 | 18:00 | Deffered, due to multiple outages on lines feeding Bhopal
49 | 2025-06-17 15:14 |  |  | 220KV-ITARSI-BUDNI-2 |  | OCCM-WR | s/d required for DTPC commissioning, wiring and testing work at Itarsi PG end | 18-Jun-2025 | 11:00 | 18-Jun-2025 | 16:59 | ok, through sub ld
50 | 2025-06-17 15:14 |  |  | 220KV-GWALIOR-MAHALGAON-2 |  | OCCM-WR | FOR BAY MAINTENANCE & TESTING WORK | 18-Jun-2025 | 09:00 | 18-Jun-2025 | 17:00 | real time
51 | 2025-06-17 15:14 |  |  | 220KV-INDORE-UJJAIN-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 18-Jun-2025 | 08:00 | 18-Jun-2025 | 18:00 | ok, through sub ld
52 | 2025-06-17 15:14 |  |  | 220KV-BETUL-PANDURNA-1 |  | OCCM-WR | FOR CONDUCTOR RE-SAGGING WORKS IN VARIOUS SECTION | 18-Jun-2025 | 08:00 | 18-Jun-2025 | 18:00 | real time
53 | 2025-06-17 15:14 |  |  | 220KV-SEONI-PG-CHINDWARA-2 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 18-Jun-2025 | 09:00 | 18-Jun-2025 | 18:00 | real time
54 | 2025-06-17 15:14 |  |  | 220KV-KHANDWA-CHHEGAON-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 18-Jun-2025 | 08:00 | 18-Jun-2025 | 18:00 | real time
55 | 2025-06-17 15:14 |  |  | 400KV-SINGAJI-PITHAMPUR-1 |  | OCCM-WR | for tower strengthening works | 16-Jun-2025 | 08:00 | 30-Jun-2025 | 17:59 | deffered
56 | 2025-06-17 15:14 |  |  | 400KV-SINGAJI-PITHAMPUR-2 |  | OCCM-WR | for tower strengthening works | 16-Jun-2025 | 08:00 | 30-Jun-2025 | 17:59 | deffered
S/I, SLDC MPPTCL JBP