## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-04
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-25 15:08 | MR2508/0326 | Daily | 220KV_220KV Anuppur Kotmikala ckt-2 | 220KV_ANUPPUR | NON-OCCM-MP | For Re-sagging work due to Low Ground clearance ma | 31-08-2025 08:00:00 | 08-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
2 | 2025-09-03 14:42 | MR2509/0079 |  | 220KV_220KV Badnawar-Barnagar ckt-1st | 400KV_BADNAWAR | NON-OCCM-MP | Installation of IInd DPR & Testing work | 04-09-2025 10:00:00 | 04-09-2025 17:00:00 | Er. Abhishek Verma | 9340855901 | OK THROUGH SUB LD
3 | 2025-09-03 16:02 | MR2509/0082 |  | 132KV_132 kV Shahdol-Birsingpur Circuit II | 220KV_BIRSINGHPUR | NON-OCCM-MP | Replacement of damaged OPGW | 04-09-2025 09:00:00 | 04-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
4 | 2025-09-03 13:22 | MR2509/0074 |  | 220KV_220 KV Chhatarpur-Tikamgarh Bay | 220KV_CHATARPUR | NON-OCCM-MP | for line & Auxillary isolator alignmant work | 04-09-2025 10:00:00 | 04-09-2025 16:00:00 | Brajendra Soni | 9131327770 | OK
5 | 2025-09-03 13:09 | MR2509/0073 |  | 220KV_200mva x-mer IV (T&R) | 400KV_CHHEGAON4 | NON-OCCM-MP | Post mansoon maint. work | 04-09-2025 10:00:00 | 04-09-2025 18:00:00 | Shri Ganesh Mansare | 9425802441 | OK THROUGH SUB LD
6 | 2025-09-03 14:24 | MR2509/0078 |  | 132KV_132 KV KATNI PANAGAR LINE | 132KV_KATNI | NON-OCCM-MP | maintenance work | 04-09-2025 10:00:00 | 04-09-2025 18:00:00 | PANKAJ YADAV | 9306713326 | OK
7 | 2025-06-30 16:15 | MR2506/0636 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 01-09-2025 09:00:00 | 06-09-2025 18:00:00 | PANKAJ YADAV | 9406713326 | DEFERRED WRPC CONSENT REQUIRED
8 | 2025-06-30 15:33 | MR2506/0626 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 01-09-2025 09:00:00 | 06-09-2025 18:00:00 | PANKAJ YADAV | 9406713326 | DEFERRED WRPC CONSENT REQUIRED
9 | 2025-09-03 13:49 | MR2509/0076 |  | 132KV_132KV MAHALGAON- SITHOLI Ckt. | 220KV_MAHALGAON | NON-OCCM-MP | Tan Delta Measurement of CT | 04-09-2025 10:00:00 | 04-09-2025 17:00:00 | P. Datey | 9425807712 | SUB LD
10 | 2025-09-03 13:47 | MR2509/0075 |  | 220KV_22KV MAHALGAON - PGCIL 3rd Ckt. | 220KV_MAHALGAON | NON-OCCM-MP | Tan Delta Measurement of CT | 04-09-2025 10:00:00 | 04-09-2025 17:00:00 | P. Datey | 9425807712 | DEFERRED WRPC CONSENT REQUIRED
11 | 2025-09-03 12:01 | MR2509/0068 |  | 132KV_132/33 KV 40 MVA X-MER MAKE IMP | 132KV_PRATAPPURA | NON-OCCM-MP | POST MONSOON MAINTENANCE | 04-09-2025 10:00:00 | 04-09-2025 17:00:00 | VIKRAM AHIRWAR | 9425805415 | SUB LD
12 | 2025-09-03 16:00 | MR2509/0080 |  | 220KV_220 KV JULWANIYA-SENDHWA CKT-2 | 220KV_SENDHWA | NON-OCCM-MP | For DPR & DTPC Wiring | 04-09-2025 10:00:00 | 04-09-2025 17:00:00 | Kashiram khanna | 9826732087 | OK THROUGH SUB LD
13 | 2025-09-03 16:17 | MR2509/0083 |  | 132KV_132KV SIDHI-MAUGANJ CKT-I | 220KV_SIDHI | NON-OCCM-MP | FLASH OVER DISC REPLACEMENT | 04-09-2025 10:00:00 | 04-09-2025 17:00:00 | G.L SAHU | 9425805102 | OK
14 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | OK, FTC TO BE SUBMITTED & EI APPROVAL REQUIRED PRIOR TO CHARGING
15 | 2025-09-03 11:06 | MR2509/0067 |  | 220KV_160 MVA X-MER IIND | 400KV_UJJAIN4 | NON-OCCM-WR | TRANSFORMER TESTING AND BAY MAINTENANCE WORK | 04-09-2025 10:00:00 | 04-09-2025 17:00:00 | S. CHAVRASIA | 9425804677 | OK THROUGH SUB LD
16 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | RAJESH TIWARI | 7898239595 | CONTINUE
17 |  |  |  | 132/33 KV 63 MVA BBL X-MER | 132 KV S/S MARHOTAL JABALPUR |  | OIL LEAKAGE ATTENDING WORK | 2025-09-04 11:00 | 2025-09-04 15:00 |  |  | OK
18 |  | 260629 | Daily | 400KV/220KV ITARSI-ICT-2 | 400KV/220KV |  | AMP of ICT#2, Dia to be kept open at both sides. | 04-Sep-2025 | 09:00 | 04-Sep-2025 | 20:00 | OK THROUGH SUB LD
19 |  | 260569 | Daily | 220KV-MALANPUR-AURIYA-1 | 220 |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 04-Sep-2025 | 09:00 | 04-Sep-2025 | 17:00 | OK THROUGH SUB LD
20 |  | 260570 | Daily | 220KV-SHUJALPUR-SHUJALPUR-MP-2 | 220 |  | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 04-Sep-2025 | 09:00 | 04-Sep-2025 | 17:00 | OK THROUGH SUB LD
21 |  | 260571 | Daily | 220KV-SATNA-KOTAR-1 | 220 |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 04-Sep-2025 | 10:00 | 04-Sep-2025 | 17:00 | OK
22 |  | 262515 | Daily | 220KV-ANNUPUR-KOTMIKALA-2 | 220 |  | For Re-sagging work due to Low Ground clearance at loc. 371-379 & 464- 475 | 04-Sep-2025 | 08:00 | 04-Sep-2025 | 17:59 | OK
23 |  | 260626 | Continous | 400KV-SATPURA-ITARSI-1 | 400 |  | For replacemnet of Bus-1 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400kV Bus-1 is required at Sarni S/S of MPGENCO) AND CT Oil sampling at Itarsi And CVT Replacement of 400KV-SATPURA-ITARSI-1 under ADD CAP at MPGENCO | 02-Sep-2025 | 09:00 | 05-Sep-2025 | 20:00 | CONTINUE
24 |  | 260627 | Continous | SATPURA - 400KV - BUS 1 | 400 |  | For replacemnet of Bus-1 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400KV-SATPURA-ITARSI-1 is required) | 02-Sep-2025 | 09:00 | 05-Sep-2025 | 20:00 | CONTINUE