## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-30 |  |  | APPROVED OUTAGE LIST FOR DATED 30.08.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | LINE END (IN CASE OF LINE) | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Status | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-29 13:06 | MR2508/0405 |  | 33KV_33 KV main bus and both Xmer | 132KV_AMARPATAN | NON-OCCM-MP | attend hot in 33 KV tala main bus |  | 30-08-2025 09:30:00 | 30-08-2025 11:30:00 | Waiting | Arun Kol | 9425815346 | O&M CONSENT REQUIRED
2 | 2025-08-29 10:57 | MR2508/0398 |  | 132KV_132 KV main bus section -1 | 132KV_BALAGHAT | NON-OCCM-MP | new PT bay jumper connection work |  | 30-08-2025 11:00:00 | 30-08-2025 14:00:00 | Waiting | swati Bisen | 9425801737 | OK FROM 11:00 TO 11:30 HRS AND FROM 13:30 TO 14:00HRS
3 | 2025-08-29 12:35 | MR2508/0401 |  | 132KV_132kV Balaghat Waraseoni Line | 132KV_BALAGHAT | NON-OCCM-MP | Suspension Clamp & Emergency Tree Cutting |  | 30-08-2025 08:00:00 | 30-08-2025 12:00:00 | Waiting | S.K. BHALADHARE | 9425807264 | OK
4 | 2025-08-12 17:39 | MR2508/0176 | Daily | 220KV_220KV South Zone (Indore) â¿¿ Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre |  | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | Accepted | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
5 | 2025-08-29 11:42 | MR2508/0399 | Daily | 220KV_220KV Indore (400KV Mangliya Line. | 220KV_INDORE-SZ | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre |  | 29-08-2025 07:00:00 | 03-09-2025 19:00:00 | Waiting | A.R.KANEL | 9425805217 | DATA REROUTING REQUIRED AND CONFIRMATION REQUIRED FROM COMMUNICATION
6 | 2025-08-26 18:22 | MR2508/0354 | Continuous | 132KV_132 KV JBP-SAHPURA DP LINE | 220KV_JABALPUR | OCCM-MP | REPLACEMENT OF TOWER LOC NO 5 |  | 28-08-2025 10:00:00 | 02-09-2025 19:00:00 | Waiting | RAJESH TIWARI | 7898239595 | CONTINUE, EI APPROVAL TO BE SUBMITTED PRIOR TO CHARGING
7 | 2025-08-29 13:26 | MR2508/0406 |  | 220KV_220 kV Jabalpur- Birsinghpur ckt-I | 220KV_JABALPUR | NON-OCCM-MP | Disc F/o change at loc. C51 Top Phase |  | 30-08-2025 10:00:00 | 30-08-2025 18:00:00 | Accepted | Jitendra Tiwari | 9425805298 | OK
8 | 2025-06-30 15:28 | MR2506/0625 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENTHENING WORK |  | 25-08-2025 09:00:00 | 30-08-2025 18:00:00 | Waiting | PANKAJ YADAV | 9406713326 | DEFERRED, WRPC CONSENT REQUIRED
9 | 2025-06-30 16:11 | MR2506/0634 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK |  | 25-08-2025 09:00:00 | 30-08-2025 18:00:00 | Waiting | PANKAJ YADAV | 9406713326 | DEFERRED, WRPC CONSENT REQUIRED
10 | 2025-08-12 17:42 | MR2508/0177 | Daily | 220KV_220KV Mangliya -Jaitpura Line | 220KV_MANGLIA2 | NON-OCCM-MP | 24 Fibre OPGW by 48 Fibre OPGW work |  | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | Accepted | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
11 | 2025-08-29 11:47 | MR2508/0400 | Daily | 220KV_220KV Indore (400KV) â¿¿ South Zone (I/C- 3) Line | 220KV_MANGLIA2 | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre |  | 29-08-2025 07:00:00 | 03-09-2025 19:00:00 | Waiting | A.R.KANEL | 9425805217 | DATA REROUTING REQUIRED AND CONFIRMATION REQUIRED FROM COMMUNICATION
12 | 2025-08-29 14:02 | MR2508/0407 |  | 220KV_160 MVA-III (BHEL) | 220KV_PITHAMPUR (SEC-III) | NON-OCCM-MP | NIFPS (CTR) system testing work by company |  | 30-08-2025 10:00:00 | 30-08-2025 18:00:00 | Accepted | RAJU DAS BAIRAGI | 9425801532 | OK THROUGH SUB LD
13 | 2025-08-29 16:15 | MR2508/0412 |  | 132KV_IC-1 | 132KV_REWA1 | NON-OCCM-MP | R&B ph CT replacement work |  | 30-08-2025 09:00:00 | 30-08-2025 18:00:00 | Accepted | Kanishka Singh | 9425804656 | OK LINE WILL BE IN SERVICE THROUGH TBC
14 | 2025-08-28 12:29 | MR2508/0377 |  | 132KV_132KV Main Bus | 132KV_WARASEONI | NON-OCCM-MP | For Jumper connection work with 132kv Main Bus |  | 30-08-2025 08:00:00 | 30-08-2025 12:00:00 | Waiting | Vijay Kumar Tandekar | 9425805095 | OK
15 |  |  |  | 400KV-BINA-MP-BINA-3 | POWERGRID-WR2 (PGCIL) |  | Simultaneous ouatge of765KV/400KV BINA-ICT-2 &400KV-BINA-MP-BINA-3 required for Bay-420 LBB Testing.Dia to be kept open at both ends. |  | 9:00 | 15:00 |  |  |  | OK THROUGH SUB LD
16 |  |  |  | 220KV-MORENA-MEHGAON-1 | MP |  | FOR LINE MAINTENANCE WORK |  | 8:00 | 17:00 |  |  |  | OK THROUGH SUB LD
17 |  |  |  | 220KV-RAJGARH-RAJGARH-MP-2 | MP |  | FOR LINE MAINTENANCE WORK |  | 9:00 | 18:00 |  |  |  | OK THROUGH SUB LD
18 |  |  |  | 132KV-DHARNI-NEPANAGAR-1 | MAH |  | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme |  | 7:00 | 19:00 |  |  |  | OK LINE TO BE IN SERVICE