## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-25 |  |  | APPROVED OUTAGE LIST FOR DATED 25.07.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
2 | 2025-07-24 15:36 | MR2507/0391 |  | 220KV_220KV CHHATARPUR - AJAYGARH (TBCB) IIND CKT. LINE | 220KV_CHATARPUR | NON-OCCM-MP | FOR SLIP/MISSING VD ATTENDING&OTHER MAINTENANCE | 25-07-2025 10:00:00 | 25-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Deffered due to s/d on 220kv Ajaygarh-Satna PG by PGCIL
3 | 2025-07-24 15:29 | MR2507/0390 |  | 220KV_220 KV Chhegaon-Nimrani-II | 400KV_CHHEGAON4 | NON-OCCM-MP | CVT Wiring Work | 25-07-2025 10:30:00 | 25-07-2025 17:00:00 | Ganesh Mansare | 9425802441 | ok, through sub ld
4 | 2025-07-24 15:13 | MR2507/0388 |  | 132KV_132 KV Main Bus Section -I | 132KV_DAMOH1 | NON-OCCM-MP | 50 MVA X-mer main bus isolater hot point arrending | 25-07-2025 07:00:00 | 25-07-2025 10:00:00 | B K Sahu | 9425801433 | o&m consent required
5 | 2025-07-22 11:31 | MR2507/0311 |  | 220KV_Dhar to Rajgarh (PGCIL) ckt | 220KV_DHAR | OCCM-MP | For line maintenance work | 25-07-2025 10:00:00 | 25-07-2025 18:00:00 | V.R. Panadia | 9425802330 | ok, through sub ld
6 | 2025-07-24 15:13 | MR2507/0389 |  | 220KV_BARWAHA-HANDIYA_Ckt | 220KV_HANDIYA | NON-OCCM-MP | DPR RELAY TESTING WORK AT 220KV SS HANDIYA | 25-07-2025 09:00:00 | 25-07-2025 16:00:00 | K.R. DONGRE | 9425802263 | ok, through sub ld
7 | 2025-06-30 14:52 | MR2506/0617 | Continuous | 400KV_400KV KATNI-DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 21-07-2025 09:00:00 | 26-07-2025 18:00:00 | SHRI PANKAJ YADAV | 9406713326 | Deffered , not in WR list
8 | 2025-06-30 15:42 | MR2506/0629 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 21-07-2025 09:00:00 | 26-07-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
9 | 2025-07-18 16:14 | MR2507/0262 | Continuous | 132KV_132 KV Khurai- Sagar Ckt | 132KV_KHURAI | NON-OCCM-MP | For modification of 132 Khurai-sagar line | 18-07-2025 07:00:00 | 27-07-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | Continuous
10 | 2025-07-24 15:10 | MR2507/0387 |  | 220KV_220KV MANDSAUR-GUJARKHEDI CKT-2 | 400KV_MANDSOUR4 | OCCM-MP | ADDITIONAL DPR-2 CONNECTING & MAINT WORK | 25-07-2025 10:00:00 | 25-07-2025 17:00:00 | RAJESH BHURIA | 9425806920 | ok, through sub ld
11 | 2025-07-23 21:04 | MR2507/0377 | Daily | 132KV_132kV Nainpur Keolari | 132KV_NAINPUR | NON-OCCM-MP | Replacement of Defective OPGW of Line 210-212 | 24-07-2025 10:00:00 | 25-07-2025 18:00:00 | S.K.Nadekar | 9425806848 | ok
12 | 2025-07-24 12:50 | MR2507/0381 | Continuous | 220KV_220KV Neemuch Mandsaur Circuit Ist | 220KV_NEEMUCH | NON-OCCM-MP | For OPGW Work | 25-07-2025 08:00:00 | 28-07-2025 16:00:00 | Gaurav Goyal | 9425805120 | pl ensure the availabililty of telemetry/communication data before permit
13 | 2025-07-24 14:21 | MR2507/0386 | Daily | 220KV_220KV Neemuch Mandsaur Circuit Ist | 220KV_NEEMUCH | NON-OCCM-MP | only hotline permit | 25-07-2025 08:00:00 | 27-07-2025 19:00:00 | Gaurav Goyal | 9425805120 | pl ensure the availabililty of telemetry/communication data before permit
14 | 2025-07-24 14:16 | MR2507/0385 | Continuous | 220KV_220KV Neemuch-Mandsaur Circuit IInd | 220KV_NEEMUCH | NON-OCCM-MP | OPGW Work | 25-07-2025 09:00:00 | 27-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | pl ensure the availabililty of telemetry/communication data before permit
15 | 2025-07-22 13:19 | MR2507/0315 | Continuous | 132KV_132KV Neemuch-Budha Line | 220KV_NEEMUCH | NON-OCCM-MP | For OPGW Testing & OPGW Splicing | 23-07-2025 08:30:00 | 30-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | sub ld
16 | 2025-07-05 17:07 | MR2507/0079 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Insatallation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
17 | 2025-07-05 16:59 | MR2507/0078 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) LIne | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
18 | 2025-07-11 16:53 | MR2507/0159 | Daily | 220KV_Main BUSâ¿¿B and Bus Coupler | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual Maintenance | 23-07-2025 09:00:00 | 26-07-2025 18:00:00 | PANKAJ SHARMA | 7898703187 | Deffered due to high OSP
19 | 2025-07-24 13:56 | MR2507/0383 |  | 132KV_132KV Pithampur-Betma Ckt-2 Line | 220KV_PITHAMPUR (SEC-III) | NON-OCCM-MP | replacement of old burned PG clamps of R & Y phas | 25-07-2025 10:30:00 | 25-07-2025 18:00:00 | A.R.KANEL | 9425805217 | sub ld
20 | 2025-07-17 15:15 | MR2507/0245 | Continuous | 400KV_400 KV MAIN BUS-2 | 400KV_SAGAR | OCCM-MP | FOR EXTENSION OF MAIN BUS -2 | 25-07-2025 08:00:00 | 26-07-2025 17:00:00 | ANIL MAHOR | 9425805149 | Deffered due to s/d on BINA PG bus s/d
21 | 2025-07-19 17:13 | MR2507/0270 | Daily | 132KV_132kV Seoni Nainpur Ckt-IInd | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section 31-37 | 22-07-2025 09:00:00 | 26-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
22 | 2025-07-19 17:15 | MR2507/0271 | Daily | 132KV_132kV Seoni Keolari Line | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section 31-37 | 22-07-2025 09:00:00 | 26-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | Deffered by site
23 | 2025-07-01 17:00 | MR2507/0020 |  | 220KV_220KV Singaji Chhegaon feeder-1 | 400KV_SINGHAJI TPS | NON-OCCM-MP | Relay Testing work of 220KV Chhegaon-1 during AOH | 25-07-2025 10:00:00 | 25-07-2025 19:00:00 | Deepak Sharma | 8005696855 | ok, through sub ld
24 | 2025-07-24 14:00 | MR2507/0384 |  | 132KV_Shutdown (H/T) of 132 kv Sirmaur-Katra Ckt-1 DCDS line | 220KV_SIRMOUR | NON-OCCM-WR | Replacement of flashover disc | 25-07-2025 11:00:00 | 25-07-2025 17:00:00 | Mr. Ajay Kumar Chaurasia | 9425805081 | ok
25 | 2025-07-24 15:43 | MR2507/0395 |  | 220KV_220 KV Interconnector-III | 400KV_UJJAIN4 | NON-OCCM-MP | FOTE Panel wiring & commissioning work | 25-07-2025 13:00:00 | 25-07-2025 14:00:00 | Mr. Santosh Chavrasia | 9425804677 | pl ensure the availabililty of telemetry/communication data before permit
26 | 2025-07-24 15:50 | MR2507/0398 |  | 220KV_220 KV Interconnector-IV | 400KV_UJJAIN4 | NON-OCCM-MP | FOTE Panel wiring & commissioning work | 25-07-2025 15:00:00 | 25-07-2025 16:00:00 | Santosh Chavrasia | 9425804677 | pl ensure the availabililty of telemetry/communication data before permit
27 | 2025-07-24 15:41 | MR2507/0394 |  | 220KV_220 KV Interconnector-II | 400KV_UJJAIN4 | NON-OCCM-MP | FOTE Panel wiring & commissioning work | 25-07-2025 12:00:00 | 25-07-2025 13:00:00 | Mr. Santosh Chavrasia | 9425804677 | pl ensure the availabililty of telemetry/communication data before permit
28 | 2025-07-24 15:47 | MR2507/0396 |  | 220KV_220 KV Interconnector-III | 400KV_UJJAIN4 | NON-OCCM-MP | FOTE Panel wiring & commissioning work | 25-07-2025 14:00:00 | 25-07-2025 15:00:00 | Santosh Chavrasia | 9425804677 | pl ensure the availabililty of telemetry/communication data before permit
29 | 2025-07-24 15:38 | MR2507/0393 |  | 220KV_220 KV Interconnector-1st | 400KV_UJJAIN4 | NON-OCCM-MP | FOTE Panel wiring & commissioning work | 25-07-2025 11:00:00 | 25-07-2025 12:00:00 | Mr. Santosh Chavrasia | 9425804677 | pl ensure the availabililty of telemetry/communication data before permit
30 | 2025-07-24 13:12 | MR2507/0382 |  | 132KV_132KV MAIN BUS | 132KV_VFJ | NON-OCCM-MP | HOT POINT MAIN BUS FLYOVER R-PHASE JUMPER I | 25-07-2025 08:00:00 | 25-07-2025 10:00:00 | AMIT KUMAR DAHIYA | 9425806926 | o&m consent required
31 |  |  |  | 400KV-BHOPAL-MP-ITARSI-2 |  | MADHYA PRADESH | FOR BAY MAINTENANCE & TESTING WORK | 25-Jul-2025 | 09:00 | 25-Jul-2025 | 18:00 | real time
32 |  |  |  | 220KV-ANNUPUR-KOTMIKALA-1 |  | MADHYA PRADESH,CHATTISGARH | FOR LINE MAINTENANCE WORK | 25-Jul-2025 | 09:00 | 25-Jul-2025 | 18:00 | real time
33 |  |  |  | 220KV-REWA-SINDHI-MP-2 |  | MADHYA PRADESH | FOR LINE MAINTENANCE WORK ( REWA RUMS) | 25-Jul-2025 | 10:00 | 25-Jul-2025 | 17:00 | real time
34 |  |  |  | 220KV-RAJGARH-DHAR-1 |  | MADHYA PRADESH | LINE MAINTENANCE WORK | 25-Jul-2025 | 08:00 | 25-Jul-2025 | 18:00 | ok, through sub ld
35 |  |  |  | 220KV-AJAYGARH-SATNA-1 |  | MADHYA PRADESH | AMP Work & Line Terminal Equipment Tightness; | 25-Jul-2025 | 09:00 | 25-Jul-2025 | 18:00 | ok
36 |  |  |  | BINA - 400KV - BUS 1 |  | POWERGRID-WR2 (PGCIL) | Simultaneous ouatge of BINA - 400KV - BUS 1 & 400KV-SATNA-BINA-2 has been required for Bay-416 LBB Testing | 25-Jul-2025 | 09:00 | 25-Jul-2025 | 15:00 | ok
37 |  |  |  | 132KV-DHARNI-NEPANAGAR-1 |  | MAHARASHTRA | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 25-Jul-2025 | 08:00 | 25-Jul-2025 | 17:59 | ok
S/I SLDC JABALPUR