## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-27 |  | APPROVED OUTAGE LIST FOR DATED 27.09.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-09-26 15:44 | MR2509/0722 |  | 132KV_132 kV Anuppur-Janakpur Circuit | 220KV_ANUPPUR | NON-OCCM-MP | F/o disc stringing replacement and other line main | 27-09-2025 10:00:00 | 27-09-2025 17:00:00 | Jitendra Tiwari | 9425805298 | ok
2 | 2025-09-25 10:17 | MR2509/0670 | Daily | 132KV_132kV Balaghat Baihar Line | 132KV_BALAGHAT | NON-OCCM-MP | Hand Trip due To load Manage | 27-09-2025 08:00:00 | 30-09-2025 17:00:00 | S.K. BHALADHARE | 9425807264 | ok
3 | 2025-09-26 13:01 | MR2509/0712 |  | 132KV_132 KV Main bus at Bhoura | 132KV_BHONRA | NON-OCCM-MP | 132 KV MAIN BUS TO ISOLATOR JUMPER WORK | 27-09-2025 12:00:00 | 27-09-2025 15:00:00 | Er. Sunny Kumar | 9425806888 | sub ld
4 | 2025-09-24 18:11 | MR2509/0666 | Continuous | 220KV_220 KV Bhopal-Sukhi Interconnector 2 on Bus Transfer | 220KV_BHOPAL | NON-OCCM-MP | Main CB is not reliable and is giving trouble | 24-09-2025 18:00:00 | 27-09-2025 17:00:00 | A K Jain | 9425806899 | Continuous
5 | 2025-09-26 11:14 | MR2509/0707 |  | 400KV_315MVA X-MER(BHEL) | 400KV_BINA4 | NON-OCCM-MP | Post Monsoon Maintenance | 27-09-2025 09:00:00 | 27-09-2025 18:00:00 | Mr.P.N. Namdeo | 7587951092 | ok, through sub ld
6 | 2025-09-20 14:29 | MR2509/0503 | Daily | 132KV_132 kV Shahdol-Birsinghpur Circuit I | 220KV_BIRSINGHPUR | NON-OCCM-MP | For replacement of damaged OPGW | 21-09-2025 09:00:00 | 27-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
7 | 2025-09-26 13:52 | MR2509/0718 |  | 220KV_220kV Chhatarpur-Ajaygarh (TBCB) Ckt. Ist Line | 220KV_CHATARPUR | NON-OCCM-MP | Missing VD/AH Provided & other Line maintenance | 27-09-2025 10:00:00 | 27-09-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
8 | 2025-09-20 18:35 | MR2509/0513 | Daily | 220KV_220KV DAMOH - DAMOH IC IIIRD CKT | 220KV_DAMOH | OCCM-MP | FOR OPGW INSTALLATION WORK | 23-09-2025 07:00:00 | 30-09-2025 19:00:00 | M.M. BAIG | 9425805067 | Deffered, not in WR list
9 | 2025-09-20 14:29 | MR2509/0504 | Daily | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | For replacement of damaged OPGW | 21-09-2025 09:00:00 | 27-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
10 | 2025-09-07 13:02 | MR2509/0161 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-2 | 220KV_INDORE NORTH | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
11 | 2025-09-07 12:51 | MR2509/0159 | Daily | 132KV_132KV North Zone- Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
12 | 2025-09-07 12:45 | MR2509/0158 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
13 | 2025-09-26 13:39 | MR2509/0715 |  | 132KV_63 MVA BBL XMER | 132KV_KHAJURAHO | NON-OCCM-MP | POST MANSOON TESTING | 27-09-2025 09:00:00 | 27-09-2025 13:00:00 | BRAJENDRA SONI | 9131327770 | ok
14 | 2025-09-26 13:42 | MR2509/0717 |  | 132KV_40 MVA ECE XMER | 132KV_KHAJURAHO | NON-OCCM-MP | POST MANSOON TESTING | 27-09-2025 14:00:00 | 27-09-2025 18:00:00 | BRAJENDRA SONI | 9131327770 | ok
15 | 2025-09-23 11:06 | MR2509/0576 | Daily | 132KV_132kV Balaghat Kirnapur Ckt-IInd | 400KV_KIRNAPUR | NON-OCCM-MP | Re-sagging of section Loc 465 to 478 & 529 to 547 | 27-09-2025 08:00:00 | 30-09-2025 17:00:00 | Shridhar Kumar Bhaladhare | 9425448642 | deffered, due to s/d on ckt 1
16 | 2025-09-26 11:45 | MR2509/0708 |  | 132KV_132kV Balaghat Kirnapur Ckt-Ist | 400KV_KIRNAPUR | NON-OCCM-MP | Re-sagging of section Loc 465 to 478 & 529 to 547 | 27-09-2025 08:00:00 | 27-09-2025 17:00:00 | Shridhar Kumar Bhaladhare | 9425448642 | ok, 132kv Balaghat-Baihar ckt to be opened for load management
17 | 2025-09-26 12:51 | MR2509/0711 |  | 220KV_220KV Nagda-IC-II Line | 400KV_NAGDA4 | NON-OCCM-MP | Line Maintenance Work. | 27-09-2025 10:00:00 | 27-09-2025 18:00:00 | Kamal Solanki | 9425805262 | ok, through sub ld
18 | 2025-09-26 13:01 | MR2509/0713 | Continuous | 132KV_132 KV NARSINGHPUR -BARMAN-I | 220KV_NARSINGHPUR | NON-OCCM-MP | Repl. of old Ckt. of barman-1 bay load shifted by | 26-09-2025 13:00:00 | 27-09-2025 18:00:00 | Dinesh kumar Kushwaha | 9425801319 | Continuous
19 | 2025-09-07 12:39 | MR2509/0157 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line. | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
20 | 2025-09-26 15:49 | MR2509/0723 |  | 132KV_63 MVA X-mer-II make BBL | 220KV_RAJGARH DHAR | NON-OCCM-MP | Post monsoon maintenance work. | 27-09-2025 10:00:00 | 27-09-2025 17:00:00 | Er. Manoj Randha | 9425820034 | sub ld
21 | 2025-09-26 15:35 | MR2509/0721 |  | 132KV_40MVA XMER-3 BHEL | 132KV_REWA1 | NON-OCCM-MP | Post monsoon maintenance and testing | 27-09-2025 11:00:00 | 27-09-2025 18:00:00 | Kanishka Singh | 9425804656 | ok
22 | 2025-09-20 18:32 | MR2509/0512 | Daily | 220KV_220KV DAMOH - SAGAR PGCIL IIND CKT. | 400KV_SAGAR | OCCM-MP | FOR OPGW INSTALLATION WORK | 23-09-2025 07:00:00 | 30-09-2025 19:00:00 | M.M. BAIG | 9425805067 | Deffered, not in WR list
23 | 2025-09-26 11:06 | MR2509/0706 |  | 220KV_160 MVA XMER-I | 220KV_SHAJAPUR | NON-OCCM-MP | POST MONSOON MAIN. WORK. | 27-09-2025 09:00:00 | 27-09-2025 17:00:00 | Er. VIJAY OJHA | 9755836908 | ok, through sub ld
24 | 2025-09-26 16:31 | MR2509/0725 |  | 220KV_220KV Shivpuri Sabalgarh Ckt Ist | 220KV_SHIVPURI | NON-OCCM-MP | Line Maintenance work | 27-09-2025 09:00:00 | 27-09-2025 17:00:00 | Suraj Pawar | 9425814079 | ok, through sub ld
25 | 2025-09-26 15:49 | MR2509/0724 |  | 132KV_132kV Sidhi - Mauganj Ckt - I | 220KV_SIDHI | NON-OCCM-MP | Disc F/o Replacement | 27-09-2025 09:30:00 | 27-09-2025 17:00:00 | G.L Sahu | 9425805102 | ok
26 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous