## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-15 |  |  | 2025-08-15
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-12 17:20 | MR2508/0174 | Daily | 220KV_220KV South Zone (Indore) â¿¿ Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | . Replacement existing of 24 Fibre OPGW by 48 Fibr | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
2 | 2025-06-30 15:17 | MR2506/0623 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 11-08-2025 09:00:00 | 16-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
3 | 2025-06-30 16:06 | MR2506/0632 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 11-08-2025 09:00:00 | 16-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
4 | 2025-08-12 17:23 | MR2508/0175 | Daily | 220KV_220KV Mangliya -Jaitpura Line. | 220KV_MANGLIA2 | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
5 | 2025-07-22 16:42 | MR2507/0344 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Installation of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | sub ld
6 | 2025-07-22 16:47 | MR2507/0345 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installatin of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
7 | 2025-08-10 17:45 | MR2508/0134 | Continuous | 132KV_132KV RAJMILAN-JANAKPUR (CGPTCL) CKT | 132KV_RAJMILAN | NON-OCCM-MP | Tower Erection work | 11-08-2025 08:00:00 | 16-08-2025 18:00:00 | G.L SAHU | 9425805102 | Continuous
8 | 2025-08-10 17:51 | MR2508/0135 | Continuous | 132KV_132KV Rajmilan-Dongrital ckt | 132KV_RAJMILAN | NON-OCCM-MP | Tower Erection work | 11-08-2025 08:00:00 | 16-08-2025 18:00:00 | G.L SAHU | 9425805102
9 |  | 261907 |  | 132KV-DHARNI-NEPANAGAR-1 |  | WR-OCCM | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 15-08-2025 07:00:00 | 15-08-2025 18:59:00 |  |  | OK A/R in N/A, Line will be in service.
10