## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-05
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-30 16:24 | MR2506/0639 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA | 400KV_ASHTA4 | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
2 | 2025-06-30 16:26 | MR2506/0640 | Daily | 220KV_220 KV BAIRAGARH-ASHTA | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-06-30 16:13 | MR2506/0635 | Daily | 220KV_220 BHOPAL-BAIRAGARH CKT-3 | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
4 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
5 | 2025-06-26 14:17 | MR2506/0554 | Daily | 220KV_220 KV Bina-Guna Ckt & 220 KV Bina-Ashoknagar Ckt | 400KV_BINA4 | NON-OCCM-MP | Hot line PTW for OPGW resagging work BY M/s ZTT | 26-06-2025 07:00:00 | 10-07-2025 19:00:00 | Sanjay singh thakur | 9425806936 | ok, line to be in service
6 | 2025-06-30 15:05 | MR2506/0620 | Continuous | 132KV_132KV Budha Mandsaur | 132KV_BUDHA | NON-OCCM-MP | in OPGW OTDR Testing and OPGW Splicing | 01-07-2025 08:30:00 | 08-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | sub ld
7 | 2025-05-07 15:18 | MR2505/0133 | Continuous | 160MVA_220/132KV_BHEL_X'mer_1 | 220KV_HANDIYA | NON-OCCM-MP | for Replacement of Transformer | 08-05-2025 10:00:00 | 08-07-2025 17:00:00 | J.D.Khoria | 9425804975 | Continuous
8 | 2025-06-23 17:09 | MR2506/0482 | Daily | 220KV_220 KV South Zone - Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
9 | 2025-06-23 17:04 | MR2506/0481 | Daily | 220KV_220KV Indore (400KV) - Mangliya line | 400KV_INDORE4 | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
10 | 2025-07-04 16:12 | MR2507/0068 |  | 220KV_220kv Bandawar kanwan ckt 2 | 220KV_KANWAN2 | NON-OCCM-WR | line maintenance work | 05-07-2025 10:00:00 | 05-07-2025 17:00:00 | k sachindra | 9425805295 | ok, through sub ld
11 | 2024-11-20 16:41 | MR2411/0432 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 30-06-2025 09:00:00 | 05-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Continuous
12 | 2024-11-20 16:43 | MR2411/0433 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 30-06-2025 09:00:00 | 05-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Continuous
13 | 2025-06-30 13:59 | MR2506/0611 | Continuous | 132KV_132 KV KATNI SLEEMNABAD LINE | 400KV_KATNI4 | NON-OCCM-MP | Work for OPG stringigng work | 01-07-2025 08:00:00 | 05-07-2025 18:00:00 | PANKAJ YADAV | 9406713326 | ensure availability of telemetry before permit
14 | 2025-07-03 13:32 | MR2507/0049 | Daily | 132KV_132 KV KATNI KYMORE CKT 1 ST | 400KV_KATNI4 | NON-OCCM-MP | for line maintenance work. | 04-07-2025 09:00:00 | 05-07-2025 18:00:00 | PANKAJ YADAV | 9406713326 | ensure availability of telemetry before permit
15 | 2025-07-03 13:41 | MR2507/0051 | Daily | 132KV_132 kv katni sleemnabad line | 400KV_KATNI4 | NON-OCCM-MP | for line maintenance work. | 04-07-2025 09:00:00 | 05-07-2025 18:00:00 | pankaj yadav | 9406713326 | ensure availability of telemetry before permit
16 | 2025-07-02 12:50 | MR2507/0035 | Daily | 132KV_132 KV KATNI KYMORE CKT 1 | 400KV_KATNI4 | NON-OCCM-MP | Work for OPG stringigng work | 03-07-2025 08:00:00 | 05-07-2025 18:00:00 | pankaj yadav | 9406713326 | ensure availability of telemetry before permit
17 | 2025-07-01 15:42 | MR2507/0010 | Continuous | 132KV_132 KV Khurai-Sagar | 132KV_KHURAI | NON-OCCM-MP | Modification/Shifting of 132 KV Khurai-Sagar | 02-07-2025 07:00:00 | 12-07-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | Continuous
18 | 2025-06-30 16:20 | MR2506/0638 | Daily | 220KV_220 KV BHOPAL-MUGALIYACHAP | 220KV_MUGALIYACHAAP | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
19 | 2025-07-04 15:40 | MR2507/0065 |  | 50MVA_132/33KV_TAL_Xmer | 132KV_NAGOD | NON-OCCM-MP | 132 KV 50 MVA TAL XMER MAGNETISING CURRENT TEST | 05-07-2025 10:00:00 | 05-07-2025 13:00:00 | RAVI PRAKASH PANDEY | 9425805296 | ok
20 | 2025-06-26 14:57 | MR2506/0557 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | OCCM-WR | Hotline work For Installation OPGW by replace E/W | 26-06-2025 08:00:00 | 10-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
21 | 2025-06-26 15:04 | MR2506/0558 | Daily | 132KV_132 kV Nepa - Pipalpani | 220KV_NEPANAGAR | NON-OCCM-MP | Hotline work Installation OPGW Replaced by E/W | 26-06-2025 08:00:00 | 10-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
22 | 2025-07-04 15:25 | MR2507/0064 |  | 132KV_Shutdown (H/T) of 132 kv Rewa - J P Baghwar DCSS line | 220KV_REWA | NON-OCCM-WR | replacement of flashover disc at Loc. No. 56, 57 | 05-07-2025 09:00:00 | 05-07-2025 15:30:00 | Mr. Ajay Kumar Chaurasia | 9425805081 | ok
23 | 2025-06-30 14:20 | MR2506/0616 | Daily | 132KV_132kv sagar-sagar ic ic 1st ckt. | 400KV_SAGAR | NON-OCCM-MP | OPGW stringing work ( hot Line permit) | 01-07-2025 07:00:00 | 08-07-2025 19:00:00 | Er. Pankaj Yadav. | 9406713326 | ok, line to be in service
24 | 2025-06-30 14:13 | MR2506/0612 | Daily | 132KV_132kv Sagar-sagar ic 3rd ckt. | 400KV_SAGAR | NON-OCCM-MP | opgw stringing Work (hot line permit) | 01-07-2025 07:00:00 | 08-07-2025 19:00:00 | Er. pankaj yadav | 9406713326 | ok, line to be in service
25 | 2025-05-03 11:32 | MR2505/0054 | Continuous | 220KV_100 MVA X-mer Make CGL | 220KV_SARNI | NON-OCCM-MP | X-mer Augmentation work by 160 MVA X-mer AREVA | 05-05-2025 10:00:00 | 10-07-2025 17:00:00 | Er K.K. Choure | 9425801357 | Continuous
26 | 2025-07-02 17:46 | MR2507/0043 |  | 220KV_220 kv Satna (MPPTCL) â¿¿ Kotar line | 220KV_SATNA | NON-OCCM-MP | Line maintenance work | 05-07-2025 09:00:00 | 05-07-2025 18:00:00 | Mr. M.M.Baig | 9425805067 | ok
27 | 2025-06-28 14:36 | MR2506/0586 |  | 220KV_220kv Sidhi-Rums(PGCIL )circuit -I | 220KV_SIDHI | NON-OCCM-MP | Jumper come tightening work | 05-07-2025 11:00:00 | 05-07-2025 17:00:00 | G.L sahu | 9425805102 | ok
28 | 2025-07-04 14:57 | MR2507/0063 |  | 132KV_132KV Sidhi-Deosar ckt-I | 220KV_SIDHI | NON-OCCM-MP | FLASH OVER DISC REPLACEMENT | 05-07-2025 11:00:00 | 05-07-2025 17:00:00 | G.L SAHU | 9425805102 | ok, o&m, shall be informed
29 | 2025-07-04 15:48 | MR2507/0066 |  | 132KV_132 kV Tikamgarh-Badamalhera line | 220KV_TIKAMGARH | NON-OCCM-MP | F/o disc replacement in varies location | 05-07-2025 10:00:00 | 05-07-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
30 |  | 253284 | Daily | 400KV-CHHEGAON-RAJGARH-1 | 400 | MP_SLDC | FOR BAY MAINTENANCE & TESTING WORK | 05-Jul-2025 | 10:00 | 05-Jul-2025 | 18:00 | real time
31 |  | 254089 | Daily | 220KV-REWA-SINDHI-MP-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK | 05-Jul-2025 | 11:00 | 05-Jul-2025 | 16:59 | ok
32 |  | 253702 | Daily | 132KV-DHARNI-NEPANAGAR-1 | 132 | MP_SLDC | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 05-Jul-2025 | 08:00 | 05-Jul-2025 | 17:59 | ok