## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-11 | APPROVED OUTAGE LIST FOR DTD.11.09.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-25 15:12 | MR2508/0327 | Daily | 220KV_220KV Anuppur Kotmikala ckt-I | 220KV_ANUPPUR | NON-OCCM-MP | Low Ground clearance maintenance work at loc. 371- | 09-09-2025 08:00:00 | 17-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
2 | 2025-09-10 13:45 | MR2509/0240 |  | 220KV_160MVA X-mer No-3rd BBL | 400KV_ASHTA4 | NON-OCCM-MP | Post monsoon maintenance and measurement of Tan De | 11-09-2025 09:00:00 | 11-09-2025 18:00:00 | Jitendra Lohana | 9425804978 | OK THROUGH SUB LD
3 | 2025-09-10 13:39 | MR2509/0239 |  | 132KV_40 MVA BHEL X-mer | 132KV_BATIYAGARH | NON-OCCM-MP | Post monsoon maintenance | 11-09-2025 11:00:00 | 11-09-2025 17:00:00 | B K Sahu | 942581433 | OK O&M TO BE INTIMATED
4 | 2025-09-10 14:34 | MR2509/0244 |  | 132KV_132 kV Bhopal-Bairagarh Tap to Lalghati line | 220KV_BHOPAL | NON-OCCM-MP | Emergency Tree cutting work | 11-09-2025 10:00:00 | 11-09-2025 17:00:00 | Ankit Mehroliya | 9425804506 | SUB LD
5 | 2025-09-06 15:08 | MR2509/0153 | Daily | 132KV_132 kV Shahdol-Birsingpur Circuit I | 220KV_BIRSINGHPUR | NON-OCCM-MP | Replacement of damaged OPGW | 07-09-2025 09:00:00 | 13-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
6 | 2025-09-10 15:43 | MR2509/0251 |  | 220KV_220kV Chhatarpur-Ajaygarh (TBCB) Ckt. 1st Line | 220KV_CHATARPUR | NON-OCCM-MP | Slip VD Removal & other Line maintenance work | 11-09-2025 10:00:00 | 11-09-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | OK
7 | 2025-09-10 12:36 | MR2509/0231 |  | 220KV_220 kV Khandwa (PGCIL) - Omkareshwar | 400KV_CHHEGAON4 | OCCM-WR | For LIne Mainenance Work. | 11-09-2025 08:00:00 | 11-09-2025 18:00:00 | C.H.Namdev | 9425802377 | OK
8 | 2025-09-06 15:08 | MR2509/0154 | Daily | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | Replacement of damaged OPGW | 07-09-2025 09:00:00 | 13-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
9 | 2025-09-10 09:30 | MR2509/0223 | Continuous | 132KV_132KV BUS COUPLER | 132KV_GUDGAON | NON-OCCM-MP | For replacement of old C&R Panel | 10-09-2025 10:00:00 | 11-09-2025 18:00:00 | Er.Sanjay kumar Pawar | 942580293 | SUB LD
10 | 2025-09-07 13:02 | MR2509/0161 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-2 | 220KV_INDORE NORTH | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK THROUGH SUB LD, LINE TO BE IN SERVICE, PRIOR TO SD DATA SHOULD BE REROUTED
11 | 2025-09-07 12:51 | MR2509/0159 | Daily | 132KV_132KV North Zone- Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
12 | 2025-09-07 12:45 | MR2509/0158 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK THROUGH SUB LD, LINE TO BE IN SERVICE, PRIOR TO SD DATA SHOULD BE REROUTED
13 | 2025-09-10 10:58 | MR2509/0224 |  | 220KV_220 KV JBP - SUKHA NO. 01 | 220KV_JABALPUR | NON-OCCM-MP | R , Y, & B CVT REPLACEMENT WORK. | 11-09-2025 09:00:00 | 11-09-2025 18:00:00 | D.N. PODDAR | 9425805034 | OK
14 | 2025-09-10 14:32 | MR2509/0242 |  | 220KV_160 mva -II | 220KV_JAORA | NON-OCCM-MP | POSTMANSOON MAINTANCE WORK | 11-09-2025 09:00:00 | 11-09-2025 18:00:00 | RAKESH BADGOTYA | 7587951143 | OK THROUGH SUB LD
15 | 2025-06-30 16:18 | MR2506/0637 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 08-09-2025 09:00:00 | 13-09-2025 18:00:00 | PANKAJ YADAV | 9406713326 | DEFERRED, WRPC CONSENT REQUIRED
16 | 2025-06-30 15:35 | MR2506/0627 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 08-09-2025 09:00:00 | 13-09-2025 08:00:00 | PANKAJ YADAV | 9406713326 | DEFERRED, WRPC CONSENT REQUIRED
17 | 2025-09-10 13:20 | MR2509/0237 |  | 132KV_132 KV Khurai-Sagar Ckt | 132KV_KHURAI | NON-OCCM-MP | for F/O disc insulator replacement & other line | 11-09-2025 09:00:00 | 11-09-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | OK
18 | 2025-09-10 15:19 | MR2509/0247 |  | 400KV_400/132/33 KV 100 MVA Transformer no-03 CGL | 400KV_KIRNAPUR | NON-OCCM-MP | For Post monsoon maintenance of transformer and ba | 11-09-2025 09:00:00 | 11-09-2025 17:00:00 | D. S. Walkey | 9425804578 | OK, 220 KV SEONI PG - SEONI MP CKT DEFERRED FROM SITE
19 | 2025-09-10 15:12 | MR2509/0246 |  | 132KV_63MVA BBL/50MVA BHEL | 220KV_KOTAR | OCCM-MP | For 33KV Main Bus Maintenance | 11-09-2025 11:00:00 | 11-09-2025 14:00:00 | Arun Kumar kol | 8319677721 | OK ONLY IF O&M CONSENTED
20 | 2025-09-10 11:54 | MR2509/0226 |  | 220KV_220/132KV 160MVA XMer BBL | 220KV_MAHALGAON | NON-OCCM-MP | Post Monsson Maintenance and attending Indication | 11-09-2025 09:00:00 | 11-09-2025 17:00:00 | P Datey | 9425805110 | OK THROUGH SUB LD
21 | 2025-09-10 16:16 | MR2509/0253 |  | 132KV_132KV Jaora mandsaur line | 132KV_MANDSOUR | NON-OCCM-MP | For Maintenance work | 11-09-2025 10:00:00 | 11-09-2025 18:00:00 | Gaurav Goyal | 9425805120 | SUB LD
22 | 2025-09-10 13:31 | MR2509/0238 |  | 132KV_63 MVA TRANSFORMER | 220KV_NAGDA | NON-OCCM-MP | POST MANSOON MAINTENANCE WORK | 11-09-2025 10:15:00 | 11-09-2025 17:00:00 | VIKRAM DEHARIYA | 7587951150 | SUB LD
23 | 2025-09-10 15:21 | MR2509/0248 |  | 220KV_220KV Nipaniya-Mandsaur-1 | 220KV_NIPANIYA | NON-OCCM-MP | DPR-II, Relay Installation and testing Work 220KV | 11-09-2025 10:00:00 | 11-09-2025 18:00:00 | SUNIL PAWAR | 9425804939 | OK THROUGH SUB LD
24 | 2025-09-07 12:39 | MR2509/0157 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line. | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
25 | 2025-09-07 12:57 | MR2509/0160 | Daily | 132KV_132KV Niranjanpur - Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
26 | 2025-09-02 18:36 | MR2509/0064 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line.&132KV Niranjanpur - Jaitpura Line &132KV North Zone- Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
27 | 2025-09-10 11:30 | MR2509/0225 |  | 132KV_132 KV Pipariya-Bareli I | 220KV_PIPARIYA | NON-OCCM-MP | Flash over disc replacement work | 11-09-2025 10:00:00 | 11-09-2025 17:00:00 | Ashutosh Rai | 9425806902 | SUB LD
28 | 2025-09-10 14:32 | MR2509/0243 |  | 220KV_220 kv Rajgarh-Nalkheda Ckt-2 | 220KV_RAJGARH (BIAORA) | NON-OCCM-MP | Post mansoon maint.work. | 11-09-2025 10:00:00 | 11-09-2025 17:00:00 | Neelesh Bastri | 9425804342 | OK THROUGH SUB LD
29 | 2025-09-10 15:46 | MR2509/0252 |  | 132KV_132kV Rajmilan - Dongrital Line | 132KV_RAJMILAN | NON-OCCM-MP | Disc F/o Change | 11-09-2025 10:00:00 | 11-09-2025 17:00:00 | G.L Sahu | 9425805102 | OK
30 | 2025-09-10 13:06 | MR2509/0236 |  | 220KV_220 KV Bus-Coupler | 220KV_RATLAM | NON-OCCM-MP | for maintanance of Auxillary bus isolator | 11-09-2025 09:00:00 | 11-09-2025 18:00:00 | NIKHIL DUNGE | 9425801487 | OK
31 | 2025-09-10 13:02 | MR2509/0235 |  | 220KV_160 MVA X-MER (BHEL)-III rd | 220KV_RATLAM | NON-OCCM-MP | for Post mansoon Maintenance & testing work | 11-09-2025 09:00:00 | 11-09-2025 18:00:00 | NIKHIL DUNGE | 9425801487 | OK THROUGH SUB LD
32 | 2025-09-10 14:04 | MR2509/0241 |  | 220KV_Shutdown (H/T) of 220 kv Rewa-Sidhi DCDS line | 220KV_REWA | OCCM-WR | flashover disc insulator string replacement | 11-09-2025 09:00:00 | 11-09-2025 17:00:00 | Mr. Ajay Kumar Chaurasia | 9425805081 | OK THROUGH SUB LD
33 | 2025-09-10 11:59 | MR2509/0230 |  | 400KV_400 KV PITHAMPURA LINE 4 | 400KV_SINGHAJI-TPS-II | NON-OCCM-MP | PMU INSTALLATION WORK BY MPPTCL | 11-09-2025 10:00:00 | 11-09-2025 18:00:00 | MR.SHARAD TIWARI | 7987469237 | OK THROUGH SUB LD
34 | 2025-09-10 15:26 | MR2509/0249 |  | 132KV_132 KV Udaipura-Tendukheda line Ckt-I | 132KV_TENDUKHEDA | NON-OCCM-MP | Flashover disc replacement work at loc.No.45/R-01 | 11-09-2025 10:00:00 | 11-09-2025 18:00:00 | Ashish Kumar | 9425805935 | OK THROUGH SUB LD
35 | 2025-09-10 14:47 | MR2509/0245 |  | 132KV_132kv tikamgarh -prithvipur line | 220KV_TIKAMGARH | NON-OCCM-MP | Bay maintenance | 11-09-2025 10:00:00 | 11-09-2025 17:00:00 | Pushpendra Kumar soni | 9425806398 | OK
36 | 2025-09-10 12:53 | MR2509/0232 |  | 132KV_40 MVA BBL-make-Make Transformer | 132KV_TIKAMGARH1 | NON-OCCM-MP | Testing | 11-09-2025 10:00:00 | 11-09-2025 17:00:00 | Pushpendra Kumar soni | 9425806398 | OK
37 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | CONTI NUE
38 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | RAJESH TIWARI | 7898239595 | CONTINUE
39 |  |  |  | 220KV-INDORE-UJJAIN-1 |  |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 11-Sep-2025 | 08:00 | 11-Sep-2025 | 18:00 | OK THROUGH SUB LD
40 |  |  |  | 400KV-BHOPAL-MP-BHOPAL-BDTCL-2 |  |  | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 11-Sep-2025 | 09:00 | 11-Sep-2025 | 18:00 | OK THROUGH SUB LD
41 |  |  |  | 220KV-SEONI-MP-SEONI-PG-1 |  |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 11-Sep-2025 | 09:00 | 11-Sep-2025 | 18:00 | DEFERRED FROM SITE
42 |  |  |  | 220KV-KHANDWA-OMKARESHWAR-1 |  |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 11-Sep-2025 | 08:00 | 11-Sep-2025 | 18:00 | OK THROUGH SUB LD
43 |  |  |  | 220KV-ANNUPUR-KOTMIKALA-1 |  |  | For Re-sagging work due to Low Ground clearance at loc. 371-379 & 464- 475 | 11-Sep-2025 | 08:00 | 11-Sep-2025 | 17:59 | OK
44 |  |  |  | 400KV-INDORE-UJJAIN-1 |  |  | FOR BAY MAINTENANCE & TESTING WORK AT UJJAIN SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 11-Sep-2025 | 09:00 | 11-Sep-2025 | 18:00 | OK THROUGH SUB LD
45 |  |  |  | 220KV-HOSHANGABAD-ITARSI-1 |  |  | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 11-Sep-2025 | 09:00 | 11-Sep-2025 | 18:00 | OK THROUGH SUB LD
46 |  |  |  | 220KV-GWALIOR-GWALIOR-II-2 |  |  | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 11-Sep-2025 | 09:00 | 11-Sep-2025 | 17:00 | OK THROUGH SUB LD
47 |  |  |  | 400KV/220KV JABALPUR-ICT-1 |  |  | FOR REPLACEMENT OF CTS | 10-Sep-2025 | 09:00 | 11-Sep-2025 | 17:00 | CONTINUE
48 |  |  |  | 220KV-INDORE-INDORE NORTH ZONE-1 |  |  | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO | 11-Sep-2025 | 07:00 | 11-Sep-2025 | 23:59 | OK LINE TO BE IN SERVICE
49 |  |  |  | 220KV-INDORE-INDORE NORTH ZONE-2 |  |  | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO | 11-Sep-2025 | 07:00 | 11-Sep-2025 | 19:59 | OK LINE TO BE IN SERVICE
S/I, SLDC MPPTCL JABALPUR