## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-11
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Status | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-03 11:54 | MR2510/0055 | Daily | 220KV_220 kV Adampur-Hoshangabd line | 220KV_ADAMPUR | NON-OCCM-MP | Defective disc replacement work | 04-10-2025 09:00:00 | 14-10-2025 17:00:00 | Waiting | Ankit Mehroliya | 9425804506 | OK THROUGH SUB LD
2 | 2025-10-10 14:35 | MR2510/0292 |  | 132KV_40 MVA X-MER EMCO | 132KV_ARON | NON-OCCM-MP | 132KV CB SF6 GAS LEAKAGE DETECTION | 11-10-2025 12:00:00 | 11-10-2025 15:00:00 | Waiting | RAKESH SUMAN | 7587951093 | SUB LD
3 | 2025-10-10 12:43 | MR2510/0281 |  | 132KV_132 KV Main Bus | 132KV_BALAGHAT | NON-OCCM-MP | hot point attending work & 2 no. isolator repairi | 11-10-2025 12:00:00 | 11-10-2025 17:00:00 | Waiting | Swati Bisen | 9425801737 | OK , 132 KV BALAGHAT - KIRNAPUR CKT-2 & 132KV KIRNAPUR - WARASEONI CKT BYPASS THROUGH AUXILIARY BUS AT 132KV S/S BALAGHAT. PROTECTION COORDINATION TO BE CONFIRMED BY TESTING
4 | 2025-10-10 12:36 | MR2510/0278 |  | 220KV_160 MVA AREVA_X-mer-1st | 220KV_BETUL | NON-OCCM-MP | for post monsoon maintenance work. | 11-10-2025 10:00:00 | 11-10-2025 17:00:00 | Waiting | Vishal Kumar Malviya | 9425804955 | OK THROUGH SUB LD
5 | 2025-10-10 12:39 | MR2510/0280 |  | 132KV_20 MVA GEC_X-mer | 220KV_BETUL | NON-OCCM-MP | Safety purpose of new 63MVA TAL X-mer erection wor | 11-10-2025 10:00:00 | 11-10-2025 17:00:00 | Waiting | Vishal Kumar malviya | 9425804955 | SUB LD
6 | 2025-10-10 14:30 | MR2510/0290 |  | 132KV_132 KV Bina-Ashoknagar Ckt | 220KV_BINA | NON-OCCM-MP | Shutdown for line maintenance work | 11-10-2025 10:00:00 | 11-10-2025 18:00:00 | Waiting | Sanjay Singh Thakur | 9425806936 | SUB LD
7 | 2025-10-10 15:44 | MR2510/0300 |  | 132KV_20 MVA NGEF X-MER | 132KV_CHANDERI | NON-OCCM-MP | Post-monsoon mintenance work | 11-10-2025 11:00:00 | 11-10-2025 17:00:00 | Waiting | Lalit singh | 9425806845 | SUB LD
8 | 2025-10-10 14:20 | MR2510/0288 |  | 132KV_40MVA X-MER No. III BBL | 132KV_CHHINDWARA1 | NON-OCCM-MP | Post Mansoon Maint. Work | 11-10-2025 09:00:00 | 11-10-2025 14:00:00 | Waiting | Er. Anju Dhurve | 9425804752 | OK O&M TO BE INTIMATED
9 | 2025-09-18 17:16 | MR2509/0453 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 06-10-2025 09:00:00 | 11-10-2025 18:00:00 | Waiting | SHRI M. M. BAIG | 9425805067 | DEFERRED
10 | 2025-10-10 15:20 | MR2510/0298 |  | 220KV_160MVA 220/132KV BHEL X-MER-1 | 220KV_DAMOH | NON-OCCM-MP | Post Monsoon Maintenance & Testing work | 11-10-2025 09:00:00 | 11-10-2025 18:00:00 | Waiting | M.K.Choubey | 9425801424 | OK
11 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | Waiting | G.L Sahu | 9425805102 | DEFERRED, DATA CONFIRMATION SHALL BE DONE BY COMMUNICATION
12 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | Waiting | G.L Sahu | 9425805102 | DEFERRED, DATA CONFIRMATION SHALL BE DONE BY COMMUNICATION
13 | 2025-10-10 14:56 | MR2510/0294 |  | 132KV_132KV ANUPPUR-DONGRITAL CKT | 132KV_DONGRITAL | NON-OCCM-MP | DISC REPLACEMENT WORK | 11-10-2025 09:00:00 | 11-10-2025 17:00:00 | Waiting | G.L SAHU | 9425805102 | OK
14 | 2025-10-10 13:20 | MR2510/0284 |  | 220KV_220KV ITARSI-HANDIA CKT-I | 220KV_HANDIYA | NON-OCCM-MP | F/O DISC REPLACEMENT WORK | 11-10-2025 09:00:00 | 11-10-2025 13:00:00 | Waiting | R.N.PARTE | 9425804701 | OK THROUGH SUB LD
15 | 2025-10-10 13:27 | MR2510/0285 |  | 220KV_220KV ITARSI-HANDIA CKT-II | 220KV_HANDIYA | NON-OCCM-MP | F/O DISC REPLACEMENT WORK. | 11-10-2025 14:00:00 | 11-10-2025 17:00:00 | Waiting | R.N.PARTE | 9425804701 | OK THROUGH SUB LD AFTER REVIVAL OF CKT-1
16 | 2025-10-10 11:49 | MR2510/0277 | Daily | 220KV_220 KV Hoshangabad-Adampur | 220KV_HOSHANGABAD | NON-OCCM-MP | Resagging work b/w loc.no. 78-94 | 11-10-2025 09:00:00 | 14-10-2025 17:00:00 | Waiting | Ashutosh Rai | 9425806902 | AS AN OPPORTUNITY SD
17 | 2025-10-10 14:29 | MR2510/0289 |  | 132KV_NORTHZONE - CHAMBLE CKT-1 LINE | 220KV_INDORE-NZ | NON-OCCM-MP | DAMAGE CONDUCTOR REPLACEMENT WORK. | 11-10-2025 06:00:00 | 11-10-2025 10:00:00 | Waiting | A.R. KANEL | 9425805217 | SUB LD
18 | 2025-10-10 14:33 | MR2510/0291 |  | 220KV_220 kV Jabalpur Amarkatak | 220KV_JABALPUR | NON-OCCM-MP | Flash over disc change at loc no 321 T Ph | 11-10-2025 11:00:00 | 11-10-2025 18:00:00 | Waiting | Jitendra Tiwari | 9425805298 | OK
19 | 2025-10-06 14:08 | MR2510/0135 |  | 132KV_132/33KV 40 MVA IMP-2 X-MER | 132KV_KARAPGAON | NON-OCCM-MP | S/D For post monsoon maintenance and testing work | 11-10-2025 11:00:00 | 11-10-2025 17:00:00 | Waiting | Ranjeet kumar kori | 9425806701 | SUB LD
20 | 2025-10-10 15:09 | MR2510/0296 | Continuous | 132KV_132 kv katni panagar line | 132KV_KATNI | NON-OCCM-MP | For replacement OPG wire | 10-10-2025 15:00:00 | 11-10-2025 15:00:00 | Waiting | panakaj yadav | 9406713326 | DATA CONFIRMATION SHALL BE DONE BY COMMUNICATION
21 | 2025-10-10 15:12 | MR2510/0297 | Continuous | 132KV_132 kv katni sleemnabad line | 400KV_KATNI4 | NON-OCCM-MP | For replacement OPG wire | 10-10-2025 10:00:00 | 11-10-2025 15:00:00 | Waiting | pankaj yadav | 9406713326 | DATA CONFIRMATION SHALL BE DONE BY COMMUNICATION
22 | 2025-09-18 12:55 | MR2509/0410 | Continuous | 400KV_400KV DAMOH - KATNI LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 06-10-2025 09:00:00 | 11-10-2025 18:00:00 | Waiting | SHRI M.M. BAIG | 9425805067 | DEFERRED
23 | 2025-10-10 11:38 | MR2510/0276 |  | 160MVA_220/132KV_BHEL_X'mer_2 | 220KV_MAHALGAON | NON-OCCM-MP | Post Monsoon Maint. and Testing Work | 11-10-2025 10:00:00 | 11-10-2025 17:00:00 | Waiting | P Datey | 9425805110 | OK THROUGH SUB LD
24 | 2025-10-09 13:42 | MR2510/0251 |  | 132KV_132KV Biaora Maqsudangarh Ckt. | 132KV_MAKSUDANGARH | NON-OCCM-MP | DF/O replacement & line maint. work | 11-10-2025 10:00:00 | 11-10-2025 17:00:00 | Waiting | Akhilesh Singh | 8586865656 | SUB LD
25 | 2025-10-05 10:37 | MR2510/0101 | Daily | 132KV_132KV Neemuch Manasa Line | 132KV_MANASA | NON-OCCM-MP | Re sagging and line maintanence work | 06-10-2025 08:00:00 | 12-10-2025 18:00:00 | Waiting | Gaurav goyal | 9425805120 | SUB LD
26 | 2025-10-10 11:29 | MR2510/0275 |  | 132KV_132 KV Narsinghpur -Gadarwara feeder | 132KV_NARSINGHPUR1 | NON-OCCM-MP | B Phase line Isolator jaw replacement work. | 11-10-2025 12:00:00 | 11-10-2025 15:00:00 | Waiting | Rajesh Chaturvedi | 9425805203 | OK
27 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | Waiting | G.L Sahu | 9425805102 | DEFERRED, DATA CONFIRMATION SHALL BE DONE BY COMMUNICATION
28 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | Waiting | G.L Sahu | 9425805102 | DEFERRED, DATA CONFIRMATION SHALL BE DONE BY COMMUNICATION
29 | 2025-10-10 13:27 | MR2510/0286 |  | 50MVA_132/33KV_BHEL_X'mer_2 | 132KV_REWA-II (SAGRA) | NON-OCCM-MP | POST MONSOON MAINTENANCE AND TESTING WORK | 11-10-2025 10:00:00 | 11-10-2025 17:00:00 | Waiting | ER. KANISHK SINGH | 9425804656 | OK O&M TO BE INTIMATED
30 | 2025-10-10 16:02 | MR2510/0301 |  | 132KV_132kv Sheopur Beerpur TBCB Ckt | 132KV_SHEOPUR KALAN | NON-OCCM-MP | LINE MAINTENANCE WORK | 11-10-2025 09:30:00 | 11-10-2025 18:30:00 | Waiting | SURAJ PAWAR | 9425814079 | SUB LD
31 | 2025-10-10 15:05 | MR2510/0295 |  | 220KV_160 MVA XMER 1st EMCO | 220KV_SHIVPURI | NON-OCCM-MP | for Post monsoon maintenance and testing work | 11-10-2025 10:00:00 | 11-10-2025 17:00:00 | Waiting | ROHIT YADAV | 9425804921 | OK THROUGH SUB LD
32 | 2025-10-10 12:48 | MR2510/0283 |  | 132KV_132 KV Sidhi Mauganj CKT-1 | 220KV_SIDHI | NON-OCCM-MP | 132 KV Aux. bus to isolator jumpering work | 11-10-2025 10:00:00 | 11-10-2025 15:00:00 | Waiting | JAGAT NARAYAN SINGH | 9425802388 | OK
33 | 2025-10-10 12:44 | MR2510/0282 |  | 132KV_132 KV Aux. bus at 220KV S/s Sidhi | 220KV_SIDHI | NON-OCCM-MP | 132 KV Aux bus to isolator jumpering work | 11-10-2025 10:00:00 | 11-10-2025 15:00:00 | Waiting | JAGAT NARAYAN SINGH | 9425802388 | OK
34 | 2025-10-10 13:34 | MR2510/0287 |  | 400KV_400/220 KV ICT-I for PMU commissioning work | 400KV_SINGHAJI TPS | NON-OCCM-MP | PMU commissioning work for 315 MVA ICT-I | 11-10-2025 10:00:00 | 11-10-2025 18:00:00 | Waiting | Deepak Sharma | 8005696855 | OK, SUB LD TO BE INTIMATED
35 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | Accepted | B.C JOSHI | 7587951137 | OK, FTC TO BE SUBMITTED
36 |  | 272130 |  | 400KV-ITARSI-INDORE-MP-2 | POWERGRID_WR2 | WR | for Testing of Reactor and Taking into service after Internal inspection work | 09:00 | 17:30 |  |  |  | OK THROUGH SUB LD
37 |  | 265317 |  | 220KV-BHIND-MORENA-2 | POWERGRID_WR2 | WR | LINE AMP WORK (CRM Test of Isolator,CT Tan delta,LA IR and other checks) | 09:00 | 18:00 |  |  |  | OK
38 |  | 265930 |  | 400KV-BADNAWAR-RAJGARH-2 | MP_SLDC | WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 08:00 | 18:00 |  |  |  | OK THROUGH SUB LD
39 |  | 265952 |  | 220KV-MORENA-MORENA-MP-1 | MP_SLDC | WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 09:00 | 17:00 |  |  |  | OK THROUGH SUB LD
40 |  | 270534 |  | 132KV-PENCH-MP-KANHAN-1 | MP_SLDC | WR | s/s required for faulty CVT replacement and overhauling of Ckt breaker | 09:00 | 17:59 |  |  |  | OK
41 |  | 266834 |  | 132KV-VSTPS-WAIDHAN-1 | NTPC_VSTPS | WR | Annual Bay Maitenanace & Testing/ CRP replacement | 08:08 | 18:00 |  |  |  | OK, CKT 2 TO BE IN SERVICE