## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-12 |  |  | APPROVED OUTAGE LIST FOR DTD 12.07.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-30 16:24 | MR2506/0639 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA | 400KV_ASHTA4 | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
2 | 2025-06-30 16:26 | MR2506/0640 | Daily | 220KV_220 KV BAIRAGARH-ASHTA | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-06-30 16:13 | MR2506/0635 | Daily | 220KV_220 BHOPAL-BAIRAGARH CKT-3 | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
4 | 2025-07-11 11:23 | MR2507/0147 |  | 132KV_132kV Balaghat-Baihar Line | 132KV_BALAGHAT | NON-OCCM-MP | FO Disc & PID Defective Disc Replacement Work | 12-07-2025 10:00:00 | 12-07-2025 18:00:00 | Shridhar Kumar Bhaladhare | 9425807264 | ok
5 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
6 | 2025-06-23 17:09 | MR2506/0482 | Daily | 220KV_220 KV South Zone - Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
7 | 2025-07-11 14:26 | MR2507/0151 |  | 400KV_400KV Indore - ISP-II line | 400KV_INDORE4 | NON-OCCM-MP | For jumpering of new 400KV isolator for 50MVAR rea | 12-07-2025 09:00:00 | 12-07-2025 18:00:00 | Sandeep Umredkar | 9425820035 | real time as per the ISP generation, at max 5-6 ISP machines can be allowed during the s/d period
8 | 2025-06-23 17:04 | MR2506/0481 | Daily | 220KV_220KV Indore (400KV) - Mangliya line | 400KV_INDORE4 | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
9 | 2024-11-20 16:45 | MR2411/0434 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 07-07-2025 09:00:00 | 12-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Continuous
10 | 2024-11-20 16:47 | MR2411/0435 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 07-07-2025 09:00:00 | 12-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Continuous
11 | 2025-07-01 15:42 | MR2507/0010 | Continuous | 132KV_132 KV Khurai-Sagar | 132KV_KHURAI | NON-OCCM-MP | Modification/Shifting of 132 KV Khurai-Sagar | 02-07-2025 07:00:00 | 12-07-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | Continuous
12 | 2025-06-30 16:20 | MR2506/0638 | Daily | 220KV_220 KV BHOPAL-MUGALIYACHAP | 220KV_MUGALIYACHAAP | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
13 | 2025-07-05 17:07 | MR2507/0079 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Insatallation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
14 | 2025-07-05 16:59 | MR2507/0078 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) LIne | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
15 | 2025-07-11 12:27 | MR2507/0148 |  | 220KV_220KV Neemuch- Ratangarh-I | 220KV_RATANGARH | NON-OCCM-WR | DTPC carrier protection (FOTE) cable connecting | 12-07-2025 11:00:00 | 12-07-2025 16:00:00 | S.H. Mansuri | 7587951068 | please confirm whether any telemetry data would be out during the s/d period, if yes then arrange the alternate path of telemetry before permit
16 | 2025-07-11 14:17 | MR2507/0150 |  | 132KV_132 kV Tikamgarh - Prithvipur line | 220KV_TIKAMGARH | NON-OCCM-MP | F/o disc replacement and other Line maint. work | 12-07-2025 10:00:00 | 12-07-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
17 | 2025-07-11 14:17 |  |  | 220KV-INDORE-INDORE-MP-1 |  | OCCM-WR | LINE MAINTENANCE WORK | 12-07-2025 09:00:00 | 12-07-2025 18:00:00 |  |  | real time
S/I, SLDC MPPTCL JABALPUR