## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-17 |  |  | APPROVED OUTAGE LIST FOR DTD.17.06.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-30 16:24 | MR2506/0639 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA | 400KV_ASHTA4 | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
2 | 2025-06-30 16:26 | MR2506/0640 | Daily | 220KV_220 KV BAIRAGARH-ASHTA | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-06-30 16:13 | MR2506/0635 | Daily | 220KV_220 BHOPAL-BAIRAGARH CKT-3 | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
4 | 2025-07-16 12:24 | MR2507/0215 |  | 220KV_220 KV Bairagarh Bhopal ckt no. 1 | 220KV_BAIRAGARH | NON-OCCM-MP | For replacement of damage conductor of B phase CT. | 17-07-2025 09:30:00 | 17-07-2025 18:00:00 | Shri Ambarish shripad joshi | 7587951085 | ok, through sub ld
5 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
6 | 2025-07-14 18:13 | MR2507/0185 | Continuous | 132KV_20MVA_GEC_X-mer | 220KV_BETUL | NON-OCCM-MP | shifting from existing foundation to wooden sleepe | 15-07-2025 10:00:00 | 18-07-2025 17:00:00 | Vishal Kumar Malviya | 9425804955 | sub ld
7 | 2025-07-16 11:48 | MR2507/0212 |  | 220KV_220 KV PGCIL ITARSI CK-2 | 220KV_BUDHNI | NON-OCCM-MP | Load Transfer From main bus to TBC continued | 17-07-2025 11:00:00 | 17-07-2025 16:00:00 | AE SPS TOMAR | 9425801629 | ok, line to be in service through TBC
8 | 2025-07-16 16:18 | MR2507/0230 |  | 220KV_220 kV Khandwa (PGCIL)-Chhegaon Ckt 1st | 400KV_CHHEGAON4 | OCCM-MP | For Jumper Tightening & Other Line Maintenance wor | 17-07-2025 10:00:00 | 17-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, through sub ld
9 | 2025-07-16 15:10 | MR2507/0227 |  | 220KV_220KV DEWAS-ASHTA LINE | 220KV_DEWAS | NON-OCCM-MP | FOR RELAY TESTING | 17-07-2025 10:30:00 | 17-07-2025 16:30:00 | ARVIND KUMAR JOSHI | 9425801305 | ok, through sub ld
10 | 2025-07-12 13:24 | MR2507/0165 | Daily | 400KV_125 MVAr SHUNT REACTOR | 400KV_INDIRASAGAR | NON-OCCM-WR | ANNUAL MAINTENANCE | 15-07-2025 10:00:00 | 17-07-2025 17:00:00 | SHRI VINAI MISHRA | 9575074321 | Deffered, due to high voltage period
11 | 2025-07-16 16:07 | MR2507/0229 |  | 400KV_400KV ISP-II FEEDER | 400KV_INDORE4 | NON-OCCM-MP | NIFPS TESTING WORK OF 50MVAR REACTOR | 17-07-2025 11:00:00 | 17-07-2025 14:00:00 | ATUL PARADKAR | 9425804929 | Deffered, due to high ISP generation
12 | 2025-07-15 15:58 | MR2507/0199 |  | 220KV_220KV Main Bus No.-1 | 220KV_ITARSI | NON-OCCM-MP | For Aug.Bus Tie single zebra to twin zebra | 17-07-2025 10:00:00 | 17-07-2025 15:00:00 | J.D.Khoria | 9425804975 | ok, through sub ld
13 | 2025-07-16 12:01 | MR2507/0213 |  | 220KV_132 kv Incoming of 160 mva - I | 220KV_JAORA | NON-OCCM-MP | shutdown on 132 kv Incoming - I for sefty porpose | 17-07-2025 10:00:00 | 17-07-2025 13:00:00 | RAKESH BADGOTYA | 7587951143 | ok, if 132kv load is manageble by sub ld indore
14 | 2025-07-16 12:07 | MR2507/0214 |  | 132KV_132 kv Incoming -II of 160 mva - II | 220KV_JAORA | NON-OCCM-MP | a shutdown on 132 kv Incomind of 160 mva -II | 17-07-2025 10:00:00 | 17-07-2025 13:00:00 | RAKESH BADGOTYA | 7587951143 | ok, if 132kv load is manageble by sub ld indore
15 | 2024-11-20 16:49 | MR2411/0436 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 14-07-2025 09:00:00 | 19-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Continuous
16 | 2024-11-20 16:54 | MR2411/0437 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 14-07-2025 09:00:00 | 19-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Continuous
17 | 2025-07-12 10:50 | MR2507/0161 | Continuous | 132KV_132 KV Khurai-Sagar Ckt | 132KV_KHURAI | NON-OCCM-MP | Extension of continous Sd for Modification work | 12-07-2025 07:00:00 | 18-07-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | Continuous
18 | 2025-07-16 13:00 | MR2507/0218 |  | 220KV_220KV Mandsour-Nipaniya-2 | 400KV_MANDSOUR4 | OCCM-MP | additional DPR -2 connecting & Bay Maintenance wor | 17-07-2025 14:00:00 | 17-07-2025 18:00:00 | Rajesh Bhuria | 9425806920 | ok, through sub ld
19 | 2025-07-16 12:51 | MR2507/0217 |  | 220KV_220KV Mandsour-Nipaniya-1 | 400KV_MANDSOUR4 | OCCM-MP | additional DPR -2 connecting & Bay Maintenance wor | 17-07-2025 09:00:00 | 17-07-2025 14:00:00 | Rajesh Bhuria | 9425806920 | ok, through sub ld
20 | 2025-06-30 16:20 | MR2506/0638 | Daily | 220KV_220 KV BHOPAL-MUGALIYACHAP | 220KV_MUGALIYACHAAP | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
21 | 2025-07-05 17:07 | MR2507/0079 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Insatallation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
22 | 2025-07-05 16:59 | MR2507/0078 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) LIne | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
23 | 2025-07-11 16:30 | MR2507/0154 | Daily | 220KV_Omkareshwar-Nimrani Line#1(Tap Barwaha) | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual Maintenance | 14-07-2025 09:00:00 | 17-07-2025 18:00:00 | PANKAJ SHARMA | 7898703187 | Deffered, due to high OSP generation
24 | 2025-07-11 16:39 | MR2507/0156 |  | 220KV_Main BUSâ¿¿B and Bus Coupler | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual Maintenance | 17-07-2025 09:00:00 | 17-07-2025 18:00:00 | PANKAJ SHARMA | 7898703187 | Deffered, due to high OSP generation
25 | 2025-07-16 14:01 | MR2507/0219 |  | 220KV_160 MVA TRANSFORMER-3 (BHEL) | 220KV_PITHAMPUR-II (SEC-I) | NON-OCCM-MP | BODY PROTECTION CABLE REPLACMENT WORK | 17-07-2025 10:00:00 | 17-07-2025 17:00:00 | RAJUDAS BAIRAGI | 9425801532 | real time
26 | 2025-07-16 14:09 | MR2507/0223 |  | 400KV_400KV PITHAMPUR-BADNAWAR CKT-I | 400KV_PITHAMPUR4 | NON-OCCM-MP | Relay testing work | 17-07-2025 11:00:00 | 17-07-2025 18:00:00 | Mr. Ankit Prajapati | 9131296643 | ok, through sub ld
27 | 2025-07-16 12:50 | MR2507/0216 |  | 132KV_132 KV RATLAM- KHACHROD feeder | 220KV_RATLAM | NON-OCCM-MP | Pree monsoon maintenance & Testing work | 17-07-2025 09:00:00 | 17-07-2025 14:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
28 | 2025-07-15 11:47 | MR2507/0186 | Continuous | 400KV_400 kv main bus-1 | 400KV_SAGAR | NON-OCCM-MP | for erection of panto iso and string of 400 kv bus | 17-07-2025 08:00:00 | 18-07-2025 17:00:00 | Anil mahor | 9425805149 | Deffered, not in WR list
29 | 2025-07-16 14:09 | MR2507/0222 |  | 220KV_160 MVA X-mer -II BHEL make | 220KV_SHUJALPUR | OCCM-MP | IR value measurement work of body protection cabl | 17-07-2025 09:00:00 | 17-07-2025 17:00:00 | Er. Nitin Verma | 998155007 | ok, through sub ld
30 | 2025-07-16 15:16 | MR2507/0228 |  | 220KV_220/132 Kv 160 MVA IMP X-mer | 220KV_SIRMOUR | NON-OCCM-MP | For NIFPS installation work. | 17-07-2025 10:00:00 | 17-07-2025 18:00:00 | Mr. Indrajeet Singh | 9424734033 | ok
31 | 2025-07-16 15:16 |  |  | 400KV-DAMOH-BIRSINGPUR-1 |  | OCCM-WR | AMP Work of of Line terminal equipment and its BAY at birsingpur , Non auto mode of ckt 2 is required for opportunity work in line . Dia to be kept open at both ends. | 17-Jul-2025 | 08:00 | 17-Jul-2025 | 20:00 | ok
32 | 2025-07-16 15:16 |  |  | 400KV-BHOPAL-MP-BINA-MP-2 |  | OCCM-WR | FOR BAY MAINTENANCE & TESTING WORK | 17-Jul-2025 | 09:00 | 17-Jul-2025 | 18:00 | real time
33 | 2025-07-16 15:16 |  |  | 400KV-INDORE-UJJAIN-2 |  | OCCM-WR | FOR BAY MAINTENANCE & TESTING WORK | 17-Jul-2025 | 09:00 | 17-Jul-2025 | 18:00 | real time
34 | 2025-07-16 15:16 |  |  | 220KV-GWALIOR-MAHALGAON-2 |  | OCCM-WR | FOR BAY MAINTENANCE & TESTING WORK | 17-Jul-2025 | 09:00 | 17-Jul-2025 | 17:00 | real time
35 | 2025-07-16 15:16 |  |  | 220KV-KHANDWA-CHHEGAON-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 17-Jul-2025 | 08:00 | 17-Jul-2025 | 18:00 | ok, through sub ld
36 | 2025-07-16 15:16 |  |  | 220KV-BHANPURA-MODAK-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 17-Jul-2025 | 08:00 | 17-Jul-2025 | 18:00 | real time
S/I, SLDC MPPTCL JABALPUR