## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-03 |  |  | 2025-07-03
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-30 16:24 | MR2506/0639 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA | 400KV_ASHTA4 | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
2 | 2025-06-30 16:26 | MR2506/0640 | Daily | 220KV_220 KV BAIRAGARH-ASHTA | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-06-30 16:13 | MR2506/0635 | Daily | 220KV_220 BHOPAL-BAIRAGARH CKT-3 | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
4 | 2025-06-25 14:54 | MR2506/0536 | Continuous | 400KV_400kV Bhopal-Itarsi Ckt. 1&2 | 400KV_BHOPAL4 | NON-OCCM-WR | For Tan Delta Measurement & Other bay Maint. Work | 03-07-2025 09:00:00 | 04-07-2025 18:00:00 | Akram Khan | 9425804695 | not in WR list
5 | 2025-07-02 12:50 | MR2507/0034 |  | 220KV_200 MVA T&R x-mer | 220KV_BINA | NON-OCCM-MP | R Phase SCT Make CT Replacement work | 03-07-2025 09:30:00 | 03-07-2025 17:30:00 | Lalit singh | 9425806845 | ok, through sub ld
6 | 2025-06-26 14:17 | MR2506/0554 | Daily | 220KV_220 KV Bina-Guna Ckt & 220 KV Bina-Ashoknagar Ckt | 400KV_BINA4 | NON-OCCM-MP | Hot line PTW for OPGW resagging work BY M/s ZTT | 26-06-2025 07:00:00 | 10-07-2025 19:00:00 | Sanjay singh thakur | 9425806936 | ok, line to be in service
7 | 2025-06-30 15:05 | MR2506/0620 | Continuous | 132KV_132KV Budha Mandsaur | 132KV_BUDHA | NON-OCCM-MP | in OPGW OTDR Testing and OPGW Splicing | 01-07-2025 08:30:00 | 08-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | sub ld
8 | 2025-07-02 10:38 | MR2507/0025 |  | 400KV_400Kv Main Bus-II | 400KV_CHHEGAON4 | NON-OCCM-MP | 400Kv Julwania-I&II pantograph isolator spider | 03-07-2025 10:00:00 | 03-07-2025 18:00:00 | Shri Ganesh Mansare | 9425802441 | If there is emergency, WRLDC approval for emergency required
9 | 2025-07-02 11:59 | MR2507/0028 |  | 400KV_400 kV Chhegaon - Khandwa (PGCIL) Ckt-1st | 400KV_CHHEGAON4 | OCCM-WR | Jumper Cone Tightening & Other Line Maintenance | 03-07-2025 10:00:00 | 03-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, through sub ld
10 | 2025-07-02 16:18 | MR2507/0037 |  | 132KV_40 MVA TELK XMER | 132KV_GARHAKOTA | NON-OCCM-MP | CT REPLACEMENT WORK OF R PH CT | 03-07-2025 12:00:00 | 03-07-2025 16:00:00 | SRAJAN SISODIYA | 9425804341 | o&m consent required
11 | 2025-05-07 15:18 | MR2505/0133 | Continuous | 160MVA_220/132KV_BHEL_X'mer_1 | 220KV_HANDIYA | NON-OCCM-MP | for Replacement of Transformer | 08-05-2025 10:00:00 | 08-07-2025 17:00:00 | J.D.Khoria | 9425804975 | Continuous
12 | 2025-06-23 17:09 | MR2506/0482 | Daily | 220KV_220 KV South Zone - Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
13 | 2025-06-23 17:04 | MR2506/0481 | Daily | 220KV_220KV Indore (400KV) - Mangliya line | 400KV_INDORE4 | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
14 | 2025-07-02 16:28 | MR2507/0039 |  | 220KV_JULWANIYA4-JULWANIYA_Ckt_1 | 400KV_JULWANIYA4 | NON-OCCM-MP | Line differential relay connection work | 03-07-2025 10:00:00 | 03-07-2025 17:00:00 | Ravindra Patil | 8305612190 | ok, through sub ld
15 | 2024-11-20 16:41 | MR2411/0432 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 30-06-2025 09:00:00 | 05-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Continuous
16 | 2024-11-20 16:43 | MR2411/0433 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 30-06-2025 09:00:00 | 05-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Continuous
17 | 2025-07-02 12:12 | MR2507/0031 |  | 132KV_132 KV KATNI SLEEMNABAD LINE | 400KV_KATNI4 | NON-OCCM-MP | FOR OPG STRING WORK | 03-07-2025 10:00:00 | 03-07-2025 18:00:00 | PANKAJ YADAV | 9406713326 | hotline work or outage?, if hot line work , ensure telemtry
18 | 2025-06-30 13:59 | MR2506/0611 | Continuous | 132KV_132 KV KATNI SLEEMNABAD LINE | 400KV_KATNI4 | NON-OCCM-MP | Work for OPG stringigng work | 01-07-2025 08:00:00 | 05-07-2025 18:00:00 | PANKAJ YADAV | 9406713326 | hotline work or outage?, if hot line work , ensure telemtry
19 | 2025-07-02 11:54 | MR2507/0026 |  | 132KV_132 KV KATNI KYMORE CKT 1ST | 400KV_KATNI4 | NON-OCCM-MP | FOR OPGE STRING WORK | 03-07-2025 10:00:00 | 03-07-2025 18:00:00 | PANKAJ YADAV | 9406713326 | hotline work or outage?, if hot line work , ensure telemtry
20 | 2025-07-02 12:50 | MR2507/0035 | Daily | 132KV_132 KV KATNI KYMORE CKT 1 | 400KV_KATNI4 | NON-OCCM-MP | Work for OPG stringigng work | 03-07-2025 08:00:00 | 05-07-2025 18:00:00 | pankaj yadav | 9406713326 | hotline work or outage?, if hot line work , ensure telemtry
21 | 2025-07-01 15:42 | MR2507/0010 | Continuous | 132KV_132 KV Khurai-Sagar | 132KV_KHURAI | NON-OCCM-MP | Modification/Shifting of 132 KV Khurai-Sagar | 02-07-2025 07:00:00 | 12-07-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | Continuous
22 | 2025-07-02 16:27 | MR2507/0038 |  | 132KV_132 kV Moondi - Narmadanagr PH-I Kalisindh line | 132KV_MOONDI | NON-OCCM-MP | Rectification work | 03-07-2025 10:00:00 | 03-07-2025 14:00:00 | M.K. More | 8817566466 | sub ld
23 | 2025-06-30 16:20 | MR2506/0638 | Daily | 220KV_220 KV BHOPAL-MUGALIYACHAP | 220KV_MUGALIYACHAAP | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
24 | 2025-07-02 12:14 | MR2507/0032 |  | 50MVA_132/33KV_TAL_Xmer | 132KV_NAGOD | NON-OCCM-MP | 132/33 kv of 50 mva x-mer make TAL magnetizing cur | 03-07-2025 11:00:00 | 03-07-2025 13:00:00 | Ravi praksh pandey | 9425805296 | ok
25 | 2025-06-26 14:57 | MR2506/0557 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | OCCM-WR | Hotline work For Installation OPGW by replace E/W | 26-06-2025 08:00:00 | 10-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
26 | 2025-06-26 15:04 | MR2506/0558 | Daily | 132KV_132 kV Nepa - Pipalpani | 220KV_NEPANAGAR | NON-OCCM-MP | Hotline work Installation OPGW Replaced by E/W | 26-06-2025 08:00:00 | 10-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
27 | 2025-07-01 11:19 | MR2507/0002 |  | 220KV_Panagar- Birsinghpur line | 220KV_PANAGAR | NON-OCCM-MP | Hot point on R phase line isolator CT side clamp | 03-07-2025 12:00:00 | 03-07-2025 15:00:00 | H L koshta | 7587951105 | ok
28 | 2025-07-02 17:05 | MR2507/0040 |  | 132KV_132/33KV 40MVA X-MER | 132KV_PANSEMAL | NON-OCCM-MP | 33KV I/C MAIN BUS ISOLATOR TO BREAKER SIDE JUMPER | 03-07-2025 11:30:00 | 03-07-2025 14:00:00 | RAVINDRA PATIL | 8305612190 | sub ld
29 |  |  |  | 220 KV MAIN BUS AT 220 KV KUKSHI |  |  | ISOLATOR ALIGNMENT | 03-07-2025 09:30:00 | 03-07-2025 12:30:00 |  |  | NOT IN PORTAL
30 | 2025-07-02 13:00 | MR2507/0036 |  | 132KV_40 MVA X-MER NGEF | 220KV_REWA | OCCM-MP | 40 MVA 33 KV MAIN BUS B PHASE JUMPER REPLACEMENT | 03-07-2025 08:00:00 | 03-07-2025 11:00:00 | INDRAJEET SINGH | 9424734033 | ok
31 | 2025-06-30 14:20 | MR2506/0616 | Daily | 132KV_132kv sagar-sagar ic ic 1st ckt. | 400KV_SAGAR | NON-OCCM-MP | OPGW stringing work ( hot Line permit) | 01-07-2025 07:00:00 | 08-07-2025 19:00:00 | Er. Pankaj Yadav. | 9406713326 | ok, line to be in service
32 | 2025-06-30 14:13 | MR2506/0612 | Daily | 132KV_132kv Sagar-sagar ic 3rd ckt. | 400KV_SAGAR | NON-OCCM-MP | opgw stringing Work (hot line permit) | 01-07-2025 07:00:00 | 08-07-2025 19:00:00 | Er. pankaj yadav | 9406713326 | ok, line to be in service
33 | 2025-05-03 11:32 | MR2505/0054 | Continuous | 220KV_100 MVA X-mer Make CGL | 220KV_SARNI | NON-OCCM-MP | X-mer Augmentation work by 160 MVA X-mer AREVA | 05-05-2025 10:00:00 | 10-07-2025 17:00:00 | Er K.K. Choure | 9425801357 | Continuous
34 | 2025-07-02 12:01 | MR2507/0029 |  | 132KV_132 kV Satna-Pawai line | 220KV_SATNA | NON-OCCM-MP | Stringing work of 220 kV Satna-Katni LILO line | 03-07-2025 08:00:00 | 03-07-2025 18:00:00 | Dharmendra Dwivedi | 9425805311 | ok
35 | 2025-07-02 11:57 | MR2507/0027 |  | 132KV_132 kV Satna-Nagod-I | 220KV_SATNA | NON-OCCM-MP | Stringing work of 220 kV Satna-Katni LILo line | 03-07-2025 08:00:00 | 03-07-2025 18:00:00 | Dharmendra Dwivedi | 9425805311 | ok
36 | 2025-06-25 16:02 | MR2506/0542 |  | 400KV_Sarni Indirasagar line | 400KV_SATPURA TPS | NON-OCCM-MP | Installation of fire wedge connector | 03-07-2025 09:00:00 | 03-07-2025 17:00:00 | SHIV KUMAR | 9425806917 | Deffered due to s/d on 400kv Sarni-Seoni ckt
37 |  | 254082 |  | 400KV-SSP-RAJGARH-2 |  | WR OCCM | to carry out the DISTANCE PROTECTION SCHEME of MAIN-1 & MAIN-2 relay testing work. | 03-07-2025 08:00:00 | 04-07-2025 18:00:00 |  |  | OK All other lines from SSP to be in serviuce. Ckt-1 (29% sensitivity) to be in service. NCA/WR2/SLDC MP to be informed.
38 |  | 251301 |  | 400KV-SEONI-PG-SATPURA-1 |  | WR OCCM | LINE BAY AMP WORK AT SEONI SS | 03-07-2025 09:00:00 | 03-07-2025 18:00:00 |  |  | OK All other lines at Stapura to be in service with AR enable. SLDC MP to be informed.
39 |  | 253283 |  | 400KV-CHHEGAON-KHANDWA-1 |  | WR OCCM | FOR BAY MAINTENANCE & TESTING WORK | 03-07-2025 10:00:00 | 03-07-2025 18:00:00 |  |  | OK All other lines at Chhegaon/Khandwa to be in service. Load to be managed by SLDC MP.
40 |  | 253310 |  | 220KV-SATNA-KOTAR-1 |  | WR OCCM | FOR LINE MAINTENANCE WORK | 03-07-2025 10:00:00 | 03-07-2025 17:00:00 |  |  | REAL TIME Ok, All other 220 kV lines at Satna to be in service. Load to be managed by SLDC MP.
41 |  | 253282 |  | 400KV/220KV JABALPUR-ICT-1 |  | WR OCCM | FOR BAY MAINTENANCE & TESTING WORK | 02-07-2025 09:00:00 | 03-07-2025 17:00:00 |  |  | REAL TIME (Sensitivity on ICT-2 is 26% and ICT-3 is 42%) to be in service with complete dia. WR2 to be informed. Load to be managed by SLDC MP in case of any contingency. WR-2 to be informed.
42 |  | 253700 |  | 132KV-DHARNI-NEPANAGAR-1 |  | WR OCCM | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 03-07-2025 08:00:00 | 03-07-2025 17:59:00 |  |  | OK A/R in N/A, Line will be in service.