## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-05 |  |  | APPROVED OUTAGE LIST FOR DTD.05.09.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-25 15:08 | MR2508/0326 | Daily | 220KV_220KV Anuppur Kotmikala ckt-2 | 220KV_ANUPPUR | NON-OCCM-MP | For Re-sagging work due to Low Ground clearance ma | 31-08-2025 08:00:00 | 08-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
2 | 2025-09-04 14:16 | MR2509/0089 |  | 132KV_132 kV Bhopal-Lalghati line | 220KV_BHOPAL | NON-OCCM-MP | Emergency Tree cutting work | 05-09-2025 10:00:00 | 05-09-2025 17:00:00 | Ankit Mehroliya | 9425804506 | SUB LD
3 | 2025-09-04 15:21 | MR2509/0092 |  | 132KV_132 kV Shahdol-Birsinghpur Circuit II | 220KV_BIRSINGHPUR | NON-OCCM-MP | replacement of damage OPGW | 05-09-2025 10:00:00 | 05-09-2025 17:00:00 | Jitendra Tiwari | 9425805298 | OK
4 | 2025-09-04 16:06 | MR2509/0101 |  | 220KV_200MVA 220/132KV T&R X-MER | 220KV_DAMOH | NON-OCCM-MP | Replacement of Inter butter Fly Valve of NIFPS Sys | 05-09-2025 11:00:00 | 05-09-2025 14:00:00 | M.K.Choubey | 9425801424 | OK
5 | 2025-09-04 15:26 | MR2509/0093 |  | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | replacement of damage OPGW | 05-09-2025 10:00:00 | 05-09-2025 17:00:00 | Jitendra Tiwari | 9425805298 | OK
6 | 2025-09-02 18:32 | MR2509/0063 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1& ckt-2 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | DEFERRED, WRPC CONSENT REQUIRED, DATA REROUTING & COMMUNICATION CONFIRMATION REQUIRED
7 | 2025-09-04 14:57 | MR2509/0091 |  | 220KV_220 KV JULWANIYA-SENDHWA CKT-II | 400KV_JULWANIYA4 | NON-OCCM-MP | FOR Addi. DPR & DTPC wiring | 05-09-2025 10:00:00 | 05-09-2025 17:00:00 | Pappu Awase | 7566990161 | OK THROUGH SUB LD
8 | 2025-06-30 16:15 | MR2506/0636 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 01-09-2025 09:00:00 | 06-09-2025 18:00:00 | PANKAJ YADAV | 9406713326 | DEFERRED WRPC CONSENT REQUIRED
9 | 2025-06-30 15:33 | MR2506/0626 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 01-09-2025 09:00:00 | 06-09-2025 18:00:00 | PANKAJ YADAV | 9406713326 | DEFERRED WRPC CONSENT REQUIRED
10 | 2025-09-02 18:36 | MR2509/0064 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line.&132KV Niranjanpur - Jaitpura Line &132KV North Zone- Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD, DATA REROUTING & COMMUNICATION REQUIRED
11 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | CONTINUE, FTC TO BE SUBMITTED PRIOR TO CHARGING
12 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | RAJESH TIWARI | 7898239595 | CONTINUE
13 | 2025-09-02 14:10 |  |  | 220KV-RAJGARH-RAJGARH-MP-2 |  | OCCM-WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 05-Sep-2025 | 08:00 | 05-Sep-2025 | 18:00 | OK THROUGH SUB LD
14 | 2025-09-02 14:10 |  |  | 400KV-SATPURA-ITARSI-1 |  | OCCM-WR | For replacemnet of Bus-1 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400kV Bus-1 is required at Sarni S/S of MPGENCO) AND CT Oil sampling at Itarsi And CVT Replacement of 400KV-SATPURA-ITARSI-1 under ADD CAP at MPGENCO | 02-Sep-2025 | 09:00 | 05-Sep-2025 | 20:00 | continue
15 | 2025-09-02 14:10 |  |  | SATPURA - 400KV - BUS 1 |  | OCCM-WR | For replacemnet of Bus-1 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400KV-SATPURA-ITARSI-1 is required) | 02-Sep-2025 | 09:00 | 05-Sep-2025 | 20:00 | continue
S/I, SLDC MPPTCL JABALPUR.