## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-24
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-23 14:56 | MR2510/0540 |  | 132KV_63 MVA and 40 MVA X-mer | 132KV_AMARPATAN | NON-OCCM-MP | For erection of 40 MVA Telk Xmer | 24-10-2025 08:00:00 | 24-10-2025 11:00:00 | Arun KUmar | 9131207339 | o&m consent required
2 | 2025-10-23 15:54 | MR2510/0543 |  | 132KV_40 MVA BBL Xmer | 132KV_AMARPATAN | NON-OCCM-MP | erection of 40 MVA Telk Xmer | 24-10-2025 06:00:00 | 24-10-2025 17:00:00 | Arun Kumar | 9131207339 | o&m consent required
3 | 2025-10-23 12:37 | MR2510/0530 |  | 220KV_160 MVA X-MER BBL | 220KV_ASHOKNAGAR | NON-OCCM-MP | POST MANSOON MAINT. | 24-10-2025 10:00:00 | 24-10-2025 18:00:00 | RAKESH SUMAN | 7587951093 | ok, through sub ld
4 | 2025-10-23 13:48 | MR2510/0537 |  | 160MVA_220/132KV_BHEL_X'mer | 220KV_BHANPURA | OCCM-MP | post monsoon maintenance | 24-10-2025 10:00:00 | 24-10-2025 18:00:00 | SH Rajesh Bhuriya | 9425811507 | ok, through sub ld
5 | 2025-10-21 12:54 | MR2510/0500 | Continuous | 220KV_Transfer the Load of 220 kV Interconnector 2 line on Bus Transfer | 220KV_BHOPAL | NON-OCCM-WR | main CB of 220 kV Interconnector 2 line is not rel | 22-10-2025 17:00:00 | 24-10-2025 17:00:00 | A. K. Jain | 9425806899 | Continuous
6 | 2025-10-23 13:48 | MR2510/0538 |  | 220KV_220 KV Bina-Sagar Ckt-1 | 400KV_BINA4 | NON-OCCM-MP | For f/o insulator replacement & other line maint | 24-10-2025 10:00:00 | 24-10-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | Deffered due to s/d on 220KV Damoh-Sagar 2nd Ckt.(PGCIL) Line
7 | 2025-09-18 17:24 | MR2509/0455 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 22-10-2025 09:00:00 | 25-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deffered
8 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
9 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
10 | 2025-10-22 14:39 | MR2510/0519 |  | 220KV_220KV Itarsi - Pipariya No.1 | 220KV_ITARSI | NON-OCCM-MP | Rep of damge Jumper of Bus Selection Isolator | 24-10-2025 11:00:00 | 24-10-2025 17:00:00 | JD Khoria | 9425804975 | ok, through sub ld, line to be in service through TBC
11 | 2025-09-18 13:08 | MR2509/0413 | Continuous | 400KV_400KV DAMOH - KATNI LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 22-10-2025 09:00:00 | 25-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deffered
12 | 2025-10-23 15:05 | MR2510/0541 |  | 400KV_400/132/33 KV 100 MVA transformer No-02 BHEL | 400KV_KIRNAPUR | NON-OCCM-MP | for post monsoon Maintenance works | 24-10-2025 09:00:00 | 24-10-2025 17:00:00 | D. S. Walkey | 9425804578 | ok
13 | 2025-10-23 15:17 | MR2510/0542 |  | 132KV_40MVA TRANSFORMER-II ABB | 220KV_KUKSHI | NON-OCCM-MP | POST MONSOON MAINTENANCE | 24-10-2025 10:00:00 | 24-10-2025 18:00:00 | ER. I.S. CHOUNGAD | 9425803475 | sub ld
14 | 2025-10-23 14:03 | MR2510/0539 |  | 132KV_132 kv Morwa â¿¿Bargawan (TBCB) circuit-II | 132KV_MORWA | NON-OCCM-MP | other line maintenance | 24-10-2025 10:00:00 | 24-10-2025 17:00:00 | G.L Sahu | 9425805102 | ok, o&m shall be informed
15 | 2025-10-21 20:35 | MR2510/0506 | Daily | 220KV_MAIN BUS B AND BUS COUPLER | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual Maintenance | 24-10-2025 09:30:00 | 25-10-2025 18:00:00 | PANKAJ SHARMA | 7898703187 | ok
16 | 2025-10-21 20:11 | MR2510/0504 | Daily | 220KV_OMKARESHWAR-NIMRANI-Tap-BARWAHA_Ckt | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual maintenance | 23-10-2025 09:30:00 | 25-10-2025 18:00:00 | Pankaj Sharma | 7898703187 | ok, through sub ld
17 | 2025-10-23 13:20 | MR2510/0536 |  | 160MVA_220/132KV_BHEL_X'mer | 220KV_PANAGAR | NON-OCCM-MP | Post mansoon maintinance | 24-10-2025 10:00:00 | 24-10-2025 18:00:00 | H.L.KOSTA | 9893281195 | ok
18 | 2025-10-23 12:57 | MR2510/0533 |  | 40MVA_132/33KV_ABB_X'mer_1 | 132KV_RAMPUR BAGHELAN | NON-OCCM-MP | post monsoon maintenance &Testing Work | 24-10-2025 10:00:00 | 24-10-2025 18:00:00 | K.K. Patel | 9893124647 | ok
19 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
20 | 2025-10-23 16:00 | MR2510/0544 |  | 132KV_132KV Neemuch-Ratangarh Line | 220KV_RATANGARH | NON-OCCM-MP | For Line Maintenance work | 24-10-2025 10:00:00 | 24-10-2025 18:00:00 | Gaurav Goyal | 9425805120 | sub ld
21 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
22 | 2025-10-23 12:41 | MR2510/0532 |  | 220KV_220KV Damoh-Sagar 2nd Ckt.(PGCIL) Line | 400KV_SAGAR | OCCM-MP | Line maintenance work | 24-10-2025 09:00:00 | 24-10-2025 18:00:00 | J.P. Asati | 9424445533 | ok
23 | 2025-10-23 13:06 | MR2510/0534 |  | 40MVA_132/33KV_BBL_X'mer | 132KV_SULTANPUR | NON-OCCM-MP | Post- monsoon Maint.& Testing Work | 24-10-2025 10:00:00 | 24-10-2025 13:00:00 | B.L.Lakhore | 7587951074 | sub ld
24 | 2025-10-23 13:17 | MR2510/0535 |  | 132KV_40 MVA X-Mer no.02 Make TELK | 132KV_SULTANPUR | NON-OCCM-MP | for Post-Monsoon Maint.& Testing work | 24-10-2025 13:30:00 | 24-10-2025 17:00:00 | B.L.Lakhore | 7587951074 | sub ld
25 | 2025-10-23 12:37 | MR2510/0531 |  | 132KV_132/33KV 50MVA X-MER TAL | 132KV_TEJGARH | NON-OCCM-MP | POST MONSOON MAINTENANCE WORK | 24-10-2025 10:00:00 | 24-10-2025 18:00:00 | RAHUL GAJBHIYE | 9425801304 | ok
26 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
27 |  | 265937 | Daily | 400KV-BINA-MP-GUNA-MP-1 | 400 | MP_SLDC | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 24-Oct-2025 | 09:00 | 24-Oct-2025 | 17:00 | real time
28 |  | 265976 | Daily | 220KV-MORENA-MALANPUR-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 24-Oct-2025 | 09:00 | 24-Oct-2025 | 17:00 | real time
29 |  | 265977 | Daily | 220KV-DAMOH-SAGAR-2 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 24-Oct-2025 | 09:00 | 24-Oct-2025 | 18:00 | ok
30 |  | 265978 | Daily | 220KV-ANNUPUR-KOTMIKALA-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 24-Oct-2025 | 9:00 | 24-Oct-2025 | 18:00 | real time
31 |  | 265979 | Daily | 220KV-REWA-SINDHI-MP-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 24-Oct-2025 | 10:00 | 24-Oct-2025 | 17:00 | real time