## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-10 |  |  | 2025-10-10
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-09 12:43 | MR2510/0246 |  | 132KV_50MVA X-MER BBL | 132KV_132KV_GYARASPUR | OCCM-MP | POST MONSOON MAINTENANCE WORK | 10-10-2025 09:00:00 | 10-10-2025 16:00:00 | K.C. GOSWAMI | 9425804976 | OK O&M TO BE INTIMATED
2 | 2025-10-03 11:54 | MR2510/0055 | Daily | 220KV_220 kV Adampur-Hoshangabd line | 220KV_ADAMPUR | NON-OCCM-MP | Defective disc replacement work | 04-10-2025 09:00:00 | 14-10-2025 17:00:00 | Ankit Mehroliya | 9425804506 | OK THROUGH SUB LD
3 | 2025-10-09 14:00 | MR2510/0255 |  | 132KV_132/33kv 50mva xmer bbl | 220KV_BADNAGAR | OCCM-MP | For Post mansoon maintenance and testing work | 10-10-2025 10:00:00 | 10-10-2025 15:00:00 | Poshkar kushwaha | 9425813990 | SUB LD
4 | 2025-10-09 11:19 | MR2510/0242 |  | 132KV_132 KV Bina-BORL Ckt-1 tap to 132 KV Bina-BORL ckt-2. | 220KV_BINA | NON-OCCM-MP | for line maintenance work | 10-10-2025 10:00:00 | 10-10-2025 17:00:00 | Sanjay Singh Thakur | 9425806936 | SUB LD
5 | 2025-10-09 16:12 | MR2510/0271 |  | 132KV_132KV Neemuch Budha Line | 132KV_BUDHA | NON-OCCM-MP | For line maintanence work | 10-10-2025 10:00:00 | 10-10-2025 18:00:00 | Gaurav Goyal | 9425805120 | SUB LD
6 | 2025-10-09 13:42 | MR2510/0250 |  | 132KV_132 kV Chhatarpur â¿¿ Bijawar ckt. 1st Tap Nowgaon Line | 220KV_CHATARPUR | NON-OCCM-MP | F/O Disc Repalcement & other line maintenance work | 10-10-2025 10:00:00 | 10-10-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | OK
7 | 2025-10-09 14:57 | MR2510/0260 |  | 40MVA_132/33KV_BBL_X'mer_2 | 220KV_CHHINDWARA | NON-OCCM-MP | POST MANSOON MAINTENANCE WORK. | 10-10-2025 11:00:00 | 10-10-2025 17:00:00 | A A QURESHI | 9425804318 | OK O&M TO BE INTIMATED
8 | 2025-10-09 12:25 | MR2510/0245 |  | 132KV_63MVA X-Mer No. II EMCO | 132KV_CHHINDWARA1 | NON-OCCM-MP | Post Mansoon Maintenance Work | 10-10-2025 09:00:00 | 10-10-2025 14:00:00 | Er. Anju Dhurve | 9425804752 | OK O&M TO BE INTIMATED
9 | 2025-10-09 13:50 | MR2510/0254 |  | 220KV_160 MVA transformer-II make BHEL | 220KV_DALODA | NON-OCCM-MP | Post monsoon maintenance work. | 10-10-2025 10:00:00 | 10-10-2025 17:00:00 | Er. Shailendra Bourasi | 9907246485 | OK THROUGH SUB LD
10 | 2025-09-18 17:16 | MR2509/0453 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 06-10-2025 09:00:00 | 11-10-2025 18:00:00 | SHRI M. M. BAIG | 9425805067 | DEFERRED
11 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | DEFERRED
12 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | DEFERRED
13 | 2025-10-09 16:47 | MR2510/0273 |  | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | Insttalation of OPGW String work. | 10-10-2025 08:00:00 | 10-10-2025 17:00:00 | G.L Sahu | 9425805102 | DATA CONFIRMATION REQUIRED FROM COMMUNICATION
14 |  |  |  | 220 KV DEWAS-INDORE |  |  | CB CLAMP HOT POINT ATTEND TO TAKE LOAD ON BUS COUPLER | 10-10-2025 10:00:00 | 10-10-2025 14:00:00 |  |  | OK THROUGH SUB LD
15 | 2025-10-09 15:34 | MR2510/0269 | Continuous | 220KV_160 MVA X-MER 3rd BHEL | 220KV_DEWAS | NON-OCCM-WR | Post monsoon maintenance. | 09-10-2025 09:30:00 | 10-10-2025 17:00:00 | Arvind Kumar Joshi | 9425801305 | OK
16 | 2025-10-09 16:41 | MR2510/0272 |  | 132KV_132 Anuppur - Dongrital Ckt | 132KV_DONGRITAL | NON-OCCM-MP | Disc Replacement Work. | 10-10-2025 10:00:00 | 10-10-2025 16:00:00 | G.L Sahu | 9425805102 | OK
17 | 2025-10-09 13:32 | MR2510/0248 |  | 132KV_132KV Guna Bhonra Ckt. Ist | 220KV_GUNA | NON-OCCM-MP | DF/O Replacement & other line maint. work | 10-10-2025 09:00:00 | 10-10-2025 17:00:00 | Akhilesh Singh | 8586865656 | SUB LD
18 | 2025-10-04 12:27 | MR2510/0086 | Daily | 220KV_220 KV Hoshangabad-Adampur | 220KV_HOSHANGABAD | NON-OCCM-MP | Resagging work b/w loc.no. 20 of lilo to 71 | 05-10-2025 09:00:00 | 10-10-2025 17:00:00 | Ashutosh Rai | 9425806902 | AS OPPORTUNITY SD
19 | 2025-10-08 13:14 | MR2510/0209 |  | 220KV_220KV INDORE-SOUTH ZONE-1 | 400KV_INDORE4 | NON-OCCM-MP | POST MONSOON MAINTANANCE WORK | 10-10-2025 09:00:00 | 10-10-2025 17:00:00 | ATUL PARADKAR | 9425804929 | OK THROUGH SUB LD
20 | 2025-10-09 15:39 | MR2510/0270 |  | 132KV_50MVA xmer 02 | 132KV_KARERA | NON-OCCM-MP | Post monsoon maintenance work | 10-10-2025 10:00:00 | 10-10-2025 17:00:00 | Virendra K ahirwar | 9425801438 | SUB LD
21 | 2025-10-09 14:59 | MR2510/0262 |  | 132KV_132 kv katni sleemnabad line ckt 2 nd | 132KV_KATNI | NON-OCCM-MP | For replacement OPG wire | 10-10-2025 10:00:00 | 10-10-2025 18:00:00 | pankaj yadav | 9406713326 | DATA CONFIRMATION SHALL BE ENSURED BY COMMUNICATION DEPARTMENT
22 | 2025-10-09 15:06 | MR2510/0265 |  | 132KV_132 kv katni panagar line | 132KV_KATNI | NON-OCCM-MP | For replacement OPG wire | 10-10-2025 10:00:00 | 10-10-2025 15:00:00 | pankaj yadav | 9406713326 | DATA CONFIRMATION SHALL BE ENSURED BY COMMUNICATION DEPARTMENT
23 | 2025-09-18 12:55 | MR2509/0410 | Continuous | 400KV_400KV DAMOH - KATNI LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 06-10-2025 09:00:00 | 11-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | DEFERRED
24 | 2025-10-09 14:23 | MR2510/0257 |  | 132KV_40 MVA BHEL TRANSFORMER | 132KV_KHURAI | NON-OCCM-MP | POST MONSOON MAINTENANCE WORK | 10-10-2025 08:00:00 | 10-10-2025 14:00:00 | ER. LALIT SINGH | 9425806845 | OK O&M TO BE INTIMATED
25 | 2025-10-09 11:21 | MR2510/0243 |  | 220KV_220 kv Kotarâ¿¿ Tons Ckt - Ist | 220KV_KOTAR | NON-OCCM-MP | Line maintenance work | 10-10-2025 11:00:00 | 10-10-2025 17:00:00 | Mr.R. K. Prajapati | 9407070182 | OK
26 | 2025-10-09 13:44 | MR2510/0252 |  | 220KV_160 MVA Transformer-I BBL | 220KV_KUKSHI | NON-OCCM-MP | For Post Monsoon Maintenace work | 10-10-2025 10:00:00 | 10-10-2025 18:00:00 | ER I.S.Chongad | 7898156028 | OK THROUGH SUB LD
27 | 2025-10-05 10:37 | MR2510/0101 | Daily | 132KV_132KV Neemuch Manasa Line | 132KV_MANASA | NON-OCCM-MP | Re sagging and line maintanence work | 06-10-2025 08:00:00 | 12-10-2025 18:00:00 | Gaurav goyal | 9425805120 | SUB LD
28 | 2025-10-09 15:23 | MR2510/0267 |  | 220KV_160 MVA AREVA TRANSFORMER 220/132/33KV | 220KV_NAGDA | NON-OCCM-MP | POST MANSOON MAINTENANCE WORK | 10-10-2025 10:00:00 | 10-10-2025 17:00:00 | VIKRAM DEHARIYA | 7000276050 | OK THROUGH SUB LD
29 | 2025-10-09 15:07 | MR2510/0266 |  | 132KV_132 kV Pandhurna Multai | 220KV_PANDHURNA | NON-OCCM-MP | ground clearance & Bird guard provide | 10-10-2025 09:00:00 | 10-10-2025 17:00:00 | A.M.Shende | 7587951136 | OK
30 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | DATA CONFIRMATION SHALL BE ENSURED BY COMMUNICATION DEPARTMENT
31 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | DATA CONFIRMATION SHALL BE ENSURED BY COMMUNICATION DEPARTMENT
32 | 2025-10-09 14:58 | MR2510/0261 |  | 220KV_220/132KV 160MVA AREVA TRANSFORMER-1 | 400KV_SAGAR | NON-OCCM-MP | POST MANSOON MAINTENANCE AND TESTING WORK | 10-10-2025 08:30:00 | 10-10-2025 16:30:00 | SRAJAN SISODIYA | 7879960164 | OK
33 | 2025-10-09 15:26 | MR2510/0268 |  | 132KV_132/33KV 40MVA X-mer-1 Make BBL | 220KV_SEONI | NON-OCCM-MP | post monsoon Maintenance work | 10-10-2025 07:00:00 | 10-10-2025 16:00:00 | Shri C.S.sanodiya | 9009798506 | OK O&M TO BE INTIMATED
34 | 2025-10-09 14:43 | MR2510/0259 |  | 132KV_132kV Seoni Lalbarra Feeder | 132KV_SEONI1 | NON-OCCM-MP | Replacement of PID defective disc insulator | 10-10-2025 10:00:00 | 10-10-2025 17:00:00 | S.K. Nadekar | 9425806848 | OK
35 | 2025-10-09 13:36 | MR2510/0249 |  | 400KV_400KV Pithampura-II for PMU commissioning work | 400KV_SINGHAJI TPS | NON-OCCM-MP | PMU commissioning work by MPPTCL | 10-10-2025 10:00:00 | 10-10-2025 18:00:00 | Deepak Sharma | 8005696855 | OK THROUGH SUB LD
36 | 2025-10-08 15:33 | MR2510/0236 |  | 132KV_132 KV AUX. BUS | 132KV_SINHAWAL | NON-OCCM-MP | ISOLATOR TO AUX. BUS JUMPRING WORK | 10-10-2025 09:00:00 | 10-10-2025 18:00:00 | J N SINGH | 9425802388 | sub ld
37 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | OK, FTC TO BE SUBMITTED PRIOR TO CHARGING
38 | 2025-10-08 14:37 | MR2510/0220 |  | 220KV_220 KV Main Bus IInd | 400KV_UJJAIN4 | NON-OCCM-WR | Main Bus maintenance work at 400 kv substaion ujja | 10-10-2025 10:00:00 | 10-10-2025 18:00:00 | S.Chavrasia | 9425804677 | OK THROUGH SUB LD
39 | 2025-10-08 14:26 | MR2510/0218 |  | 132KV_40 MVA BBL NO.-2 | 132KV_VFJ | NON-OCCM-MP | POST MONSOON MAINTENENCE | 10-10-2025 09:00:00 | 10-10-2025 17:00:00 | AMIT KUMAR DAHIYA | 9425806926 | OK
40 |  | 265200 |  | 220KV-GWALIOR-MAHALGAON-2 |  | WR-OCCM | AMP Works | 10-10-2025 09:00:00 | 10-10-2025 18:00:00 |  |  | OK THROUGH SUB LD All other lines at Mahalgaon to be in service with AR enabled. No other element shall be effected. care to be taken. Wr2 to be informed. Load to be managed by SLDC MP
41 |  | 265316 |  | 220KV-BHIND-MORENA-1 |  | WR-OCCM | LINE AMP WORK (CRM Test of Isolator,CT Tan delta,LA IR and other checks) | 10-10-2025 09:00:00 | 10-10-2025 18:00:00 |  |  | OK THROUGH SUB LD circuit 2 to be in service. Load to be managed by SLDC MP. SLDC to be informed.
42 |  | 265928 |  | 400KV-INDORE-PITHAMPUR-2 |  | WR-OCCM | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 10-10-2025 08:00:00 | 10-10-2025 18:00:00 |  |  | OK THROUGH SUB LD Ok.400kV INDORE-PG -PITHAMPUR -T1 Sensitivity of 36.00% and All other lines at INDORE - 400KV and PITHAMPUR - 400KV to be in service with A/R Enabled
43 |  | 265929 |  | 400KV-BHOPAL-MP-ITARSI-2 |  | WR-OCCM | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 10-10-2025 09:00:00 | 10-10-2025 18:00:00 |  |  | OK THROUGH SUB LD Ok.400kV BHOPAL-MP -ITARSI-PG -T1 Sensitivity of 49.51% and All other lines at BHOPAL-MP - 400KV and ITARSI - 400KV to be in service with A/R Enabled. 400 kV Bhopal-Bina line 1 is under forced outage.
44 |  | 265951 |  | 220KV-MALANPUR-AURIYA-1 |  | WR-OCCM | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 10-10-2025 09:00:00 | 10-10-2025 17:00:00 |  |  | OK THROUGH SUBLD All other lines at Malanpur to be in service. Load to be managed by SLDC MP. NLDC consent is required.
45 |  | 265219 |  | 400KV-KORADI-SATPURA-1 |  | WR-OCCM | For replacemnet of Bus-1 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400kV Bus-1 is required at Sarni S/S of MPGENCO) And CVT Replacement of 400KV-SATPURA-KORADI-1 under ADD CAP at MPGENCO | 07-10-2025 09:00:00 | 10-10-2025 20:00:00 |  |  | OK THROUGH SUB LD All other lines at Koradi/Satpura to be in service with AR enabled. SLDC MH/MP to be informed
46 |  | 265220 |  | SATPURA - 400KV - BUS 1 |  | WR-OCCM | For replacemnet of Bus-1 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400KV-SATPURA-KORADI-1 is required) | 07-10-2025 09:00:00 | 10-10-2025 20:00:00 |  |  | OK THROUGH SUB LD All elements to be in service with bus-2. In case of N-1, all elements will be out. No other element shall be effected. Load to be managed by SLDC MP