## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-07
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-03 12:03 | MR2510/0056 | Daily | 220KV_220 kV Adampur-Hoshangabad line | 220KV_ADAMPUR | NON-OCCM-MP | Defective Disc replacement work | 04-10-2025 09:00:00 | 14-10-2025 17:00:00 | Ankit Mehroliya | 9425804506 | ok, through sub ld
2 | 2025-10-06 14:38 | MR2510/0139 |  | 33KV_33 KV Main bus | 132KV_AMARPATAN | NON-OCCM-MP | jumpering work of 33 KV station Xmer | 07-10-2025 09:00:00 | 07-10-2025 11:00:00 | Arun Kumar | 9131207339 | o&m consent required
3 | 2025-10-06 13:46 | MR2510/0132 |  | 220KV_220/33kv 50mva xmer 2nd bbl | 220KV_BADNAGAR | OCCM-MP | For Post maintenance and testing | 07-10-2025 10:00:00 | 07-10-2025 17:00:00 | Poshkar kushwaha | 9425813990 | ok, through sub ld, o&m shall be informed
4 | 2025-10-02 14:20 | MR2510/0042 |  | 400KV_125 MVAR BUS REACTOR | 400KV_BADNAWAR | NON-OCCM-MP | Post Mansoon Maintenance & Testing work | 07-10-2025 08:00:00 | 07-10-2025 18:00:00 | Er Abhishek Verma | 9340855901 | ok, as per the voltage profile
5 | 2025-10-06 15:09 | MR2510/0141 |  | 132KV_20 MVA GEC_X-mer | 220KV_BETUL | NON-OCCM-MP | erection work of new 63 MVA TAL X-mer | 07-10-2025 09:00:00 | 07-10-2025 17:00:00 | Vishal Kumar Malviya | 9425804955 | sub ld
6 | 2025-10-06 13:49 | MR2510/0133 |  | 132KV_132 KV Bina-Khurai Ckt-2 | 220KV_BINA | NON-OCCM-MP | For line maintenance work. | 07-10-2025 10:00:00 | 07-10-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | ok
7 | 2025-10-06 15:44 | MR2510/0146 |  | 132KV_50 MVA bbl-make transformer | 132KV_BUDHERA | NON-OCCM-MP | Post mansoon maintenance | 07-10-2025 09:00:00 | 07-10-2025 15:00:00 | Pushpendra Kumar soni | 9425806398 | ok
8 | 2025-10-06 15:47 | MR2510/0148 |  | 132KV_132kv Tikamgarh-Budera 1st line | 132KV_BUDHERA | NON-OCCM-MP | Oil leakage attend of 132kv B-phase ct | 07-10-2025 15:00:00 | 07-10-2025 18:00:00 | Pushpendra kumar soni | 9425806398 | ok
9 | 2025-10-06 10:44 | MR2510/0125 |  | 132KV_132 kV Hatta â¿¿ Bijawar Line | 220KV_CHATARPUR | NON-OCCM-MP | Loose AH tightening & other line maintenance | 07-10-2025 11:00:00 | 07-10-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
10 | 2025-09-18 17:16 | MR2509/0453 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 06-10-2025 09:00:00 | 11-10-2025 18:00:00 | SHRI M. M. BAIG | 9425805067 | real time
11 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
12 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
13 | 2025-10-04 12:27 | MR2510/0086 | Daily | 220KV_220 KV Hoshangabad-Adampur | 220KV_HOSHANGABAD | NON-OCCM-MP | Resagging work b/w loc.no. 20 of lilo to 71 | 05-10-2025 09:00:00 | 10-10-2025 17:00:00 | Ashutosh Rai | 9425806902 | as opportunity s/d
14 | 2025-10-06 15:23 | MR2510/0143 |  | 220KV_220 kV Jabalpur- Birsinghpur ckt-II | 220KV_JABALPUR | NON-OCCM-MP | Disc Change at loc. C96 Top Ph | 07-10-2025 10:00:00 | 07-10-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
15 | 2025-10-06 14:55 | MR2510/0140 |  | 132KV_40 MVA Transformer-I Make EMCO | 132KV_JHABUA | NON-OCCM-MP | For Post Monsoon Maintenance work | 07-10-2025 10:00:00 | 07-10-2025 18:00:00 | Er.Varsingh Mohoniya | 9425803496 | sub ld
16 | 2025-10-06 13:26 | MR2510/0129 |  | 132KV_132/33 kv 50 MVA Tal X-mer | 132KV_KARAKBEL | NON-OCCM-MP | post monsoon maintenance work | 07-10-2025 10:30:00 | 07-10-2025 18:00:00 | Dinesh Kumar kushwaha | 9425801319 | o&m consent required
17 | 2025-09-18 12:55 | MR2509/0410 | Continuous | 400KV_400KV DAMOH - KATNI LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 06-10-2025 09:00:00 | 11-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deffered, not in WR list
18 | 2025-10-06 14:30 | MR2510/0137 |  | 132KV_40 MVA Xmer BBL | 132KV_MAJHGAWAN | NON-OCCM-MP | Attending hot point in Y phase | 07-10-2025 12:00:00 | 07-10-2025 15:00:00 | Ravi Pandey | 9425805229 | o&m consent required
19 | 2025-10-05 10:37 | MR2510/0101 | Daily | 132KV_132KV Neemuch Manasa Line | 132KV_MANASA | NON-OCCM-MP | Re sagging and line maintanence work | 06-10-2025 08:00:00 | 12-10-2025 18:00:00 | Gaurav goyal | 9425805120 | sub ld
20 | 2025-10-06 12:25 | MR2510/0128 |  | 132KV_132KV Nagda-Unhel Line | 220KV_NAGDA | NON-OCCM-MP | Disc Insulator replacement work | 07-10-2025 10:00:00 | 07-10-2025 18:00:00 | Kamal Solanki | 9425805262 | sub ld
21 | 2025-10-02 15:27 | MR2510/0050 | Continuous | 220KV_220/132 Kv 160MVA BHEL 3 X-mer | 220KV_NARSINGHPUR | NON-OCCM-MP | Replacement of CB,PI&Mainbus isolator erection | 03-10-2025 09:00:00 | 08-10-2025 17:00:00 | Dinesh Kumar Kushwaha | 9425182413 | Continuous
22 | 2025-10-06 15:26 | MR2510/0145 |  | 220KV_160 MVA Xmer-1 | 220KV_PIPARIYA | NON-OCCM-WR | For post moonson maintenance work | 07-10-2025 10:00:00 | 07-10-2025 17:00:00 | B K Jhariya | 9425806831 | ok, through sub ld
23 | 2025-10-02 10:44 | MR2510/0018 | Daily | 400KV_315 MVA ICT-II make-CGL | 400KV_PITHAMPUR4 | NON-OCCM-MP | Post monsoon maintenance & testing work. | 06-10-2025 10:00:00 | 07-10-2025 18:00:00 | Rajudas bairagi | 9425801532 | ok, through sub ld
24 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
25 | 2025-10-06 12:13 | MR2510/0127 |  | 220KV_220/132KV 160MVA BHEL X-Mer-I | 220KV_RATANGARH | NON-OCCM-WR | Post - monsoon maintenance work | 07-10-2025 10:00:00 | 07-10-2025 17:00:00 | S.H. Mansuri | 7587951068 | ok, through sub ld
26 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
27 | 2025-10-06 14:09 | MR2510/0136 |  | 220KV_220 kV Satna (MPPTCL) â¿¿ Kotar line | 220KV_SATNA | NON-OCCM-MP | Urgent disc replacement work at loc no 112 | 07-10-2025 11:00:00 | 07-10-2025 17:00:00 | Mr. R.K.Prajapati | 9407070182 | ok
28 | 2025-10-06 15:23 | MR2510/0144 |  | 132KV_132kV Sidhi - Mauganj Ckt - I | 220KV_SIDHI | NON-OCCM-MP | Line Maintenance Work. | 07-10-2025 09:30:00 | 07-10-2025 17:00:00 | G.L Sahu | 9425805102 | ok
29 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
30 |  | 265219 |  | 400KV-KORADI-SATPURA-1 | 400 | POWERGRID_WR2 | For replacemnet of Bus-1 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400kV Bus-1 is required at Sarni S/S of MPGENCO) And CVT Replacement of 400KV-SATPURA-KORADI-1 under ADD CAP at MPGENCO | 07-Oct-2025 | 09:00 | 10-Oct-2025 | 20:00 | ok
31 |  | 265220 |  | SATPURA - 400KV - BUS 1 | 400 | POWERGRID_WR2 | For replacemnet of Bus-1 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400KV-SATPURA-KORADI-1 is required) | 07-Oct-2025 | 09:00 | 10-Oct-2025 | 20:00 | ok
32 |  | 265318 |  | 400KV-BINA-MP-GUNA-MP-1 | 400 | POWERGRID_WR2 | AMP work. | 07-Oct-2025 | 09:00 | 07-Oct-2025 | 18:00 | Deffered in view of NHPTL TESTING
33 |  | 265944 |  | 220KV-BETUL-SARNI-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 07-Oct-2025 | 09:00 | 07-Oct-2025 | 17:00 | ok, through sub ld
34
35
36
37
38
39
40