## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-23 | APPROVED OUTAGE LIST FOR DATED 23.10.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-22 15:30 | MR2510/0525 |  | 132KV_33 KV Main bus | 132KV_AMARPATAN | NON-OCCM-MP | erection of radiator of 40 mva Telk Xmer | 23-10-2025 10:00:00 | 23-10-2025 14:00:00 | Arun Kumar | 9425426476 | o&m consent required
2 | 2025-10-22 15:18 | MR2510/0523 |  | 132KV_40 MVA BBL Xmer | 132KV_AMARPATAN | NON-OCCM-MP | for erection 40 MVA Telk Xmer | 23-10-2025 09:00:00 | 23-10-2025 17:00:00 | Arun Kumar | 9425426476 | o&m consent required
3 | 2025-10-22 15:02 | MR2510/0522 |  | 132KV_132 kV Anuppur-Shahdol line | 220KV_ANUPPUR | NON-OCCM-MP | F/o disc replacement & other line maintenance | 23-10-2025 10:00:00 | 23-10-2025 17:00:00 | Jitendra Tiwari | 9425805298 | ok
4 | 2025-10-22 12:35 | MR2510/0514 |  | 132KV_132kV Balaghat Baihar Line | 132KV_BALAGHAT | NON-OCCM-MP | Jumper Cone Tightening & PID Difective | 23-10-2025 10:00:00 | 23-10-2025 18:00:00 | S.K. BHALADHARE | 9425807264 | ok
5 | 2025-10-21 12:54 | MR2510/0500 | Continuous | 220KV_Transfer the Load of 220 kV Interconnector 2 line on Bus Transfer | 220KV_BHOPAL | NON-OCCM-WR | main CB of 220 kV Interconnector 2 line is not rel | 22-10-2025 17:00:00 | 24-10-2025 17:00:00 | A. K. Jain | 9425806899 | Continuous
6 | 2025-09-18 17:24 | MR2509/0455 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 22-10-2025 09:00:00 | 25-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deffered
7 | 2025-10-22 13:36 | MR2510/0518 |  | 220KV_200MVA 220/132KV T&R X-MER | 220KV_DAMOH | NON-OCCM-MP | Post Monsoon Maintenance & Testing work. | 23-10-2025 09:00:00 | 23-10-2025 18:00:00 | M.K.Choubey | 9425801424 | ok
8 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
9 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
10 | 2025-10-22 16:19 | MR2510/0527 |  | 220KV_220KV INDORE-BARNAGAR LINE | 400KV_INDORE4 | NON-OCCM-MP | POST MONSOON MAINTANANCE WORK | 23-10-2025 09:00:00 | 23-10-2025 17:00:00 | ATUL PARADKAR | 9425804929 | ok, through sub ld
11 | 2025-10-22 13:07 | MR2510/0515 |  | 50MVAR_BUS _Reactor | 400KV_JULWANIYA4 | NON-OCCM-MP | Post monsoon maintenance & testing work | 23-10-2025 10:00:00 | 23-10-2025 16:00:00 | ER. Ravindra Patil | 8305612190 | ok, through sub ld
12 | 2025-09-18 13:08 | MR2509/0413 | Continuous | 400KV_400KV DAMOH - KATNI LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 22-10-2025 09:00:00 | 25-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deffered
13 | 2025-10-22 15:32 | MR2510/0526 |  | 132KV_132 KV INTERCONNECTOR NO -2 Feeder | 132KV_NARSINGHPUR1 | NON-OCCM-MP | R Phase line side isoiator jaw clamp hot point att | 23-10-2025 11:00:00 | 23-10-2025 15:00:00 | Jayprakash Dharne | 7587951106 | real time
14 | 2025-10-21 20:31 | MR2510/0505 |  | 220KV_Bus A and Bus Coupler | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual Maintenance | 23-10-2025 09:30:00 | 23-10-2025 18:00:00 | Pankaj Sharma | 7898703187 | ok
15 | 2025-10-21 20:11 | MR2510/0504 | Daily | 220KV_OMKARESHWAR-NIMRANI-Tap-BARWAHA_Ckt | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual maintenance | 23-10-2025 09:30:00 | 25-10-2025 18:00:00 | Pankaj Sharma | 7898703187 | ok, through sub ld
16 | 2025-10-22 13:16 | MR2510/0517 |  | 132KV_40 MVA X-mer-III Make-IMP | 132KV_RAJGARH DHAR1 | NON-OCCM-MP | For Post monsoon maintenance work. | 23-10-2025 10:00:00 | 23-10-2025 18:00:00 | Er. Manoj Randha | 9425820034 | sub ld
17 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
18 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
19 | 2025-10-22 13:07 | MR2510/0516 |  | 132KV_132 kv Satna â¿¿Prism (Cement) line | 220KV_SATNA | NON-OCCM-MP | Damage conductor strength repaired work | 23-10-2025 11:00:00 | 23-10-2025 16:00:00 | Mr. R.K.Prajapati | 9407070182 | ok
20 | 2025-10-22 14:43 | MR2510/0520 |  | 220KV_220/132KV 160 MVA BBL X-mer | 220KV_SIRMOUR | OCCM-MP | Post Monsoon Maintenance & Testing Work | 23-10-2025 10:00:00 | 23-10-2025 17:00:00 | Shri Indrajeet Singh | 9424734033 | ok
21 | 2025-10-22 15:21 | MR2510/0524 |  | 220KV_160MVA TRANSFORMER-II | 220KV_SUWASRA2 | NON-OCCM-MP | POST MANSOON MAINTENANCE & TESTING WORK | 23-10-2025 10:00:00 | 23-10-2025 18:00:00 | SUNIL PAWAR | 9425804939 | ok, through sub ld
22 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
23 |  |  |  | 400KV/220KV SEONI-PG-ICT-1 | POWERGRID-WR1 (PGCIL) |  | For AMP Works@Seoni SS | 23-Oct-2025 | 09:00 | 23-Oct-2025 | 18:00 | ok
24 |  |  |  | 400KV/220KV SATNA-ICT-2 | POWERGRID-WR2 (PGCIL) |  | AMP Work, Dia to be kept open at both sides. | 23-Oct-2025 | 09:00 | 23-Oct-2025 | 18:00 | real time
25 |  |  |  | 400KV-BHOPAL-MP-BINA-MP-2 | MADHYA PRADESH |  | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 23-Oct-2025 | 09:00 | 23-Oct-2025 | 17:00 | real time
26 |  |  |  | 220KV-GWALIOR-MALANPUR-1 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 23-Oct-2025 | 09:00 | 23-Oct-2025 | 17:00 | real time