## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-13
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-12 13:39 | MR2510/0336 |  | 220KV_50 MVA Xmer | 220KV_ADAMPUR | NON-OCCM-MP | Post Monsoon Maintenance | 13-10-2025 09:00:00 | 13-10-2025 17:00:00 | K P Choudhary | 9425803214 | SUB LD
2 | 2025-10-12 13:45 | MR2510/0339 |  | 220KV_220 KV Adampur-Bhopal line bay | 220KV_ADAMPUR | NON-OCCM-MP | Bay Post Monsoon Maintenance | 13-10-2025 09:00:00 | 13-10-2025 17:00:00 | K P Choudhary | 9425802314 | DEFERRED DUE TO SD ON 220 KV ADAMPUR - HOSHANGABAD CKT
3 | 2025-10-03 11:54 | MR2510/0055 | Daily | 220KV_220 kV Adampur-Hoshangabd line | 220KV_ADAMPUR | NON-OCCM-MP | Defective disc replacement work | 04-10-2025 09:00:00 | 14-10-2025 17:00:00 | Ankit Mehroliya | 9425804506 | OK THROUGH SUB LD
4 | 2025-10-12 16:06 | MR2510/0346 |  | 132KV_132/33kv 40mva xmer bbl | 220KV_BADNAGAR | OCCM-MP | For Post maintenance and testing | 13-10-2025 10:00:00 | 13-10-2025 16:00:00 | Poshkar kushwaha | 9425813990 | SUB LD
5 | 2025-10-12 12:53 | MR2510/0331 |  | 220KV_220KV Main Bus Section-I | 220KV_BARWAHA | NON-OCCM-MP | for Hot point attending Work | 13-10-2025 09:00:00 | 13-10-2025 15:00:00 | Er.Imran Beg | 9425805200 | OK THROUGH SUB LD, 4 NO. 220 KV CKT WILL BE OUT OF SERVICE. MENTION SEPERATELY, APPROVED TIME FROM 10:00 TO 14:00 HRS.
6 | 2025-10-12 15:18 | MR2510/0345 |  | 220KV_160 MVA BBL_X-mer-2nd | 220KV_BETUL | NON-OCCM-MP | Post monsoon maintenance & Testing work | 13-10-2025 10:00:00 | 13-10-2025 17:00:00 | Vishal Kumar Malviya | 9425804955 | OK THROUGH SUB LD
7 | 2025-10-11 15:01 | MR2510/0317 |  | 40MVA_132/33KV_BHEL_X'mer | 132KV_BICHHUA | NON-OCCM-MP | POST MANSOON MAINTENANCE. | 13-10-2025 09:00:00 | 13-10-2025 17:00:00 | A A QURESHI | 9425804318 | OK O&M to be informed
8 | 2025-10-12 12:35 | MR2510/0330 |  | 400KV_400KV Guna-I 80MVAr(CGL) Line Reactor-I . | 400KV_BINA4 | NON-OCCM-MP | Post-monsoon maintenance & testing work. | 13-10-2025 10:00:00 | 13-10-2025 15:00:00 | Parmanand Namdeo | 7587951092 | OK
9 | 2025-10-12 14:21 | MR2510/0342 |  | 132KV_132 kV Birsinghpur-Umariya Circuit II | 220KV_BIRSINGHPUR | NON-OCCM-MP | F/o disc replacement & other line maintenance | 13-10-2025 10:00:00 | 13-10-2025 17:00:00 | Jitendra Tiwari | 9425805298 | OK
10 | 2025-09-18 17:20 | MR2509/0454 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 13-10-2025 09:00:00 | 18-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | DEFERRED
11 | 2025-10-12 13:43 | MR2510/0337 |  | 50MVA_132/33KV_BBL_Xmer | 132KV_DEOSAR | OCCM-MP | for relay testing work | 13-10-2025 12:00:00 | 13-10-2025 17:00:00 | R.B. Singh | 9907230394 | OK O&M TO BE INTIMATED
12 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | DEFERRED, DATA CONFIRMATION REQUIRED FROM COMMUNICATION
13 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | DEFERRED, DATA CONFIRMATION REQUIRED FROM COMMUNICATION
14 | 2025-10-10 11:49 | MR2510/0277 | Daily | 220KV_220 KV Hoshangabad-Adampur | 220KV_HOSHANGABAD | NON-OCCM-MP | Resagging work b/w loc.no. 78-94 | 11-10-2025 09:00:00 | 14-10-2025 17:00:00 | Ashutosh Rai | 9425806902 | OK AS OPPORTUNITY SD
15 | 2025-10-09 14:23 | MR2510/0256 |  | 220KV_220KN INDORE-SOUTH ZONE-3 LINE | 400KV_INDORE4 | NON-OCCM-MP | POST MONSOON MAINTANANCE WORK | 13-10-2025 09:00:00 | 13-10-2025 17:00:00 | ATUL PARADKAR | 9425804929 | DEFERRED DUE TO MULTIPLE OUTAGES IN INDORE AREA AT 220KV S/S BARWAHA
16 | 2025-10-11 13:04 | MR2510/0309 |  | 132KV_132/33 KV 50 MVA TAL X-MER | 132KV_KATANGI_JBP | NON-OCCM-MP | 132/33 KV 50 MVA TAL X-MER for Post mansoon maint | 13-10-2025 10:00:00 | 13-10-2025 17:00:00 | A.K. Pandey | 9424645081 | OK O&M TO BE INTIMATED
17 | 2025-09-18 13:00 | MR2509/0411 | Continuous | 400KV_400KV DAMOH - KATNI LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 13-10-2025 09:00:00 | 18-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | DEFERRED
18 | 2025-10-11 17:28 | MR2510/0323 |  | 220KV_220/132 KV 160 MVA BHEL 1st X Mer | 220KV_MAHALGAON | NON-OCCM-MP | Post Monsoon Maint. and Testing Work | 13-10-2025 10:00:00 | 13-10-2025 17:00:00 | P Datey | 9425805110 | OK THROUGH SUB LD
19 | 2025-10-12 13:02 | MR2510/0333 |  | 220KV_200 mva x-mer make cgl. | 220KV_MALANPUR | NON-OCCM-MP | post monsoon maintenance | 13-10-2025 10:00:00 | 13-10-2025 17:00:00 | VIKRAM AHIRWAR | 9425805415 | DEFERRED DUE TO SD ON 160MVA AT Mahalgaon
20 | 2025-10-12 13:30 | MR2510/0334 |  | 132KV_132/33 KV 50 MVA BBL | 132KV_MAUGANJ | NON-OCCM-MP | For post monsoon maintenance and testing work | 13-10-2025 10:00:00 | 13-10-2025 17:00:00 | Mr. Indrajeet Singh | 9424734033 | OK O&M TO BE INTIMATED
21 | 2025-10-12 14:27 | MR2510/0343 |  | 160MVA_220/132KV_BHEL_Xmer_2 | 220KV_MORENA | NON-OCCM-MP | Post monsoon maintenance work. | 13-10-2025 10:00:00 | 13-10-2025 18:00:00 | AMIT KUMAR DHANELIYA | 9425802242 | OK THROUGH SUB LD
22 | 2025-10-12 10:20 | MR2510/0324 |  | 400KV_315MVA ICT-3 transformer Make-BHEL | 400KV_NAGDA4 | NON-OCCM-MP | Post monsoon maintenance and testing work | 13-10-2025 09:00:00 | 13-10-2025 18:00:00 | Sunil Bamniya | 9425820045 | OK THROUGH SUB LD
23 | 2025-10-12 10:50 | MR2510/0326 |  | 132KV_132/33KV 40MVA X-mer-1 Make-BBL | 132KV_NAINPUR | NON-OCCM-MP | Post Monsoon Maintenance & testing work | 13-10-2025 10:30:00 | 13-10-2025 18:00:00 | Shri Sandeep Damahe | 9425805009 | OK O&M TO BE INTIMATED
24 | 2025-10-12 12:58 | MR2510/0332 |  | 220KV_160 Mva X-mer BHEL-2 | 220KV_NALKHEDA | NON-OCCM-WR | Post monsoon Xmer Testing and Mani. Work | 13-10-2025 09:00:00 | 13-10-2025 17:00:00 | VK Gupta | 9425801214 | OK THROUGH SUB LD
25 | 2025-10-10 19:08 | MR2510/0303 |  | 132KV_40 MVA X-MER MAKE BBL | 220KV_NARSINGHPUR | NON-OCCM-MP | Postmonsoon maintenance & testing work | 13-10-2025 10:00:00 | 13-10-2025 17:00:00 | Er K.K. Choure | 9425801357 | OK O&M TO BE INTIMATED
26 | 2025-10-11 10:39 | MR2510/0306 |  | 220KV_220/132KV 160MVA NGEF X-Mer-I | 220KV_NEEMUCH | NON-OCCM-WR | Post monsoon maintenance work | 13-10-2025 09:00:00 | 13-10-2025 17:00:00 | Vivek Mojasia | 9425806921 | OK THROUGH SUB LD
27 | 2025-10-09 14:25 | MR2510/0258 |  | 220KV_220KV Rajgarh I/C- 1 line | 400KV_RAJGARH-PG | OCCM-WR | line maintinance work | 13-10-2025 08:00:00 | 13-10-2025 18:00:00 | V.R.Panadia | 8120516165 | OK THROUGH SUB LD
28 | 2025-10-12 13:38 | MR2510/0335 |  | 132KV_132KV Rajmilan-Janakpur ckt | 132KV_RAJMILAN | NON-OCCM-MP | Disc replacement work | 13-10-2025 08:00:00 | 13-10-2025 17:00:00 | G.L SAHU | 9425805102 | OK, Janakpur supply to be maintained through Anuppur
29 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | DEFERRED
30 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | DEFERRED
31 | 2025-10-12 16:28 | MR2510/0347 |  | 132KV_50MVA BHEL X-MER | 132KV_REWA-II (SAGRA) | NON-OCCM-MP | PENTING WORK | 13-10-2025 10:00:00 | 13-10-2025 18:00:00 | Er. KANISHK SINGH | 9425804656 | OK O&M TO BE INTIMATED
32 | 2025-10-11 15:06 | MR2510/0318 |  | 220KV_100 MVA XMER AREVA | 400KV_SAGAR | OCCM-WR | POST MONSOON MAINTENENCE WORK | 13-10-2025 09:30:00 | 13-10-2025 17:30:00 | SRAJAN SISODIYA | 7879960164 | OK
33 | 2025-10-12 11:48 | MR2510/0328 |  | 220KV_160MVA X-mer BBL | 220KV_SENDHWA2 | NON-OCCM-MP | Post monsoon maintenance & testing work | 13-10-2025 09:30:00 | 13-10-2025 17:30:00 | ER. Kashiram Khanna | 9826732087 | OK THROUGH SUB LD
34 | 2025-10-12 11:01 | MR2510/0327 |  | 220KV_160 MVA transformer no 2ND BHEL | 220KV_SHIVPURI | NON-OCCM-MP | for Post monsoon maintenance and testing work | 13-10-2025 09:00:00 | 13-10-2025 14:00:00 | ROHIT KUMAR YADAV | 9425804921 | OK THROUGH SUB LD
35 | 2025-10-11 14:12 | MR2510/0312 |  | 400KV_400/220KV ICT-2 for PMU commissioning work by MPPTCL | 400KV_SINGHAJI TPS | NON-OCCM-MP | PMU commissioning work | 13-10-2025 10:00:00 | 13-10-2025 18:00:00 | Deepak Sharma | 8005696855 | OK SUB LD TO BE INTIMATED
36 | 2025-10-12 14:10 | MR2510/0340 |  | 220KV_220KV UJJAIN HATHUNIYA CKT 1 | 220KV_UJJAIN | OCCM-WR | LINE MAINTENANE | 13-10-2025 09:00:00 | 13-10-2025 18:00:00 | K SACHINDRA | 9425805295 | OK
37 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | OK, FTC TO BE SUBMITTED
38 | 2025-10-12 10:33 | MR2510/0325 |  | 220KV_220 KV Interconnector-IV | 400KV_UJJAIN4 | NON-OCCM-MP | Postmonsoon bay maintenance work | 13-10-2025 10:00:00 | 13-10-2025 17:00:00 | Santosh Chavrasia | 9425804677 | DEFERRED DUE TO SD ON 220 KV INDORE - UJJAIN CKT
39 |  |  |  | 63 MVA BBL TRASFORMER | 220 KV JABALPUR |  | POST MONSOON MAINTENENCE WORK AND OIL LEAKAGE WORK | 03-09-2025 09:00:00 | 13-10-2025 18:00:00 |  |  | OK
40 |  |  |  | 400KV CHHEGAON – MALWA – I Ckt. | 400 KV CHHEGAON |  | For DTPC Wiring Work. | 13-10-2025 10:00:00 | 13-10-2025 18:00:00 |  |  | REAL TIME
41 |  | 269551 |  | MAIN BAY - 220KV-KHANDWA-CHHANERA-2 AND KHANDWA - 220KV - BUS 1 at KHANDWA - 220KV | 220 | POWERGRID_WR2 | AMP work | 13-Oct-2025 | 09:00 | 13-Oct-2025 | 18:00 | OK
42 |  | 265215 |  | 400KV-ITARSI-INDORE-MP-1 | 400 | POWERGRID_WR2 | Retrofitting of Old Electromechanical Differential Relay with New ABB make Relay of Line Reactor & CT Oil Sampling works.Dia to be kept open at both ends. | 13-Oct-2025 | 09:00 | 13-Oct-2025 | 20:00 | OK THROUGH SUB LD
43 |  | 265188 |  | 220KV-SHUJALPUR-RAJGARH-MP-1 | 220 | POWERGRID_WR2 | AMP WORK OF LINE BAY 203 L | 13-Oct-2025 | 08:00 | 13-Oct-2025 | 17:30 | OK THROUGH SUB LD
44 |  | 265931 |  | 400KV/220KV JABALPUR-ICT-2 | 400KV/220KV | MP_SLDC | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 13-Oct-2025 | 09:00 | 14-Oct-2025 | 17:00 | REAL TIME
45 |  | 265953 |  | 220KV-GWALIOR-MAHALGAON-1 | 220 | MP_SLDC | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 13-Oct-2025 | 09:00 | 13-Oct-2025 | 17:00 | OK THROUGH SUB LD
46 |  | 265954 |  | 220KV-INDORE-UJJAIN-1 | 220 | MP_SLDC | FOR BAY MAINTENANCE & TESTING WORK AT UJJAIN SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 13-Oct-2025 | 09:00 | 13-Oct-2025 | 18:00 | OK THROUGH SUB LD
47 |  | 265955 |  | 220KV-SEONI-MP-SEONI-PG-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 13-Oct-2025 | 09:00 | 13-Oct-2025 | 18:00 | OK , LOADING ON 132KV BALAGHAT - KIRNAPUR CKT - 1 & 2 SHOULD BE MONITORED.
48 |  | 265956 |  | 220KV-RAJGARH-RAJGARH-MP-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 13-Oct-2025 | 08:00 | 13-Oct-2025 | 18:00 | OK THROUGH SUB LD
49
50
51