## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-23
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-09-22 14:52 | MR2509/0563 |  | 132KV_132kv Bilpank - Badnagar line | 220KV_BADNAGAR | NON-OCCM-MP | For line maintenance work | 23-09-2025 10:00:00 | 23-09-2025 18:00:00 | Kumar Vishal | 9425805018 | sub ld
2 | 2025-09-22 16:23 | MR2509/0570 |  | 220KV_220KV Badnawar-Ratlam 1st | 400KV_BADNAWAR | NON-OCCM-MP | Installation of 2nd DPR and testing work | 23-09-2025 10:00:00 | 23-09-2025 17:00:00 | Er. Abhishek Verma | 9340855901 | ok, through sub ld
3 | 2025-09-22 10:01 | MR2509/0531 |  | 132KV_132KV Barwaha-Chhotikhargone DP line | 220KV_BARWAHA | NON-OCCM-MP | Replacement of Flashover Disc | 23-09-2025 10:00:00 | 23-09-2025 18:00:00 | Naresh Pandre | 9425806905 | sub ld
4 | 2025-09-15 14:04 | MR2509/0337 | Continuous | 400KV_315 MVA X-MER NO.3 (BHEL) | 400KV_BHOPAL4 | NON-OCCM-MP | POSTTMONSOON MAINTENENCE | 22-09-2025 09:00:00 | 23-09-2025 18:00:00 | AKRAM KAHN | 9425804695 | Deffered, due to s/d on Ashta ICT
5 | 2025-09-22 14:28 | MR2509/0558 |  | 132KV_40 MVA BBL | 132KV_BIJAWAR | NON-OCCM-MP | for post Monsoon maintenance & Testing | 23-09-2025 14:00:00 | 23-09-2025 18:00:00 | Brajendra Soni | 9131327770 | ok
6 | 2025-09-22 14:24 | MR2509/0555 |  | 132KV_50 MVA BBL Transformer | 132KV_BIJAWAR | NON-OCCM-MP | for Post Monsoon Maintenance & Testing | 23-09-2025 09:00:00 | 23-09-2025 14:00:00 | Brajendra Soni | 9131327770 | ok
7 | 2025-09-20 14:29 | MR2509/0503 | Daily | 132KV_132 kV Shahdol-Birsinghpur Circuit I | 220KV_BIRSINGHPUR | NON-OCCM-MP | For replacement of damaged OPGW | 21-09-2025 09:00:00 | 27-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
8 | 2025-09-22 15:06 | MR2509/0564 |  | 132KV_63 MVA Transformer No 3 BBL | 132KV_CHAMBAL | NON-OCCM-WR | post mansoon maintenance | 23-09-2025 09:00:00 | 23-09-2025 12:00:00 | A. K. jain | 9425806899 | sub ld
9 | 2025-09-22 15:15 | MR2509/0565 |  | 63MVA_132/33KV_ABB_X'mer_2 | 132KV_CHAMBAL | NON-OCCM-WR | post mansoon maintenance | 23-09-2025 12:00:00 | 23-09-2025 17:00:00 | A. K. Jain | 9425806899 | sub ld
10 | 2025-09-22 10:57 | MR2509/0534 | Daily | 315MVA_400/220KV_CGL_X'mer_1 | 400KV_CHHEGAON4 | NON-OCCM-MP | POST MANSOON MAINT. WORK | 23-09-2025 10:00:00 | 24-09-2025 18:00:00 | SHRI GANESH MANSARE | 9425802441 | ok, through sub ld
11 | 2025-09-20 18:35 | MR2509/0513 | Daily | 220KV_220KV DAMOH - DAMOH IC IIIRD CKT | 220KV_DAMOH | OCCM-MP | FOR OPGW INSTALLATION WORK | 23-09-2025 07:00:00 | 30-09-2025 19:00:00 | M.M. BAIG | 9425805067 | Deffered, not in WRPC OCC approval list
12 | 2025-09-20 14:29 | MR2509/0504 | Daily | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | For replacement of damaged OPGW | 21-09-2025 09:00:00 | 27-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
13 | 2025-09-22 13:02 | MR2509/0547 |  | 160MVA_220/132KV_BHEL_X'mer_2 | 220KV_GWALIOR-II | NON-OCCM-MP | POST MONSOON MAINTENANCE | 23-09-2025 11:00:00 | 23-09-2025 17:00:00 | R. C. ARORA | 9425805108 | ok, through sub ld
14 | 2025-09-22 13:05 | MR2509/0548 |  | 220KV_220KV BUS COUPLER | 220KV_GWALIOR-II | NON-OCCM-MP | SAFTEY PURPOSE | 23-09-2025 11:00:00 | 23-09-2025 17:00:00 | R. C. ARORA | 9425805108 | ok, through sub ld
15 | 2025-09-07 13:02 | MR2509/0161 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-2 | 220KV_INDORE NORTH | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
16 | 2025-09-07 12:51 | MR2509/0159 | Daily | 132KV_132KV North Zone- Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
17 | 2025-09-22 16:03 | MR2509/0569 |  | 220KV_160 MVA TRANSFORMER -II BHEL | 220KV_INDORE-II (JETPURA) | NON-OCCM-WR | POST MONSOON MAINT. WORK | 23-09-2025 10:00:00 | 23-09-2025 17:00:00 | DEEPAK GUPTA | 9425803845 | Deffered, due to s/d on Ujjain x-mer
18 | 2025-09-07 12:45 | MR2509/0158 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
19 | 2025-09-02 18:32 | MR2509/0063 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1& ckt-2 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | RESCHEDULED FRO 11.09.2025 TO 30.09.2025
20 | 2025-09-18 17:36 | MR2509/0457 | Continuous | 400KV_315MVA ICT-2 | 400KV_INDORE4 | NON-OCCM-MP | Post monsoon mainteance | 22-09-2025 09:00:00 | 23-09-2025 17:00:00 | atul paradkar | 9425804929 | Continuous
21 | 2025-09-22 11:09 | MR2509/0535 |  | 220KV_220/132/33KV 160MVA X-MER No.-2 | 220KV_ITARSI | NON-OCCM-MP | Post Monsoon Maintanence & Testing work. | 23-09-2025 09:00:00 | 23-09-2025 17:00:00 | J.D.Khoria | 9425804975 | real time
22 | 2025-09-20 15:16 | MR2509/0506 | Continuous | 132KV_132 kv katni sleemnabad ckt 2 | 132KV_KATNI | NON-OCCM-MP | Modification work | 21-09-2025 09:00:00 | 23-09-2025 18:00:00 | pankaj yadav | 9406713326 | EI aprpoval required
23 | 2025-09-22 15:42 | MR2509/0567 |  | 132KV_50 MVA BHEL X-Mer | 132KV_KHURAI | NON-OCCM-MP | Post monsoon Maintenance work | 23-09-2025 10:00:00 | 23-09-2025 17:00:00 | bhupendra khawse | 9425806471 | ok
24 | 2025-09-20 11:19 | MR2509/0495 | Daily | 132KV_132kV Balaghat Kirnapur Ckt-Ist | 400KV_KIRNAPUR | NON-OCCM-MP | Re-sagging of section Loc 465 to 478 & 529 to 547 | 21-09-2025 09:00:00 | 23-09-2025 17:00:00 | Shridhar Kumar Bhaladhare | 9425448642 | ok, 132kv Balaghat-Baihar ckt and 132kv Waraseoni-Katangi ckt to be opened for load management
25 | 2025-09-15 16:59 | MR2509/0358 |  | 220KV_220 kv Satna (PGCIL) â¿¿ Kotar line | 220KV_KOTAR | NON-OCCM-MP | Line maintenance work | 23-09-2025 10:00:00 | 23-09-2025 17:00:00 | Mr.R.K. Prajapati | 9407070182 | Deffered, not in WRPC OCC approval list
26 | 2025-09-07 12:39 | MR2509/0157 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line. | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
27 | 2025-09-07 12:57 | MR2509/0160 | Daily | 132KV_132KV Niranjanpur - Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
28 | 2025-09-02 18:36 | MR2509/0064 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line.&132KV Niranjanpur - Jaitpura Line &132KV North Zone- Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
29 | 2025-09-19 15:56 | MR2509/0485 |  | 400KV_400kV Main bus-II | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tightening, Greasing,cleaning & Isolator alignment | 23-09-2025 10:00:00 | 23-09-2025 18:00:00 | Sh. Rajudash bairagi | 9425801532 | Deffered, due to s/d on 220KV Pithampur sec-3-Pithampur (400) I/C ckt-1, 2
30 | 2025-09-22 11:38 | MR2509/0538 |  | 220KV_220KV Pithampur sec-3-Pithampur (400) I/C ckt-2 line. | 400KV_PITHAMPUR4 | NON-OCCM-MP | Safety purpose | 23-09-2025 09:00:00 | 23-09-2025 18:00:00 | RAJENDRA KANOJE | 9425801348 | shall be allowed only 4 hrs, real time after 10hrs, laoding on other ckts of pithampur to be monitored, through sub ld
31 | 2025-09-22 11:36 | MR2509/0537 |  | 220KV_220KV Pithampur sec-3-Pithampur (400) I/C ckt- 1 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Safety purpose | 23-09-2025 09:00:00 | 23-09-2025 18:00:00 | RAJENDRA KANOJE | 9425801348
32 | 2025-09-22 15:41 | MR2509/0566 |  | 132KV_40 MVA X-mer-I (Make- GEC ALSTHOM ) | 132KV_RAJGARH DHAR1 | NON-OCCM-MP | Post monsoon maintenance work. | 23-09-2025 10:00:00 | 23-09-2025 18:00:00 | Er. Manoj Randha | 9425820034 | sub ld
33 | 2025-09-22 14:14 | MR2509/0553 |  | 132KV_40MVA XMER-2 BBL | 132KV_REWA1 | NON-OCCM-MP | Post monsoon maintenance and testing work | 23-09-2025 10:00:00 | 23-09-2025 18:00:00 | Kanishka Singh | 9425804656 | ok
34 | 2025-09-22 12:50 | MR2509/0545 |  | 220KV_220KV DAMOH-SAGAR 2nd Ckt. Line(PGCIL) | 400KV_SAGAR | OCCM-MP | Line maintenance work | 23-09-2025 09:00:00 | 23-09-2025 18:00:00 | J.P. Asati | 9424445533 | ok
35 | 2025-09-20 18:32 | MR2509/0512 | Daily | 220KV_220KV DAMOH - SAGAR PGCIL IIND CKT. | 400KV_SAGAR | OCCM-MP | FOR OPGW INSTALLATION WORK | 23-09-2025 07:00:00 | 30-09-2025 19:00:00 | M.M. BAIG | 9425805067 | Deffered, not in WRPC OCC approval list
36 | 2025-09-22 14:30 | MR2509/0561 |  | 220KV_50MVA 220/33 BBLx-mer | 400KV_SAGAR | NON-OCCM-MP | POST MONSOON MAINTENANC | 23-09-2025 10:00:00 | 23-09-2025 17:00:00 | srajan sisodiya | 7879960164 | ok, o&m shall be informed
37 | 2025-09-22 12:21 | MR2509/0543 |  | 132KV_132/33kv, 50 MVA X-MER-II nd (BBL) | 132KV_SAILANA | NON-OCCM-MP | For post monsoon maintenance & testing work. | 23-09-2025 09:00:00 | 23-09-2025 18:00:00 | MAHESH PATIDAR | 9977504423 | sub ld
38 | 2025-09-21 13:02 | MR2509/0524 |  | 132KV_132/33KV 50 MVA X-MER-2 MAKE -BHEL | 132KV_SEONI1 | NON-OCCM-MP | POST MONSOON MAINTANACE WORK | 23-09-2025 08:00:00 | 23-09-2025 17:00:00 | Shri C.S.Sanodiya | 9009798506 | o&m consent required
39 | 2025-09-22 14:28 | MR2509/0559 |  | 220KV_220kv 160mva x-mer 1st emco | 220KV_SHIVPURI | NON-OCCM-MP | 160 MVA transformer no 1st EMCO from 11:00 hrs. To | 23-09-2025 11:00:00 | 23-09-2025 17:00:00 | AE ROHIT KUMAR YADAV | 8120064160 | ok, through sub ld
40 | 2025-09-22 14:43 | MR2509/0562 |  | 132KV_132 Shrinagar-Narsinghpur DP Line | 132KV_SHRINAGAR | NON-OCCM-MP | Flashover disc replacement work at Loc. No. 305/B | 23-09-2025 10:00:00 | 23-09-2025 18:00:00 | Ashish Kumar | 9425805935 | T&C and Discom to be initmated
41 | 2025-09-22 13:49 | MR2509/0550 |  | 220KV_160 MVA X-MER 1st BHEL | 220KV_SHUJALPUR | NON-OCCM-MP | Post mansoon maintenance and testing work | 23-09-2025 09:00:00 | 23-09-2025 18:00:00 | N.N. Verma | 7587951076 | ok, through sub ld
42 | 2025-09-22 10:02 | MR2509/0532 |  | 220KV_220 KV Nipaniya - Suwasara line | 220KV_SUWASRA2 | NON-OCCM-MP | Flashover disc Insulator replce.& other Line work | 23-09-2025 10:00:00 | 23-09-2025 17:00:00 | Ravindra Kumar Marskole | 9425814080 | ok, through sub ld
43 | 2025-09-22 13:49 | MR2509/0552 |  | 220KV_220kV Tikamgarh-Damoh (MPPTCL) Line | 220KV_TIKAMGARH | NON-OCCM-MP | AH, VD Tightening & other line maintenance work | 23-09-2025 10:00:00 | 23-09-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
44 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
45 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | RAJESH TIWARI | 7898239595 | Completed
46 | 2025-09-22 16:03 | MR2509/0568 |  | 33KV_33kV HALF MAIN BUS | 132KV_WAIDHAN | OCCM-MP | Replacement of dameged conductor on 33kv Waidhan & | 23-09-2025 09:00:00 | 23-09-2025 14:00:00 | R.B. Singh | 9907230394 | o&m consent required
47 | 2025-09-22 16:03 |  |  | 160MVA_220/132KV_BBL_X'mer_ | 220KV S/S SITPURA | NON-OCCM | PMM | 2025-09-23 10:00 | 2025-09-23 17:00 | A.E SATNA 220KV
48 | 2025-09-22 16:03 |  |  | 400KV-KORADI-SATPURA-1 | POWERGRID-WR1 (PGCIL) |  | For CT Replacement of 400KV-SATPURA-KORADI-1 under ADD CAP at MPGENCO, Dia to be kept open at both ends. | 23-Sep-2025 | 09:00 |  |  | Ok.400kV KORADI-BHUSAWAL-T1 Sensitivity of 23.00% and All other lines at Koradi - 400KV and SATPURA - 400KV to be in service with A/R Enabled
49 | 2025-09-22 16:03 |  |  | 400KV-KORBA-NTPC-BIRSINGPUR-1 | POWERGRID-WR1 (PGCIL) |  | AMP Work of of Line terminal equipment & Associated LR and its BAY | 23-Sep-2025 | 08:00 |  |  | Ok.400kV BIRSINGPUR -BALCO-T1 Sensitivity of 36.62% and All other lines at KORBA-NTPC - 400KV and BIRSINGPUR - 400KV to be in service with A/R Enabled
50 | 2025-09-22 16:03 |  |  | 400KV-BADNAWAR-RAJGARH-1 | POWERGRID-WR2 (PGCIL),MADHYA PRADESH |  | For Attending Hotspot in Line Isolator of Line Bay, Non auto mode of ckt 2 is required . Dia to be kept open at both ends. | 23-Sep-2025 | 10:00 |  |  | Ok.400kV RAJGARH-PG -BADNAWAR-MP -T2 Sensitivity of 55.03% and All other lines at Badnawar - 400KV and RAJGARH - 400KV to be in service with A/R Enabled
51 | 2025-09-22 16:03 |  |  | 400KV-BHOPAL-MP-ITARSI-1 | MADHYA PRADESH |  | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 23-Sep-2025 | 09:00 |  |  | Real time,400kV BHOPAL-MP -ITARSI-PG -T2 Sensitivity of 49.51% and All other lines at BHOPAL-MP - 400KV and ITARSI - 400KV to be in service with A/R Enabled. Load to be managed by SLDC MP.
52 | 2025-09-22 16:03 |  |  | 220KV-GWALIOR-MAHALGAON-3 | MADHYA PRADESH |  | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 23-Sep-2025 | 09:00 |  |  | Real time, All other 220KV lines to be in service at Gwalior/Mahalgaon with A/R enabled. No other element shall be effected. Load to be managed by SLDC MP.
53 | 2025-09-22 16:03 |  |  | 220KV-KHANDWA-CHHEGAON-1 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 23-Sep-2025 | 08:00 |  |  | Real time, ckt-1 to be in service. Load to be managed by SLDC MP. WR2 to be informed.
54 | 2025-09-22 16:03 |  |  | 220KV-DAMOH-SAGAR-2 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 23-Sep-2025 | 09:00 |  |  | ok, All other 220KV lines to be in service at Sagar with A/R enabled. No other element shall be effected. WR-2 to be informed. Load to be managed by SLDC MP.
55 | 2025-09-22 16:03 |  |  | 220KV-ANNUPUR-KOTMIKALA-1 | MADHYA PRADESH,CHATTISGARH |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 23-Sep-2025 | 09:00 |  |  | Real time, All other lines at Annuppur/Kotmikala to be in service with AR enabled. Load to be managed by SLDC MP/CG
56 | 2025-09-22 16:03 |  |  | 220KV-INDORE-INDORE NORTH ZONE-1 | MADHYA PRADESH |  | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO | 23-Sep-2025 | 07:00 |  |  | ok, A/R in N/A, Line will be in service.
57 | 2025-09-22 16:03 |  |  | 220KV-INDORE-INDORE NORTH ZONE-2 | MADHYA PRADESH |  | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO | 23-Sep-2025 | 07:00 |  |  | ok, A/R in N/A, Line will be in service.