## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-26
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-25 16:05 | MR2510/0586 |  | 132KV_63 mva and 40 mva Xmer | 132KV_AMARPATAN | NON-OCCM-MP | replacement of 132 KV CT of 40mva Xmer | 26-10-2025 08:00:00 | 26-10-2025 11:00:00 | Arun Kumar | 9131207339 | OK ONLY IF O&M CONSENT PROVIDED
2 | 2025-10-25 15:01 | MR2510/0585 |  | 400KV_315 MVA ICT 2nd MAKE -T&R | 400KV_BADNAWAR | NON-OCCM-MP | POST MANS | 26-10-2025 09:00:00 | 26-10-2025 18:00:00 | Er . ABHISHEK VERMA | 9340855901 | REAL TIME
3 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | DATA CONFIRMATION REQUIRED FROM COMMUNICATION
4 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | DATA CONFIRMATION REQUIRED FROM COMMUNICATION
5 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | DATA CONFIRMATION REQUIRED FROM COMMUNICATION
6 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | DATA CONFIRMATION REQUIRED FROM COMMUNICATION
7 | 2025-10-25 14:12 | MR2510/0583 |  | 220KV_160 MVA X-MER Ist | 220KV_SHEOPUR KALAN2 | NON-OCCM-MP | post monsoon maintenance & RELAY testing work at 2 | 26-10-2025 10:00:00 | 26-10-2025 17:00:00 | I.A.KHAN | 6264419968 | OK THROUGH SUB LD
8 | 2025-10-25 10:33 | MR2510/0577 |  | 132KV_220KV Shivpuri Karahal line | 220KV_SHIVPURI | NON-OCCM-MP | LINE Maintenance work | 26-10-2025 10:00:00 | 26-10-2025 17:00:00 | SURAJ PAWAR | 9425814079 | SUB LD
9 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | OK, FTC TO BE SUBMITTED
10 | 2025-10-22 16:42 | MR2510/0528 |  | 132KV_132 KV MAIN BUS | 220KV_UJJAIN | NON-OCCM-MP | To replace 02 nos. damaged bus section Isolators | 26-10-2025 10:00:00 | 26-10-2025 15:00:00 | B.C JOSHI | 7587951137 | SUB LD-OK FOR 160MVA X'MER AFTER LOAD MANAGEMENT.
11 | 2025-10-22 16:42 | MR2510/0528 |  | 400KV-SATPURA-ITARSI-1 | POWERGRID-WR2 (PGCIL) | Approved | For replacemnet of Bus-2 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400kV Bus-1 is required at Sarni S/S of MPGENCO) And CT Replacement of 400KV-SATPURA-ITARSI-1 under ADD CAP at MPGENCO | 25.10.25 | 28.10.25 |  |  | CONTINUE, Ok.400kV SATPURA-INDIRASAGAR-T1 Sensitivity of 34.00% and All other lines at SATPURA - 400KV and ITARSI - 400KV to be in service with A/R Enabled
S/I SLDC JABALPUR