## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-20 | APPROVED OUTAGE LIST FOR DATED 20.09.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-09-19 12:49 | MR2509/0462 |  | 400KV_315 MVA X-MER NO.3 MAKE TOSHIBA | 400KV_ASHTA4 | NON-OCCM-MP | TAN DELTA & CAPACITANCE MESUREMENT OF CTS | 20-09-2025 09:00:00 | 20-09-2025 15:00:00 | JITENDRA LOHANA | 9425804978 | ok, through sub ld
2 | 2025-09-19 12:53 | MR2509/0463 |  | 220KV_220 KV BUS TIE | 400KV_ASHTA4 | NON-OCCM-MP | TAN DELTA & CAPACITANCE MESUREMENT OF CTS | 20-09-2025 12:00:00 | 20-09-2025 15:00:00 | JITENDRA LOHANA | 9425804978 | ok, through sub ld
3 | 2025-09-19 14:03 | MR2509/0475 |  | 220KV_220 KV Bina-Sagar Ckt-2 | 400KV_BINA4 | NON-OCCM-MP | For line maintenance work. | 20-09-2025 09:00:00 | 20-09-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | ok
4 | 2025-09-14 13:00 | MR2509/0312 | Daily | 132KV_132 kV Shahdol-Birsinghpur Circuit I | 220KV_BIRSINGHPUR | NON-OCCM-MP | For replacement of damaged OPGW | 15-09-2025 08:00:00 | 20-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
5 | 2025-09-19 13:21 | MR2509/0465 |  | 132KV_63 MVA BBL Transformer | 220KV_CHATARPUR | NON-OCCM-MP | for post monsoon maint & Testing | 20-09-2025 10:00:00 | 20-09-2025 14:00:00 | Brajendra Soni | 9131327770 | ok
6 | 2025-09-19 15:47 | MR2509/0482 |  | 160MVA_220/132KV_BBL_X'mer_2 | 400KV_CHHEGAON4 | NON-OCCM-MP | Post monsoon maintenance | 20-09-2025 10:00:00 | 20-09-2025 18:00:00 | Ganesh Mansare | 9425802441 | ok
7 | 2025-09-14 13:01 | MR2509/0313 | Daily | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | For replacement of damaged OPGW | 15-09-2025 08:00:00 | 20-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
8 | 2025-09-19 16:38 | MR2509/0488 |  | 160MVA_220/132KV_BHEL_X'mer_1 | 220KV_GWALIOR-II | NON-OCCM-MP | POSTMONSOON MAINTENANCE | 20-09-2025 11:00:00 | 20-09-2025 17:00:00 | R. C. ARORA | 9425805108 | ok, through sub ld
9 | 2025-09-19 16:51 | MR2509/0492 |  | 220KV_220KV BUS COUPLER | 220KV_GWALIOR-II | NON-OCCM-MP | SAFTEY PURPOSE | 20-09-2025 11:00:00 | 20-09-2025 17:00:00 | R. C. ARORA | 9425805108 | ok, through sub ld
10 | 2025-09-07 13:02 | MR2509/0161 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-2 | 220KV_INDORE NORTH | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
11 | 2025-09-07 12:51 | MR2509/0159 | Daily | 132KV_132KV North Zone- Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
12 | 2025-09-07 12:45 | MR2509/0158 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
13 | 2025-09-19 15:15 | MR2509/0479 | Continuous | 132KV_132 kv katni sleemnabad 2 | 132KV_KATNI | NON-OCCM-MP | Modification work | 20-09-2025 09:00:00 | 21-09-2025 18:00:00 | PANKAJ YADAV | 9406713326 | ok, EI approval required while charging
14 | 2025-09-19 13:35 | MR2509/0466 |  | 132KV_132/33KV 50MVA BHEL X-MER | 132KV_KATRA | OCCM-MP | Y&B Phase LV CT damage jumper maintenance | 20-09-2025 08:00:00 | 20-09-2025 10:00:00 | IJ Singh | 9424734033 | ok
15 | 2025-09-19 14:25 | MR2509/0477 |  | 132KV_132/33KV_40MVA XMER(BBL) | 132KV_KHIMLASA | NON-OCCM-MP | POST MONSOON MAINTENACE | 20-09-2025 09:00:00 | 20-09-2025 17:00:00 | PARMANAND NAMDEO | 7587951092 | sub ld
16 | 2025-09-07 12:39 | MR2509/0157 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line. | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
17 | 2025-09-07 12:57 | MR2509/0160 | Daily | 132KV_132KV Niranjanpur - Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
18 | 2025-09-02 18:36 | MR2509/0064 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line.&132KV Niranjanpur - Jaitpura Line &132KV North Zone- Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
19 | 2025-09-19 16:58 | MR2509/0493 |  | 132KV_132KV PATERA - AMANGANJ JK CEMENT LINE | 132KV_PATERA | NON-OCCM-MP | NEW MODIFIED TOWERS AND RELEASE THE ERS | 20-09-2025 09:00:00 | 20-09-2025 17:00:00 | M.M. BAIG | 9425805067 | ok, Electrical Inspector charging approval required while charging
20 | 2025-09-19 10:44 | MR2509/0461 |  | 132KV_132 kV Prithvipur - Jatara line | 132KV_PRITHVIPUR | NON-OCCM-MP | Emergency Tree Cutting & other line maintenance | 20-09-2025 10:00:00 | 20-09-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
21 | 2025-09-19 16:42 | MR2509/0490 |  | 132KV_132 KV Main Bus | 132KV_RAGHOGARH | NON-OCCM-MP | for 132 Gail Feeder Jumpering work | 20-09-2025 11:00:00 | 20-09-2025 15:00:00 | Sagar Singh Dhakad | 9589205697 | sub ld
22 | 2025-09-19 16:19 | MR2509/0487 |  | 132KV_50 MVA X-mer-I (Make- TAL ) | 220KV_RAJGARH DHAR | NON-OCCM-MP | Post monsoon maintenance work. | 20-09-2025 10:00:00 | 20-09-2025 18:00:00 | Er. Manoj Randha | 9425820034 | sub ld
23 | 2025-09-19 14:30 | MR2509/0478 |  | 132KV_Shutdown on 63MVA BBL X-MER | 132KV_SALEEMNABAD | NON-OCCM-MP | post monsoon maintence | 20-09-2025 10:00:00 | 20-09-2025 17:00:00 | Abhishek Mishra | 9425801440 | ok
24 | 2025-09-19 14:12 | MR2509/0476 |  | 132KV_132 KV Shahpura-Shrinagar DP Line | 132KV_SHAHPURA | NON-OCCM-MP | Flashover Disc replacement work at loc.No.170/B-Ph | 20-09-2025 10:00:00 | 20-09-2025 18:00:00 | Ashish Kumar | 9425805935 | ok
25 | 2025-09-19 16:04 | MR2509/0486 |  | 132KV_132kV Sidhi - Deosar Ckt - I | 220KV_SIDHI | NON-OCCM-MP | Line maintenance work. | 20-09-2025 09:30:00 | 20-09-2025 17:00:00 | G.L Sahu | 9425805102 | ok, o&m to be informed
26 | 2025-09-16 18:41 | MR2509/0369 | Continuous | 132KV_132 KV ASHTA- SONKACHH | 132KV_SONKATCH | NON-OCCM-MP | in above work of lilo formation of ehv line for co | 18-09-2025 09:00:00 | 20-09-2025 17:00:00 | A.R.KANEL | 9425805217 | sub ld
27 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
28 | 2025-09-19 15:56 | MR2509/0484 |  | 132KV_50 MVA X-MER TAL | 132KV_UNCHEHRA | NON-OCCM-MP | For Post Monsoon Maintenance And Testing Work. | 20-09-2025 10:00:00 | 20-09-2025 17:00:00 | Arun Kumar | 9425802368 | ok
29 | 2025-09-19 15:30 | MR2509/0480 |  | 220KV_160MVA X-MER-II BHEL | 220KV_VIDISHA | OCCM-MP | POST MONSOON MAINTENANCE WORK | 20-09-2025 09:00:00 | 20-09-2025 18:00:00 | KC GOSWAMI | 9425804976 | ok, through sub ld
30 | 2025-09-19 15:36 | MR2509/0481 |  | 132KV_63MVA X-MER-I BBL | 220KV_VIDISHA | OCCM-MP | POST MONSOON MAINTENANCE WORK | 20-09-2025 09:00:00 | 20-09-2025 18:00:00 | KC GOSWAMI | 9425804976 | sub ld
31 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | RAJESH TIWARI | 7898239595 | CONTINUE
|  |  |  | 400KV/220KV SHUJALPUR-ICT-1 |  |  | AMP WORKS OF 315MVA,400/220kV ICT-I AT SHUJALPUR, DIA TO BE KEPT OPEN AT BOTH SIDES. | 20-Sep-2025 | 08:00 | 20-Sep-2025 | 17:30 | ok
|  |  |  | 220KV-INDORE-INDORE NORTH ZONE-1 |  |  | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO | 20-Sep-2025 | 07:00 | 20-Sep-2025 | 23:59
|  |  |  | 220KV-INDORE-INDORE NORTH ZONE-2 |  |  | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO | 20-Sep-2025 | 07:00 | 20-Sep-2025 | 19:59
S/I SLDC JABALPUR