## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-20 |  |  | 2025-08-20
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-19 14:49 | MR2508/0250 | Daily | 220KV_220 kV Anuppur- Kotmikala ckt-I | 220KV_ANUPPUR | NON-OCCM-MP | Re sagging work at loc. 418-432 | 20-08-2025 08:00:00 | 21-08-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
2 | 2025-08-18 13:44 | MR2508/0226 |  | 220KV_220 kV Khandwa (PGCIL) - Chhegaon Ckt-2nd | 400KV_CHHEGAON4 | OCCM-MP | For Line Maintenance Work | 20-08-2025 08:00:00 | 20-08-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, through sub ld
3 | 2025-08-19 12:33 | MR2508/0242 |  | 220KV_220 kV Seoni Chhindwara Ckt-II | 220KV_CHHINDWARA | OCCM-MP | V/D Provide work & J/c, A/h, V/d tightening | 20-08-2025 09:00:00 | 20-08-2025 17:00:00 | A.M.Shende | 7587951136 | ok
4 | 2025-08-19 12:00 | MR2508/0240 |  | 132KV_132 KV Garoth - Suwasara line | 132KV_GAROTH | NON-OCCM-MP | flash-over disc replacement and other line work | 20-08-2025 10:00:00 | 20-08-2025 17:00:00 | Ravindra Kumar Marskole | 9425814080 | sub ld
5 | 2025-08-12 17:20 | MR2508/0174 | Daily | 220KV_220KV South Zone (Indore) â¿¿ Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | . Replacement existing of 24 Fibre OPGW by 48 Fibr | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
6 | 2025-08-19 12:41 | MR2508/0245 |  | 220KV_JBP SUKHA NO.2 | 220KV_JABALPUR | NON-OCCM-MP | OLD CVT REPLACEMENT WORK | 20-08-2025 10:00:00 | 20-08-2025 17:00:00 | DN PODDAR | 9425805034 | real time
7 | 2025-06-30 15:24 | MR2506/0624 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 18-08-2025 09:00:00 | 23-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
8 | 2025-06-30 16:09 | MR2506/0633 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 18-08-2025 09:00:00 | 23-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
9 | 2025-08-19 14:47 | MR2508/0249 |  | 220KV_220 KV Main Bus-1st | 400KV_MANDSOUR4 | NON-OCCM-MP | jampar work | 20-08-2025 10:00:00 | 20-08-2025 18:00:00 | J.P. Parmar | 9425806919 | ok, through sub ld
10 | 2025-08-12 17:23 | MR2508/0175 | Daily | 220KV_220KV Mangliya -Jaitpura Line. | 220KV_MANGLIA2 | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
11 | 2025-07-22 16:42 | MR2507/0344 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Installation of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | sub ld
12 | 2025-07-22 16:47 | MR2507/0345 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installatin of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
13 | 2025-08-19 11:14 | MR2508/0239 |  | 220KV_Panagar- Amarkantak line | 220KV_PANAGAR | NON-OCCM-MP | Relay testing work | 20-08-2025 10:00:00 | 20-08-2025 17:00:00 | H L koshta | 7587951105 | ok
14 | 2025-08-14 17:22 | MR2508/0187 |  | 400KV_400KV Pithampur-PGCIL ckt-II | 400KV_PITHAMPUR4 | NON-OCCM-MP | CTsTan-Delta Testing & Bay Maintenance work | 20-08-2025 11:00:00 | 20-08-2025 18:00:00 | Rajudas Bairagi | 9425801532 | Deffered, not in WRPC approval list
15 | 2025-08-19 14:45 | MR2508/0248 |  | 400KV_400KV Pithampur-badnawar ckt-II | 400KV_PITHAMPUR4 | NON-OCCM-WR | CT Tan Delta Measurement | 20-08-2025 11:00:00 | 20-08-2025 18:00:00 | Rajudas bairagi | 9425801532 | ok, through sub ld
16 | 2025-08-19 14:34 | MR2508/0247 | Continuous | 132KV_132 kv REWA-MANGWAN CKT-2 | 220KV_REWA | NON-OCCM-MP | FEEDER PANEL SHIFTING WORK | 20-08-2025 10:00:00 | 21-08-2025 18:00:00 | KANISK SINGH | 9425804656 | ok
17 | 2025-08-14 18:24 | MR2508/0188 | Continuous | 400KV_400 kv main bus 1 | 400KV_SAGAR | NON-OCCM-MP | FOR EXTENSION OF MAIN BUS 1 | 20-08-2025 08:00:00 | 21-08-2025 17:00:00 | ANIL KUMAR MAHORE | 7747087295 | Deffered, not in WRPC approval list
18 | 2025-08-17 16:26 | MR2508/0215 | Continuous | 400KV_315 MVA, 400KV/220KV, Interconnecting Transformer- 2 | 400KV_SINGHAJI TPS | NON-OCCM-MP | Overhauling work | 18-08-2025 09:00:00 | 23-08-2025 18:00:00 | Yogesh Chouhan | 7999328631 | Continuous
19 | 2025-08-19 12:40 | MR2508/0243 |  | 132KV_132 kV Tikamgarh - Diguada Ckt. IInd Line | 220KV_TIKAMGARH | NON-OCCM-MP | JCT checking & other line maintenance work | 20-08-2025 10:00:00 | 20-08-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
20 |  | 256278 |  | NHPTL-TESTING-@-NHPTL - 400KV at BINA-NHPTL - 400KV |  | WR-OCCM | SC TESTING | 20-08-2025 09:00:00 | 20-08-2025 18:00:00 |  |  | Ok all the instructions of WRLDC to be passed to jp bina & MP Bina for bupassing , JP Bina/SLDC MP to be informed. JP Bina mentioned that "Consent may be given provided that the said arrangement at Bina 400 KV Sub Station is done during light load hours i.e. from 09:00 hours to 11:00 hours". A separate mail done for sequence of operation and bypass arrangement details.
21 |  | 256747 |  | 132KV-MANSAR-MS-PENCH-1 |  | WR-OCCM | For routine maintenance work | 20-08-2025 09:00:00 | 20-08-2025 18:00:00 |  |  | Ok, Load to be managed by MSLDC /SLDC MP.
22 |  | 259811 |  | 220KV-SEONI-MP-SEONI-PG-1 |  | WR-OCCM | LINE BAY AMP WORK AT SEONI SS// Rescheduled form 01.08.2025 | 20-08-2025 09:00:00 | 20-08-2025 18:00:00 |  |  | ok All other lines at Seoni-MP to be in service. Wr1 to be informed. Load to be managed by SLDC MP. MPSLDC to be informed
23 |  | 258551 |  | 400KV-KORBA-NTPC-BIRSINGPUR-1 |  | WR-OCCM | AMP Work of of Line terminal equipment & Associated LR and its BAY.Dia to be kept open at both ends. | 20-08-2025 08:00:00 | 20-08-2025 20:00:00 |  |  | Ok. Ckt-2(Bypassed at Balco) Sensitivity of 31% and all other lines at Birsingpur to be in service with AR Enabled.NTPC/SLDC MP to be informed
24 |  | 256986 |  | 220KV-INDORE-UJJAIN-2 |  | WR-OCCM | FOR BAY MAINTENANCE & TESTING WORK AT 400KV S/S UJJAIN | 20-08-2025 09:00:00 | 20-08-2025 18:00:00 |  |  | real time All other lines at Ujjain to be in service. Wr2 to be informed, Load to be managed by SLDC MP
25 |  | 256987 |  | 220KV-SEONI-PG-CHINDWARA-2 |  | WR-OCCM | FOR LINE MAINTENANCE WORK | 20-08-2025 09:00:00 | 20-08-2025 18:00:00 |  |  | ok All other lines at Chindwara to be in service with AR enabled. No other element shall be effected. care to be taken. WR-1 to be informed
26 |  | 256988 |  | 220KV-KHANDWA-CHHEGAON-2 |  | WR-OCCM | FOR LINE MAINTENANCE WORK | 20-08-2025 08:00:00 | 20-08-2025 18:00:00 |  |  | OK THROUGH SUB LD All other lines at Chhegaon to be in service with AR enabled. No other element shall be effected. WR2 to be informed. Load to be managed by SLDC MP
27 |  | 256989 |  | 220KV-RAJGARH-RAJGARH-MP-1 |  | WR-OCCM | FOR LINE MAINTENANCE WORK | 20-08-2025 08:00:00 | 20-08-2025 18:00:00 |  |  | REAL TIME Ckt-2 (Sensitivity-93%) to be in service with Ar enabled.Load to be managed by SLDC MP. Outage shall be facilitated if flow on each ckt less than 130 MW/Ckt
28 |  | 262184 |  | 220KV-ANNUPUR-KOTMIKALA-1 |  | WR-OCCM | for resagging work between loc 418-432 | 20-08-2025 08:00:00 | 20-08-2025 17:59:00 |  |  | OK All other lines at Annuppur/Kotmikala to be in service. SLDC CG to be informed. Load to be managed by SLDC CG/MP
29 |  | 259214 |  | 132KV-DHARNI-NEPANAGAR-1 |  | WR-OCCM | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 20-08-2025 07:00:00 | 20-08-2025 18:59:00 |  |  | OK A/R in NA, Line to be in service