## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-13 |  |  | APPROVED OUTAGE LIST FOR DTD. 13.08.25
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-11 10:24 | MR2508/0137 |  | 132KV_Regarding Shutdown Required on 132 KV Mandla-Bichhiya line Ckt-1 &132 KV Mandla-Bichhiya line Ckt-2 (idealy charge up to dead end tower) for feeder bay shifting work at 132KV Sub Bichhiya | 132KV_BICHHIYA | NON-OCCM-MP | For feeder bay shifting work at 132KV S/s Bichhiya | 13-08-2025 08:00:00 | 13-08-2025 12:00:00 | Vijay Kumar Tandekar | 9425805095 | ok
2 | 2025-08-11 14:24 | MR2508/0143 | Continuous | 132KV_132kv 50mva bbl-make transformer | 132KV_DIGODA | NON-OCCM-MP | Air, cell of main-conservator tank charged by bbl | 12-08-2025 10:00:00 | 13-08-2025 07:00:00 | Pushpendra kumar soni | 9425806398 | Continuous
3 | 2025-08-12 14:02 | MR2508/0162 |  | 132KV_132KV HATTA-BIJAWAR LINE | 132KV_HATTA | NON-OCCM-MP | Line maintenance work | 13-08-2025 09:00:00 | 13-08-2025 18:00:00 | J.P. Asati | 9424445533 | ok
4 | 2025-08-10 13:51 | MR2508/0131 | Daily | 220KV_220KV South Zone - Jaitpura Line. | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre | 11-08-2025 07:00:00 | 13-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
5 | 2025-08-12 13:00 | MR2508/0160 |  | 220KV_220KV Itarsi PGCIL NO.-1 Load Transfer on 220KV TBC | 220KV_ITARSI | OCCM-WR | Line Differential relay testing & commi. work. | 13-08-2025 10:00:00 | 13-08-2025 17:00:00 | J.D.Khoria | 9425804975 | ok, line to be in service through TBC
6 | 2025-06-30 15:17 | MR2506/0623 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 11-08-2025 09:00:00 | 16-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
7 | 2025-06-30 16:06 | MR2506/0632 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 11-08-2025 09:00:00 | 16-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
8 | 2025-08-12 14:40 | MR2508/0165 |  | 400KV_400 KV Bhilai line and 400 KV Main Bus -2 | 400KV_KIRNAPUR | OCCM-MP | For hot point attend of Y phase panto isolator of | 13-08-2025 09:00:00 | 13-08-2025 18:00:00 | D. S. Walkey | 9425804578 | as opportunity s/d
9 | 2025-08-11 13:58 | MR2508/0138 |  | 400KV_400 KV Kirnapur - Bhilai Line | 400KV_KIRNAPUR | OCCM-MP | Suspension Clamp Tightening & other Maint. Work | 13-08-2025 09:00:00 | 13-08-2025 18:00:00 | S.K. Bhaladhare | 9425807264 | ok
10 | 2025-08-11 18:00 | MR2508/0157 |  | 132KV_132kV Mandla-Bichhiya Line | 132KV_MANDLA | NON-OCCM-MP | Jumper Cone Tightening & Other Maint. Work | 13-08-2025 08:00:00 | 13-08-2025 12:00:00 | S.K. BHALADHARE | 9425807264 | as opportunity s/d
11 | 2025-08-10 13:46 | MR2508/0130 | Daily | 220KV_220KV Indore (400KV) â¿¿ Mangliya Line | 220KV_MANGLIA2 | NON-OCCM-MP | 24 Fibre OPGW by 48 Fibre OPGW work | 11-08-2025 07:00:00 | 13-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
12 | 2025-08-12 14:10 | MR2508/0163 |  | 220KV_220kv Nagda-Nagra Ckt-I Line | 400KV_NAGDA4 | NON-OCCM-MP | Defective disc insulator replacement work. | 13-08-2025 10:00:00 | 13-08-2025 18:00:00 | Kamal Solanki | 9425805262 | ok, through sub ld
13 | 2025-07-22 16:42 | MR2507/0344 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Installation of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | sub ld
14 | 2025-07-22 16:47 | MR2507/0345 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installatin of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
15 | 2025-08-12 13:06 | MR2508/0161 |  | 220KV_220 kV Khandwa - Nepa | 220KV_NEPANAGAR | OCCM-MP | Other Line Maintenance work | 13-08-2025 08:00:00 | 13-08-2025 18:00:00 | C.H.Namdev | 9425802377 | real time
16 | 2025-08-12 15:53 | MR2508/0171 |  | 132KV_132Kv half main Bus | 220KV_PANDHURNA | NON-OCCM-MP | Jumpering work | 13-08-2025 10:00:00 | 13-08-2025 14:00:00 | Sanjay shende | 9425811447 | ok, through sub ld
17 | 2025-08-12 14:23 | MR2508/0164 |  | 220KV_220KV INTER CONNECTOR-II LINE | 220KV_PITHAMPUR (SEC-III) | NON-OCCM-MP | 220 KV CT TEN DELTA TESTING | 13-08-2025 10:00:00 | 13-08-2025 14:00:00 | R.D.BAIRAGI | 9425801532 | ok, through sub ld
18 | 2025-08-12 16:08 | MR2508/0172 |  | 220KV_Rajgarh-Clean wind power(Khiledi) DCSS line | 220KV_RAJGARH DHAR | NON-OCCM-MP | for Y phase pilot disc insulator replacement work | 13-08-2025 11:00:00 | 13-08-2025 16:00:00 | V.R.Panadia | 9425802330 | ok, through sub ld
19 | 2025-08-10 17:45 | MR2508/0134 | Continuous | 132KV_132KV RAJMILAN-JANAKPUR (CGPTCL) CKT | 132KV_RAJMILAN | NON-OCCM-MP | Tower Erection work | 11-08-2025 08:00:00 | 16-08-2025 18:00:00 | G.L SAHU | 9425805102 | Continuous
20 | 2025-08-10 17:51 | MR2508/0135 | Continuous | 132KV_132KV Rajmilan-Dongrital ckt | 132KV_RAJMILAN | NON-OCCM-MP | Tower Erection work | 11-08-2025 08:00:00 | 16-08-2025 18:00:00 | G.L SAHU | 9425805102 | Continuous
21 | 2025-08-05 12:05 | MR2508/0051 | Continuous | 400KV_400 kv MAIN BUS-2 | 400KV_SAGAR | OCCM-MP | FOR EXT OF MAIN BUS-2 AND PANTO ISO ERECTIONIO | 13-08-2025 09:00:00 | 14-08-2025 17:00:00 | ANIL MAHOR | 9425805149 | ok, WRLDC code required
22 | 2025-08-08 19:36 | MR2508/0122 | Continuous | 400KV_50 MVA Station Transformer #11 | 400KV_SATPURA TPS | NON-OCCM-MP | For testing of transformer, bay equipment & P Rela | 11-08-2025 09:00:00 | 14-08-2025 18:00:00 | YASHWANT WARATHE | 9752778063 | Continuous
23 | 2025-08-07 13:20 | MR2508/0107 | Continuous | 400KV_500 MVA, 400/220 kV ICT | 400KV_SGTPS | NON-OCCM-MP | Testing of NR, DCRM of Bkr, CT testing, aircell re | 08-08-2025 08:00:00 | 14-08-2025 19:00:00 | Pramod Mishra | 8989973149 | Continuous
24 | 2025-08-08 16:06 | MR2508/0121 | Continuous | 400KV_63MVA, 400/11&6.6 kV Station Trf-5B | 400KV_SGTPS | NON-OCCM-MP | Relay testing,DCRM of Bkr, CT testing, Aircell rep | 09-08-2025 09:00:00 | 14-08-2025 19:00:00 | Pramod Mishra | 8989973149 | Continuous
25 | 2025-08-12 15:39 | MR2508/0169 |  | 132KV_132kV Sidhi - Mauganj Ckt - I | 220KV_SIDHI | NON-OCCM-MP | OPGW STRING WORK | 13-08-2025 09:00:00 | 13-08-2025 17:00:00 | G.L Sahu | 9425805102 | ok
26 | 2025-08-12 15:05 | MR2508/0166 |  | 220KV_220/132 Kv 160 MVA IMP | 220KV_SIRMOUR | NON-OCCM-MP | For NIFPS installation work | 13-08-2025 10:00:00 | 13-08-2025 13:00:00 | Mr. Indrajeet Singh | 9424734033 | ok
27 | 2025-08-08 15:04 | MR2508/0119 |  | 400KV_400 KV UJJAIN -INDORE PGCIL CKT IIND | 400KV_UJJAIN4 | OCCM-WR | BAY MAINTENANCE AND TESTING WORK | 13-08-2025 09:00:00 | 13-08-2025 18:00:00 | SANTOSH CHAVRASIA | 9425804677 | ok, through sub ld
28 | 2025-08-12 15:28 | MR2508/0168 |  | 400KV_400KV Ujjain Hathuniya PGCIL ckt 1 | 400KV_UJJAIN4 | OCCM-WR | Line maintenance | 13-08-2025 11:00:00 | 13-08-2025 17:00:00 | K Sachindra | 7415651054 | as opportunity s/d
29 | 2025-08-12 15:28 |  |  | ITARSI - 220KV - BUS 1 |  | OCCM-WR | COE Compliance | 13-Aug-2025 | 09:00 | 13-Aug-2025 | 20:00 | ok
30 | 2025-08-12 15:28 |  |  | 400KV-KORBA-NTPC-BIRSINGPUR-1 |  | OCCM-WR | ATTENDING S/D NATURE DEFECTS IN LINE, Dia to be kept open. | 13-Aug-2025 | 07:00 | 13-Aug-2025 | 18:00 | ok
31 | 2025-08-12 15:28 |  |  | 220KV-KHANDWA-NEPANAGAR-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 13-Aug-2025 | 08:00 | 13-Aug-2025 | 18:00 | ok, through sub ld
32 | 2025-08-12 15:28 |  |  | 220KV-GWALIOR-MAHALGAON-1 |  | OCCM-WR | FOR BAY MAINTENANCE & TESTING WORK | 13-Aug-2025 | 09:00 | 13-Aug-2025 | 17:00 | real time
33 | 2025-08-12 15:28 |  |  | 220KV-SEONI-MP-SEONI-PG-2 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 13-Aug-2025 | 09:00 | 13-Aug-2025 | 18:00 | real time
34 | 2025-08-12 15:28 |  |  | SAGAR - 400KV - BUS 2 |  | OCCM-WR | for bus extension work and erection of pantograph isolator for installation of new 125 MVAR bus reactor | 13-Aug-2025 | 08:00 | 14-Aug-2025 | 16:59 | ok
35 | 2025-08-12 15:28 |  |  | 400KV-INDORE-UJJAIN-2 |  | OCCM-WR | FOR BAY MAINTENANCE & TESTING WORK AT 400KV S/S UJJAIN | 13-Aug-2025 | 09:00 | 13-Aug-2025 | 18:00 | ok, through sub ld
36 | 2025-08-12 15:28 |  |  | 400KV-KIRNAPUR-BHILAI-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 13-Aug-2025 | 09:00 | 13-Aug-2025 | 18:00 | ok
37 | 2025-08-12 15:28 |  |  | 400KV-INDORE-PITHAMPUR-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 13-Aug-2025 | 08:00 | 13-Aug-2025 | 18:00 | real time
S/I, SLDC MPPTCL JABALPUR