## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-22 |  |  | APPROVED OUTAGE LIST FOR DTD.22.07.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-07-18 11:19 | MR2507/0249 |  | 220KV_220KV BAIRAGARH BHOPAL CKT NO. II | 220KV_BAIRAGARH | NON-OCCM-MP | REPLACEMENT OF DAMEGE CONDUCTOR | 22-07-2025 09:30:00 | 22-07-2025 18:00:00 | AMBARISH SHRIPAD JOSHI | 7587951085 | Deffered by site
2 | 2025-07-21 16:10 | MR2507/0306 |  | 220KV_220 KV omkareshwar-Nimrani Tap barwaha Line | 220KV_BARWAHA | NON-OCCM-MP | Removal of metal sheet from loc no 23-24 | 22-07-2025 09:00:00 | 22-07-2025 12:00:00 | Naresh Pandre | 9425806905 | ok, through sub ld
3 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
4 | 2025-07-21 15:25 | MR2507/0302 |  | 132KV_20 MVA GEC_X-mer | 220KV_BETUL | NON-OCCM-MP | Transformer deairing work | 22-07-2025 11:00:00 | 22-07-2025 13:00:00 | Vishal Kumar Malviya | 9425804955 | sub ld
5 | 2025-07-21 13:21 | MR2507/0295 |  | 220KV_220 kV Birsinghpur TPS-Birsinghpur IC I | 220KV_BIRSINGHPUR | NON-OCCM-MP | F/o disc stringing replacement & other line maint. | 22-07-2025 10:00:00 | 22-07-2025 17:00:00 | Jitendra Tiwari | 9425805298 | ok
6 | 2025-07-21 13:41 | MR2507/0296 |  | 220KV_220kV Chhatarpur-Ajaygarh (TBCB) Ckt. 1st Line | 220KV_CHATARPUR | NON-OCCM-MP | Missing/Slip VD Attending & other Line maint. Work | 22-07-2025 10:00:00 | 22-07-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
7 | 2025-07-21 14:32 | MR2507/0299 |  | 220KV_220 KV BUS-TIE | 220KV_CHICHLI | NON-OCCM-MP | CT Testing work | 22-07-2025 11:00:00 | 22-07-2025 17:00:00 | Rajesh chaturvedi | 9425805203 | ok
8 | 2025-07-21 15:31 | MR2507/0303 |  | 132KV_132kV Dabra - Simariyatal Line | 132KV_DABRA | NON-OCCM-MP | ABT meter testing Railway | 22-07-2025 12:00:00 | 22-07-2025 16:00:00 | Pankaj Kumar | 9425805317 | sub ld
9 | 2025-07-21 11:26 | MR2507/0288 |  | 132KV_40 mva x-mer IInd BHEL | 220KV_GUNA | NON-OCCM-MP | for 132 kv ct replacement work | 22-07-2025 10:00:00 | 22-07-2025 17:00:00 | sagar singh dhakad | 9589205697 | sub ld
10 | 2025-07-21 12:43 | MR2507/0292 |  | 132KV_63MVA X-mer No.I | 132KV_HARDA | NON-OCCM-MP | 33 KV Incoming No.I CB timing work | 22-07-2025 10:00:00 | 22-07-2025 12:00:00 | Sh.J.D.Khoria | 9425804975 | sub ld
11 | 2025-07-21 12:25 | MR2507/0289 |  | 132KV_132 KV ITARSI-PIPARIYA | 220KV_ITARSI | NON-OCCM-MP | F/O DISC REPLACEMENT WORK | 22-07-2025 10:00:00 | 22-07-2025 18:00:00 | Ashutosh Rai | 9425806902 | sub ld
12 | 2025-07-21 14:48 | MR2507/0300 |  | 132KV_132 KV Karera Dabra line | 132KV_KARERA | NON-OCCM-MP | Flash over disc replacement work and other line ma | 22-07-2025 10:00:00 | 22-07-2025 17:00:00 | Satish Kumar Bhagat | 9425806916 | sub ld
13 | 2025-06-30 14:52 | MR2506/0617 | Continuous | 400KV_400KV KATNI-DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 21-07-2025 09:00:00 | 26-07-2025 18:00:00 | SHRI PANKAJ YADAV | 9406713326 | Deffered, not in WR list
14 | 2025-06-30 15:42 | MR2506/0629 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 21-07-2025 09:00:00 | 26-07-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
15 | 2025-07-18 16:14 | MR2507/0262 | Continuous | 132KV_132 KV Khurai- Sagar Ckt | 132KV_KHURAI | NON-OCCM-MP | For modification of 132 Khurai-sagar line | 18-07-2025 07:00:00 | 27-07-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | Continuous
16 | 2025-07-21 12:28 | MR2507/0291 | Continuous | 220KV_220 KV Main Bus-1st | 400KV_MANDSOUR4 | NON-OCCM-MP | Stringing work of 220 KV Yard | 22-07-2025 09:00:00 | 24-07-2025 18:00:00 | J.P. Parmar | 9425806919 | ok, through sub ld
17 | 2025-07-21 13:07 | MR2507/0294 |  | 132KV_132KV Nagda-Mahidpur Ckt-I Line | 220KV_NAGDA | NON-OCCM-MP | Disc Insulator replacement work | 22-07-2025 09:00:00 | 22-07-2025 18:00:00 | Kamal Solanki | 9425805262 | sub ld
18 | 2025-07-21 15:15 | MR2507/0301 |  | 400KV_Nagda-Mandsour ckt-1 | 400KV_NAGDA4 | NON-OCCM-MP | FOTE cable connection work | 22-07-2025 10:00:00 | 22-07-2025 15:00:00 | Sunil Bamniya | 9425820045 | please confirm, whether telemetry will be available/out during the s/d period, if under outage then ensure its re-routing
19 | 2025-07-21 12:55 | MR2507/0293 |  | 40MVA_132/33KV_EMCO_X'mer_1 | 132KV_NAGOD | NON-OCCM-MP | L V Neutral damage pad clamp replacement for | 22-07-2025 10:00:00 | 22-07-2025 12:00:00 | Shriv- Ravi Prakash Pandey | 9425805296 | ok
20 | 2025-07-21 16:02 | MR2507/0305 |  | 220KV_220 KV Narsinghpur-Pipariya line | 220KV_NARSINGHPUR | NON-OCCM-MP | Flashover disc replacement workat loc.No.03/R-Phas | 22-07-2025 10:00:00 | 22-07-2025 18:00:00 | Ashish Kumar | 9425805935 | Deffered, due to bus tie s/d in Chichali
21 | 2025-07-05 17:07 | MR2507/0079 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Insatallation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
22 | 2025-07-05 16:59 | MR2507/0078 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) LIne | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, if approved in WRLDC RC-1
23 | 2025-07-11 16:44 | MR2507/0157 | Daily | 220KV_Omkareshwar-Khandwa Line (Line#5) | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual Maintenance | 21-07-2025 09:00:00 | 23-07-2025 18:00:00 | PANKAJ SHARMA | 7898703187 | Deffered, due to high OSP generation
24 | 2025-07-11 16:49 | MR2507/0158 |  | 220KV_Main BUSâ¿¿A and Bus Coupler | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual Maintenance | 22-07-2025 09:00:00 | 22-07-2025 18:00:00 | PANKAJ SHARMA | 7898703187 | Deffered, due to high OSP generation
25 | 2025-07-21 15:57 | MR2507/0304 |  | 132KV_132KV RAJMILAN-BARGAWAN(TBCB) CKT | 132KV_RAJMILAN | NON-OCCM-MP | DISC FLASH OVER REPLACEMENT | 22-07-2025 11:00:00 | 22-07-2025 16:00:00 | G.L SAHU | 9425805102 | ok
26 | 2025-07-21 14:16 | MR2507/0298 |  | 220KV_160 MVA X-MER (BHEL)-1st | 220KV_RATLAM | NON-OCCM-MP | Pre monsoon maintenance and Ten Delta Testing work | 22-07-2025 09:00:00 | 22-07-2025 17:00:00 | NIKHIL DUNGE | 9425801487 | ok, through sub ld
27 | 2025-07-17 15:12 | MR2507/0243 | Continuous | 400KV_400 KV MAIN BUS-1 | 400KV_SAGAR | OCCM-MP | FOR EXTENSION OF 400 KV MAIN BUS-1 | 22-07-2025 08:00:00 | 23-07-2025 17:00:00 | ANIL MAHOR | 9425805149 | ok, WRLDC code to be taken
28 | 2025-07-19 17:13 | MR2507/0270 | Daily | 132KV_132kV Seoni Nainpur Ckt-IInd | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section 31-37 | 22-07-2025 09:00:00 | 26-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
29 | 2025-07-19 17:15 | MR2507/0271 | Daily | 132KV_132kV Seoni Keolari Line | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section 31-37 | 22-07-2025 09:00:00 | 26-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
30 | 2025-07-01 16:46 | MR2507/0017 |  | 400KV_400KV Singaji-Pithampura feeder-2 | 400KV_SINGHAJI TPS | NON-OCCM-MP | Relay testing work of Pithampura-2 during AOH | 22-07-2025 10:00:00 | 22-07-2025 19:00:00 | Deepak Sharma | 8005696855 | ok, through sub ld
31 | 2025-07-21 14:14 | MR2507/0297 |  | 220KV_220/132 Kv 160 MVA IMP | 220KV_SIRMOUR | NON-OCCM-MP | For NIFPS installation work by M/s CTR Pune | 22-07-2025 10:00:00 | 22-07-2025 18:00:00 | Mr. Indrajeet Singh | 9424734033 | ok
32 | 2025-07-21 14:14 |  |  | SAGAR - 400KV - BUS 1 |  |  | for bus extension work and errection of pantograph isolator for installation of new 125MVAR bus reactor | 22-Jul-2025 | 08:00 | 23-Jul-2025 | 16:59 | ok
33 | 2025-07-21 14:14 |  |  | 400KV/132KV VINDHYACHAL-ICT-3 |  |  | Annual Bay Maintenance and Testing/ Relay testing | 22-Jul-2025 | 08:00 | 31-Jul-2025 | 18:00 | ok
34 | 2025-07-21 14:14 |  |  | 400KV-BHOPAL-MP-ITARSI-1 |  |  | FOR BAY MAINTENANCE & TESTING WORK | 22-Jul-2025 | 09:00 | 22-Jul-2025 | 18:00 | real time
35 | 2025-07-21 14:14 |  |  | 220KV-MORENA-MALANPUR-1 |  |  | FOR LINE MAINTENANCE WORK | 22-Jul-2025 | 09:00 | 22-Jul-2025 | 17:00 | real time
36 | 2025-07-21 14:14 |  |  | 220KV-PANDURNA-KALMESHWAR-1 |  |  | FOR LINE MAINTENANCE WORK | 22-Jul-2025 | 09:00 | 22-Jul-2025 | 18:00 | real time
37 | 2025-07-21 14:14 |  |  | 220KV-SHUJALPUR-RAJGARH-MP-2 |  |  | LINE MAINTENANCE WORK | 22-Jul-2025 | 08:00 | 22-Jul-2025 | 18:00 | real time
38 | 2025-07-21 14:14 |  |  | 400KV-BINA-MP-BINA-2 |  |  | Simultaneous ouatge of 1200KV/400KV BINA-ICT-1 & 400KV-BINA-MP-BINA-2 has been required for Bay-402 LBB Testing | 22-Jul-2025 | 09:00 | 22-Jul-2025 | 15:00 | ok
S/I, SLDC MPPTCL JABALPUR.