## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-06-19 |  |  | APPROVED OUTAGE LIST FOR DTD 19.06.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-18 15:24 | MR2506/0400 |  | 220KV_220 kV Amarkantak-Panagar Circuit | 220KV_AMARKANTAK | NON-OCCM-MP | F/o disc stringing replacement & other line maint. | 19-06-2025 10:00:00 | 19-06-2025 17:00:00 | Jitendra Tiwari | 9425805298 | ok
2 | 2025-06-12 11:11 | MR2506/0261 | Daily | 400KV_400 KV ASHTA UJJAIN LINE 1, 2 | 400KV_ASHTA4 | NON-OCCM-MP | LIVE LINE PERMIT FOR FIBER MAINTENANCE SPLICING | 12-06-2025 09:00:00 | 20-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-06-16 19:00 | MR2506/0357 | Daily | 220KV_220 KV BHOPAL BAIRAGARH LINE-3 | 220KV_BAIRAGARH | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
4 | 2025-06-18 15:16 | MR2506/0399 |  | 132KV_132kV Balaghat-Lalburra Line | 132KV_BALAGHAT | NON-OCCM-MP | Tightening Work of Sus. Clamp, A/H, V/D | 19-06-2025 09:00:00 | 19-06-2025 17:00:00 | SHRIDHAR KUMAR BHALADHARE | 9425807264 | ok
5 | 2025-05-02 13:52 | MR2505/0038 | Continuous | 132KV_20 MVA Emco-i | 132KV_BARWANI | NON-OCCM-WR | augmentation of new 63 MVA transformer | 03-05-2025 11:00:00 | 30-06-2025 19:00:00 | vijay chand saiyam | 9425820043 | Continuous
6 | 2025-06-18 13:01 | MR2506/0392 |  | 132KV_132 KV Bina Chanderi Line | 220KV_BINA | NON-OCCM-MP | Flash over and Broken disc replacement work | 19-06-2025 10:00:00 | 19-06-2025 18:00:00 | Satish Kumar Bhagat | 9425806916 | sub ld
7 | 2025-06-18 13:26 | MR2506/0393 |  | 220KV_220 kv Chhegaon - Khandwa (PGCIL) Ckt 2nd | 400KV_CHHEGAON4 | OCCM-MP | For Providing Bypas Jumper & Line Maintenance work | 19-06-2025 08:00:00 | 19-06-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, through sub ld
8 | 2025-04-28 13:05 | MR2504/0766 | Continuous | 20MVA_132/33KV_BHEL_X'mer_4 | 220KV_DAMOH | OCCM-MP | augmantation of 20 MVA transformer by 63 mva trans | 28-04-2025 14:00:00 | 30-06-2025 16:00:00 | MK Choubey | 8959559657 | Continuous
9 | 2025-05-07 15:18 | MR2505/0133 | Continuous | 160MVA_220/132KV_BHEL_X'mer_1 | 220KV_HANDIYA | NON-OCCM-MP | for Replacement of Transformer | 08-05-2025 10:00:00 | 08-07-2025 17:00:00 | J.D.Khoria | 9425804975 | Continuous
10 | 2025-06-18 14:40 | MR2506/0395 |  | 220KV_220 kv Hoshangabad Mandideep Feedar | 220KV_HOSHANGABAD | NON-OCCM-MP | For Commissioning Of Main 2 DPR Relay | 19-06-2025 10:00:00 | 19-06-2025 17:00:00 | V.P.DWIVEDI | 9425804799 | real time
11 | 2025-06-17 21:54 | MR2506/0387 | Continuous | 400KV_UNIT - 7 | 400KV_INDIRASAGAR | NON-OCCM-WR | ANNUAL MAINTENANCE | 18-06-2025 06:00:00 | 30-06-2025 18:00:00 | Vinay Mishra | 9575074321 | as per system requirement
12 | 2025-06-17 21:15 | MR2506/0385 |  | 400KV_400 KV ISP- INDORE-1 FEEDER | 400KV_INDIRASAGAR | NON-OCCM-WR | ANNUAL MAINTENANCE | 19-06-2025 07:00:00 | 19-06-2025 16:00:00 | Vinay Mishra | 9575074321 | ok, through sub ld, shall be given from 10hrs
13 | 2025-06-12 16:27 | MR2506/0283 | Daily | 220KV_NORTH ZONE - HATUNIYA CKT-2 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF EXISTING E/W BY 24F OPGW | 15-06-2025 07:00:00 | 25-06-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
14 | 2025-06-12 15:54 | MR2506/0282 | Daily | 220KV_NORTH ZONE - HATUNIYA CKT-1 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF EXISTING E/W BY 24F OPGW | 15-06-2025 07:00:00 | 25-06-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
15 | 2025-05-23 18:38 | MR2505/0487 | Continuous | 220KV_NARSINGHPUR-JABALPUR_Ckt_2 | 220KV_JABALPUR | NON-OCCM-MP | BUNCHING OF 132KV JBP SHAHPURA WITH220 KV JBP NSP | 26-05-2025 09:00:00 | 20-06-2025 18:00:00 | RAJESH TIWARI | 7898239595 | Deffered by site
16 | 2025-06-18 10:50 | MR2506/0388 |  | 220KV_160 mva -I | 220KV_JAORA | NON-OCCM-MP | control cable ripairing WORK | 19-06-2025 09:00:00 | 19-06-2025 16:00:00 | RAKESH BADGOTYA | 7587951143 | ok, through sub ld
17 | 2024-11-20 16:15 | MR2411/0427 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 16-06-2025 09:00:00 | 21-06-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | ok, 220kv Tikamgarh-Chattarpur ckt to be opnened for load management
18 | 2024-11-20 16:18 | MR2411/0428 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 16-06-2025 09:00:00 | 21-06-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | ok, 220kv Tikamgarh-Chattarpur ckt to be opnened for load management
19 | 2025-06-18 15:11 | MR2506/0398 |  | 132KV_132KV Morwa-Bargawan(TBCB) CKT-I | 132KV_MORWA | NON-OCCM-MP | Flsh over disc Replacement | 19-06-2025 10:00:00 | 19-06-2025 19:00:00 | G.L SAHU | 9425805102 | ok
20 | 2025-06-16 18:57 | MR2506/0356 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA LINE | 220KV_MUGALIYACHAAP | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | communication consent required for Data outage
21 | 2025-06-17 18:22 | MR2506/0380 | Daily | 220KV_Omkareshwar - Nimrani Line | 220KV_OMKARESHWAR | NON-OCCM-WR | Annual maintenance | 18-06-2025 09:00:00 | 21-06-2025 18:00:00 | Sh. Pankaj Sharma | 7898703187 | Deffered due to tower collapse at Julwaniya
22 | 2025-06-17 18:27 | MR2506/0381 | Daily | 220KV_Main Bus-A & Bus Coupler | 220KV_OMKARESHWAR | NON-OCCM-WR | Annual maintenance | 19-06-2025 09:00:00 | 20-06-2025 18:00:00 | Sh. Pankaj Sharma | 7898703187 | Deffered due to tower collapse at Julwaniya
23 | 2025-06-09 15:58 | MR2506/0188 | Continuous | 220KV_Generating Unit No. 06 | 220KV_OMKARESHWAR | NON-OCCM-WR | Annual maintenance | 10-06-2025 10:00:00 | 24-06-2025 18:00:00 | Sh. Pankaj Sharma | 7898703187 | as per system requirement
24 | 2025-06-16 12:02 | MR2506/0337 | Continuous | 132KV_132/33KV 50MVA BBL X-MER | 132KV_PATAN | NON-OCCM-MP | OIL LEAKAGE ATTENDING AND OTHER RELATED WORK | 17-06-2025 09:00:00 | 19-06-2025 17:00:00 | RAHUL GAJBHIYE | 9425801304 | Continuous
25 | 2025-04-28 17:06 | MR2504/0792 | Continuous | 132KV_132KV Pench Mansar Line | 132KV_PENCH | OCCM-WR | Overhauling of 132KV SF6 CB | 19-06-2025 09:00:00 | 20-06-2025 20:00:00 | Arun Mungole | 8329756200 | not in WR approval list
26 | 2025-05-08 17:07 | MR2505/0173 | Continuous | 400KV_400kV SSTPH-Pithampur Line Ckt-2 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered due to tower collapse at Julwaniya
27 | 2025-05-08 16:57 | MR2505/0172 | Continuous | 400KV_400kVSSTPH-Pithampur Ckt-1 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered due to tower collapse at Julwaniya
28 | 2025-06-13 14:42 | MR2506/0295 | Daily | 132KV_132kv SAGAR-SAGAR IC 3 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | Work installation of OPGW | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
29 | 2025-06-13 14:38 | MR2506/0294 | Daily | 132KV_132KV SAGAR-SAGAR IC 1 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | OPGW Work installation (Hot Line Permit | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
30 | 2025-05-03 11:32 | MR2505/0054 | Continuous | 220KV_100 MVA X-mer Make CGL | 220KV_SARNI | NON-OCCM-MP | X-mer Augmentation work by 160 MVA X-mer AREVA | 05-05-2025 10:00:00 | 10-07-2025 17:00:00 | Er K.K. Choure | 9425801357 | Continuous
31 | 2025-06-18 12:27 | MR2506/0391 |  | 220KV_220 KV Sarni-Handiya line | 220KV_SARNI | NON-OCCM-MP | Resagging work between section 192-213 | 19-06-2025 09:00:00 | 19-06-2025 18:00:00 | Ashutosh Rai | 9425806902 | ok, through sub ld
32 | 2025-05-21 18:29 | MR2505/0451 | Continuous | 400KV_400KV ASHTA LINE-II | 400KV_SATPURA TPS | NON-OCCM-MP | Maintanance & testing of bay Equipment | 19-06-2025 09:00:00 | 21-06-2025 18:00:00 | S.S THAKUR | 9424611244 | Deffered due to OPGW work on 400 KV ASHTA UJJAIN LINE 1, 2
33 | 2025-06-13 09:54 | MR2506/0287 | Continuous | 220KV_Birsinghpur- Manpur fdr. | 400KV_SGTPS | NON-OCCM-MP | For overhauling of 220 KV circuit breaker | 16-06-2025 08:00:00 | 19-06-2025 16:00:00 | s banerjee | 9424352880 | Continuous
34 | 2025-06-18 16:13 | MR2506/0401 | Continuous | 132KV_132kV Sidhi - Mauganj Ckt I&II | 220KV_SIDHI | NON-OCCM-MP | Strining Work | 19-06-2025 08:00:00 | 22-06-2025 18:00:00 | G.L Sahu | 9425805102 | ok, EI and PTCC approval to be submitted while charging
35 | 2025-06-18 15:04 | MR2506/0396 | Continuous | 220KV_220 KV JABALPUR NO.1 LOAD TRANSFER ON 220 KV BUS COUPLER | 220KV_SUKHA | NON-OCCM-MP | CIRCUIT BREAKER WIRING & OTHER RELATED WORK | 19-06-2025 10:00:00 | 20-06-2025 17:00:00 | Ashish sonkeshriya | 7587951153 | ok, line to be in service through TBC
36 | 2025-04-17 17:31 | MR2504/0478 | Daily | 132KV_132 kV Tikamgarh IC - 1st line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Installation work | 18-04-2025 07:00:00 | 19-06-2025 19:00:00 | MPPTCL Chhatarpur | 942580499 | ok, line to be in service
37 | 2025-04-17 17:34 | MR2504/0479 | Daily | 132KV_132 kV Tikamgarh-Badamalhera line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Installation work | 18-04-2025 07:00:00 | 19-06-2025 19:00:00 | Manoj Kumar Tiwari | 942580499 | ok, line to be in service
38 | 2025-06-18 13:42 | MR2506/0394 |  | 220KV_220 KV Ujjain Interconnector- III (Ujjain 220 -Ujjain 400 KV) | 220KV_UJJAIN | NON-OCCM-MP | Pre monsoon Maintenance Work | 19-06-2025 10:00:00 | 19-06-2025 17:00:00 | B.C JOSHI | 7587951137 | as opportunity s/d
39 | 2025-06-18 12:02 | MR2506/0390 |  | 220KV_220 KV Interconnector III | 400KV_UJJAIN4 | NON-OCCM-WR | DPR Relay installation work | 19-06-2025 10:00:00 | 19-06-2025 17:00:00 | SANTOSH CHAVRASIA | 9425804677 | ok, through sub ld
40 | 2025-06-18 12:02 |  |  | 400KV-DAMOH-KATNI-1 |  | OCCM-WR | TOWER STRENGTHENING WORK | 19-Jun-2025 | 09:00 | 24-Jun-2025 | 17:00 | ok, 220kv Tikamgarh-Chattarpur ckt to be opened for load management
41 | 2025-06-18 12:02 |  |  | 220KV-BINA-MP-BINA-1 |  | OCCM-WR | for AMP work of LINE CT & Line terminal equipment | 19-Jun-2025 | 07:00 | 19-Jun-2025 | 18:00 | ok
42 | 2025-06-18 12:02 |  |  | 400KV-NAGDA-DEHGAM-1 |  | OCCM-WR | Outage of 400kV Nagda-Dehgam#1 for DTPC commissioning and end to end testing work, For Shutdown Nature defect Rectification Work , Non auto mode of ckt 2 is required . Dia to be kept open at both ends. | 19-Jun-2025 | 07:00 | 19-Jun-2025 | 18:00 | ok
43 | 2025-06-18 12:02 |  |  | 400KV-KIRNAPUR-BHILAI-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 19-Jun-2025 | 09:00 | 19-Jun-2025 | 18:00 | real time
44 | 2025-06-18 12:02 |  |  | 400KV-BADNAWAR-RAJGARH-2 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 19-Jun-2025 | 08:00 | 19-Jun-2025 | 18:00 | real time
45 | 2025-06-18 12:02 |  |  | 220KV-KHANDWA-CHHEGAON-2 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 19-Jun-2025 | 08:00 | 19-Jun-2025 | 18:00 | ok, through sub ld
46 | 2025-06-18 12:02 |  |  | 220KV-BHANPURA-MODAK-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 19-Jun-2025 | 08:00 | 19-Jun-2025 | 18:00 | real time
47 | 2025-06-18 12:02 |  |  | 220KV-SHUJALPUR-RAJGARH-MP-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 19-Jun-2025 | 08:00 | 19-Jun-2025 | 18:00 | real time
48 | 2025-06-18 12:02 |  |  | 220KV-INDORE-INDORE NORTH ZONE-1 |  | OCCM-WR | AR from auto to non auto mode for replacement of existing earth wire by 24 Fibre OPGW work | 19-Jun-2025 | 07:00 | 19-Jun-2025 | 18:59 | ok, line to be in service
49 | 2025-06-18 12:02 |  |  | 220KV-INDORE-INDORE NORTH ZONE-2 |  | OCCM-WR | AR from auto to non auto mode for replacement of existing earth wire by 24 Fibre OPGW work | 19-Jun-2025 | 07:00 | 19-Jun-2025 | 18:59 | ok, line to be in service
S/I, SLDC MPPTCL JABALPUR