## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-06-17
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-11 15:29 | MR2506/0256 |  | 220KV_220 kV Anuppur-Kotmikala Circuit I | 220KV_ANUPPUR | NON-OCCM-MP | For low ground Clearance maintenance between Span | 17-06-2025 08:00:00 | 17-06-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ckt 2 is approved
2 | 2025-06-12 11:11 | MR2506/0261 | Daily | 400KV_400 KV ASHTA UJJAIN LINE 1, 2 | 400KV_ASHTA4 | NON-OCCM-MP | LIVE LINE PERMIT FOR FIBER MAINTENANCE SPLICING | 12-06-2025 09:00:00 | 20-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-06-16 12:50 | MR2506/0339 |  | 220KV_220KV Main bus - 1st | 400KV_BADNAWAR | NON-OCCM-MP | For attending Hot point and bus maintainance | 17-06-2025 09:00:00 | 17-06-2025 17:00:00 | Er. Avinash Varsha (Elite power tech) | 7275196145 | ok, through sub ld
4 | 2025-06-16 15:31 | MR2506/0348 |  | 220KV_220 KV Handia Barwaha Line | 220KV_BARWAHA | NON-OCCM-MP | Line Maintenance work | 17-06-2025 10:00:00 | 17-06-2025 17:00:00 | Naresh Pandre | 9425806905 | Deffered due to s/d on
5 | 2025-05-02 13:52 | MR2505/0038 | Continuous | 132KV_20 MVA Emco-i | 132KV_BARWANI | NON-OCCM-WR | augmentation of new 63 MVA transformer | 03-05-2025 11:00:00 | 30-06-2025 19:00:00 | vijay chand saiyam | 9425820043 | sub ld
6 | 2025-06-12 09:07 | MR2506/0260 | Daily | 220KV_220 KV Bina- Pichhore & 220 KV Bina- Datia Ckt | 400KV_BINA4 | NON-OCCM-MP | Hot line PTW for OPGW work By M/s ZTT | 12-06-2025 07:00:00 | 18-06-2025 19:00:00 | Satish Kumar Bhagat & Sanjay Singh Thakur | 9425806916 | ok, line to be in service
7 | 2025-06-12 17:11 | MR2506/0285 |  | 220KV_220kv Budhni- Pgcil (itarsi) ckt- 1 | 220KV_BUDHNI | NON-OCCM-WR | DTPC Commissioning & wiring , testing work | 17-06-2025 11:00:00 | 17-06-2025 17:00:00 | shri s.p.s. Tomar | 9425801629 | ok, through sub ld
8 | 2025-06-16 13:14 | MR2506/0341 | Daily | 132KV_132 kV Bijawar -Badamalhera Line | 220KV_CHATARPUR | NON-OCCM-MP | OPGW installation work | 17-06-2025 07:00:00 | 18-06-2025 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
9 | 2025-06-14 11:03 | MR2506/0305 |  | 220KV_220kV Khandwa (PGCIL) â¿¿ Nepa Line | 400KV_CHHEGAON4 | OCCM-MP | For Line Maintenance Work. | 17-06-2025 08:00:00 | 17-06-2025 18:00:00 | C.H. Namdev | 9425802377 | real time
10 | 2025-06-16 13:33 | MR2506/0342 |  | 132KV_132 kV Chhindwara-Borgaon | 220KV_CHHINDWARA | NON-OCCM-MP | Flash over tension disc replace | 17-06-2025 10:00:00 | 17-06-2025 18:00:00 | A.M.Shende | 7587951136 | real time, as per the laoding on pandhurna x-mer
11 | 2025-04-28 13:05 | MR2504/0766 | Continuous | 20MVA_132/33KV_BHEL_X'mer_4 | 220KV_DAMOH | OCCM-MP | augmantation of 20 MVA transformer by 63 mva trans | 28-04-2025 14:00:00 | 30-06-2025 16:00:00 | MK Choubey | 8959559657 | Continuous
12 | 2025-05-07 15:18 | MR2505/0133 | Continuous | 160MVA_220/132KV_BHEL_X'mer_1 | 220KV_HANDIYA | NON-OCCM-MP | for Replacement of Transformer | 08-05-2025 10:00:00 | 08-07-2025 17:00:00 | J.D.Khoria | 9425804975 | Continuous
13 | 2025-06-12 15:53 | MR2506/0281 | Daily | 220KV_NORTH ZONE - HATUNIYA CKT-1 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF EXISTING E/W BY 24F OPGW | 15-06-2025 07:00:00 | 25-06-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
14 | 2025-06-12 16:27 | MR2506/0283 | Daily | 220KV_NORTH ZONE - HATUNIYA CKT-2 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF EXISTING E/W BY 24F OPGW | 15-06-2025 07:00:00 | 25-06-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
15 | 2025-05-23 18:38 | MR2505/0487 | Continuous | 220KV_NARSINGHPUR-JABALPUR_Ckt_2 | 220KV_JABALPUR | NON-OCCM-MP | BUNCHING OF 132KV JBP SHAHPURA WITH220 KV JBP NSP | 26-05-2025 09:00:00 | 20-06-2025 18:00:00 | RAJESH TIWARI | 7898239595 | Deffered by site
16 | 2024-11-20 16:15 | MR2411/0427 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 16-06-2025 09:00:00 | 21-06-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | shall be given from 19th
17 | 2024-11-20 16:18 | MR2411/0428 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 16-06-2025 09:00:00 | 21-06-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | shall be given from 19th
18 | 2025-06-16 16:32 | MR2506/0349 |  | 132KV_132 KV Aux bus in 132/33 KV S/s Madwas | 132KV_MADWAS | NON-OCCM-MP | Overhead Stringing work | 17-06-2025 08:00:00 | 17-06-2025 13:00:00 | Jagat Narayan Singh | 9425802388 | ok
19 | 2025-06-16 11:39 | MR2506/0336 |  | 132KV_132 kv Maihar - Reliance (Cement) line | 220KV_MAIHAR | NON-OCCM-MP | Switch yard maintenance | 17-06-2025 09:00:00 | 17-06-2025 13:00:00 | Mr.M.M.Baig | 9425805067 | ok
20 | 2025-06-16 16:38 | MR2506/0350 |  | 220KV_220KV Narmadapuram bay on 220KVBUS-Coupler | 220KV_MANDIDEEP | OCCM-MP | Relay TESTINGWORK | 17-06-2025 11:00:00 | 17-06-2025 18:00:00 | A.K. VREMA | 9425801324 | ok, line to be in service through TBC
21 | 2025-06-16 10:43 | MR2506/0335 |  | 132KV_132kV NAINPUR-BAIHAR LINE | 132KV_NAINPUR | NON-OCCM-MP | Tightening Work of J/C & Emergency Tree Cutting | 17-06-2025 10:00:00 | 17-06-2025 17:00:00 | SHRIDHAR KUMAR BHALADHARE | 9425807264 | ok
22 | 2025-06-12 12:51 | MR2506/0265 | Daily | 220KV_220KV Daloda-Mandsaur | 220KV_NEEMUCH | NON-OCCM-MP | OPGW OTDR testing & OPGW Splicing | 13-06-2025 08:30:00 | 17-06-2025 18:30:00 | Gaurav Goyal | 9425805120 | ok, line to be in service
23 | 2025-06-09 15:58 | MR2506/0188 | Continuous | 220KV_Generating Unit No. 06 | 220KV_OMKARESHWAR | NON-OCCM-WR | Annual maintenance | 10-06-2025 10:00:00 | 24-06-2025 18:00:00 | Sh. Pankaj Sharma | 7898703187 | as per system requirement
24 | 2025-06-16 12:02 | MR2506/0337 | Continuous | 132KV_132/33KV 50MVA BBL X-MER | 132KV_PATAN | NON-OCCM-MP | OIL LEAKAGE ATTENDING AND OTHER RELATED WORK | 17-06-2025 09:00:00 | 19-06-2025 17:00:00 | RAHUL GAJBHIYE | 9425801304 | ok
25 | 2025-04-28 16:55 | MR2504/0789 | Continuous | 132KV_PENCH-KANHAN_Ckt | 132KV_PENCH | OCCM-WR | Maintenance of SF6 CB | 17-06-2025 09:00:00 | 18-06-2025 20:00:00 | SE(O&M)Pench | 8329756200 | not in WR list
26 | 2025-04-28 17:02 | MR2504/0790 | Continuous | 132KV_132KV Pench Kanhan Line | 132KV_PENCH | OCCM-WR | Overhauling of 132KV SF6 CB | 17-06-2025 09:00:00 | 18-06-2025 20:00:00 | Arun Mungole | 8329756200 | not in WR list
27 | 2025-05-08 17:07 | MR2505/0173 | Continuous | 400KV_400kV SSTPH-Pithampur Line Ckt-2 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered, shall be given after restoration of 400kv Chhegaon-Julwaniya ckt 1, 2
28 | 2025-05-08 16:57 | MR2505/0172 | Continuous | 400KV_400kVSSTPH-Pithampur Ckt-1 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered, shall be given after restoration of 400kv Chhegaon-Julwaniya ckt 1, 2
29 | 2025-06-16 13:10 | MR2506/0340 |  | 400KV_400kv Sagar-Bina Lilo Line (PGCIL) | 400KV_SAGAR | OCCM-MP | Line Maintenance work | 17-06-2025 09:00:00 | 17-06-2025 18:00:00 | Pankaj yadav | 9406713326 | ok
30 | 2025-06-13 14:42 | MR2506/0295 | Daily | 132KV_132kv SAGAR-SAGAR IC 3 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | Work installation of OPGW | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
31 | 2025-06-13 14:38 | MR2506/0294 | Daily | 132KV_132KV SAGAR-SAGAR IC 1 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | OPGW Work installation (Hot Line Permit | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
32 | 2025-05-03 11:32 | MR2505/0054 | Continuous | 220KV_100 MVA X-mer Make CGL | 220KV_SARNI | NON-OCCM-MP | X-mer Augmentation work by 160 MVA X-mer AREVA | 05-05-2025 10:00:00 | 10-07-2025 17:00:00 | Er K.K. Choure | 9425801357 | Continuous
33 | 2025-06-15 13:13 | MR2506/0319 | Daily | 220KV_220 kv Sarni Handia | 220KV_SARNI | NON-OCCM-MP | Resagging work b/w loc.no. 192 to213 | 16-06-2025 09:00:00 | 18-06-2025 18:00:00 | Ashutosh rai | 9425806902 | ok, through sub ld
34 | 2025-05-21 18:20 | MR2505/0450 | Continuous | 400KV_400KV ASHTA LINE-I | 400KV_SATPURA TPS | NON-OCCM-MP | Maintenance & testing of bay Equipment | 16-06-2025 09:00:00 | 18-06-2025 18:00:00 | S.S THAKUR | 9425611244 | Deffered
35 | 2025-06-13 09:54 | MR2506/0287 | Continuous | 220KV_Birsinghpur- Manpur fdr. | 400KV_SGTPS | NON-OCCM-MP | For overhauling of 220 KV circuit breaker | 16-06-2025 08:00:00 | 19-06-2025 16:00:00 | s banerjee | 9424352880 | Continuous
36 | 2025-04-17 17:31 | MR2504/0478 | Daily | 132KV_132 kV Tikamgarh IC - 1st line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Installation work | 18-04-2025 07:00:00 | 19-06-2025 19:00:00 | MPPTCL Chhatarpur | 942580499 | ok, line to be in service
37 | 2025-04-17 17:34 | MR2504/0479 | Daily | 132KV_132 kV Tikamgarh-Badamalhera line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Installation work | 18-04-2025 07:00:00 | 19-06-2025 19:00:00 | Manoj Kumar Tiwari | 942580499 | ok, line to be in service
38 | 2025-06-16 15:18 | MR2506/0346 |  | 220KV_220 KV Ujjain Intconnector -II (400 KV Ujjain - 220 KV Ujjain) | 220KV_UJJAIN | NON-OCCM-WR | Pre monsoon maintenance | 17-06-2025 10:00:00 | 17-06-2025 17:00:00 | B.C JOSHI | 7587951137 | ok, as opportunity s/d
39 | 2025-06-16 13:39 | MR2506/0343 |  | 220KV_220kV interconnector ckt.-IInd | 400KV_UJJAIN4 | NON-OCCM-MP | DPR Relay installation & bay maint.work | 17-06-2025 10:00:00 | 17-06-2025 17:00:00 | Mr.Santosh Chavrasia | 9425804677 | ok, through sub ld
40 |  |  |  | 400 KV ISP NAGADA / 400 KV ISP INDORE 1 / 400 KV ISP SARNI | ISP |  | AOH |  |  |  |  | Deffered, NOT IN WR LIST
41 |  | 249519 |  | 220KV-BINA-SHIVPURI-1 | 220 | POWERGRID_WR2 | for AMP work of LINE CT & Line terminal equipment | 17-Jun-2025 | 07:00 | 17-Jun-2025 | 18:00 | ok
42 |  | 249520 |  | BINA - 220KV - BUS 1 | 220 | POWERGRID_WR2 | For AMP work 1. Bay Isolators associated with 220 KV Bus -1 will be out of service. 2.Elements connected with 220kV Bus-1 shall be charged through 220kV Bus-2 | 17-Jun-2025 | 07:00 | 17-Jun-2025 | 18:00 | ok
43 |  | 250027 |  | 220KV-ANNUPUR-KOTMIKALA-2 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK | 17-Jun-2025 | 09:00 | 17-Jun-2025 | 17:00 | ok
44 |  | 253576 |  | 220KV-ITARSI-BUDNI-1 | 220 | MP_SLDC | s/d required for DTPC commissioning, wiring and testing work at Itarsi PG end | 17-Jun-2025 | 11:00 | 17-Jun-2025 | 16:59 | ok, through sub ld
45 |  | 249967 |  | 400KV-SAGAR-BINA-1 | 400 | MP_SLDC | FOR LINE MAINTENANCE WORK | 17-Jun-2025 | 09:00 | 17-Jun-2025 | 18:00 | ok
46 |  | 250003 |  | 220KV-KHANDWA-NEPANAGAR-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK | 17-Jun-2025 | 08:00 | 17-Jun-2025 | 18:00 | real time
47 |  | 250004 |  | 220KV-BETUL-PANDURNA-1 | 220 | MP_SLDC | FOR CONDUCTOR RE-SAGGING WORKS IN VARIOUS SECTION | 17-Jun-2025 | 08:00 | 17-Jun-2025 | 18:00 | real time
48 |  | 251467 |  | 400KV-SINGAJI-PITHAMPUR-1 | 400 | MP_SLDC | for tower strengthening works | 16-Jun-2025 | 08:00 | 30-Jun-2025 | 17:59 | Deffered
49 |  | 251468 |  | 400KV-SINGAJI-PITHAMPUR-2 | 400 | MP_SLDC | for tower strengthening works | 16-Jun-2025 | 08:00 | 30-Jun-2025 | 17:59 | Deffered
50 |  | 253392 |  | 220KV-INDORE-INDORE NORTH ZONE-1 | 220 | MP_SLDC | AR from auto to non auto mode for replacement of existing earth wire by 24 Fibre OPGW work | 17-Jun-2025 | 07:00 | 17-Jun-2025 | 18:59 | ok, line to be in service
51 |  | 253404 |  | 220KV-INDORE-INDORE NORTH ZONE-2 | 220 | MP_SLDC | AR from auto to non auto mode for replacement of existing earth wire by 24 Fibre OPGW work | 17-Jun-2025 | 07:00 | 17-Jun-2025 | 18:59 | ok, line to be in service