## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-08 |  |  | APPROVED OUTAGE LIST FOR DTD.08.10.25
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-03 12:03 | MR2510/0056 | Daily | 220KV_220 kV Adampur-Hoshangabad line | 220KV_ADAMPUR | NON-OCCM-MP | Defective Disc replacement work | 04-10-2025 09:00:00 | 14-10-2025 17:00:00 | Ankit Mehroliya | 9425804506 | ok, through sub ld
2 | 2025-10-07 11:14 | MR2510/0158 |  | 220KV_160 MVA X-MER -II BHEL | 220KV_ASHOKNAGAR | NON-OCCM-MP | Post mansoon Maintenance | 08-10-2025 10:00:00 | 08-10-2025 18:00:00 | RAKESH SUMAN | 7587951093 | ok, through sub ld
3 | 2025-10-07 11:56 | MR2510/0166 |  | 132KV_132 KV Ashta-Ichhawar ckt no.2 | 400KV_ASHTA4 | NON-OCCM-MP | Post monsoon Maintenance | 08-10-2025 09:00:00 | 08-10-2025 12:00:00 | Jitendra Lohana | 9425804978 | sub ld
4 | 2025-10-07 14:52 | MR2510/0189 |  | 220KV_220/132kv 160mva xmer make areva | 220KV_BADNAGAR | OCCM-MP | For Post maintenance and testing work | 08-10-2025 10:00:00 | 08-10-2025 17:00:00 | Poshkar kushwaha | 8103589820 | ok, through sub ld
5 | 2025-10-02 14:27 | MR2510/0044 |  | 400KV_315 MVA ICT-2 T&R | 400KV_BADNAWAR | NON-OCCM-MP | Post mansoon maintenance & testing work | 08-10-2025 08:00:00 | 08-10-2025 18:00:00 | Er Abhishek Verma | 9340855901 | ok, through sub ld
6 | 2025-10-01 17:30 | MR2510/0015 |  | 220KV_160MVA XMER II MAKE-BHEL | 220KV_BADOD | NON-OCCM-WR | POST MONSOON MAINTE & TRANSFORMER TESTING WORK | 08-10-2025 09:00:00 | 08-10-2025 17:30:00 | ER Y K RATHORE | 9425804968 | ok, through sub ld
7 | 2025-10-01 17:32 | MR2510/0016 |  | 220KV_220KV BAROD-SUWASRA CKT-I | 220KV_BADOD | NON-OCCM-WR | DPR RELAY SETTING WORK & HAND TRIP ONLY BAROD END | 08-10-2025 12:30:00 | 08-10-2025 13:30:00 | ER Y K RATHORE | 9425804968 | Deferred due to s/d on Main bus at 400kv Ujjain
8 | 2025-10-01 17:34 | MR2510/0017 |  | 220KV_220KV BAROD-SUWASRA CKT-II | 220KV_BADOD | NON-OCCM-WR | DPR RELAY SETTING WORK & HAND TRIP ONLY BAROD END | 08-10-2025 14:30:00 | 08-10-2025 15:30:00 | ER Y K RATHORE | 9425804968 | Deferred due to s/d on Main bus at 400kv Ujjain
9 | 2025-10-07 11:22 | MR2510/0160 |  | 220KV_220KV Main Bus section-l | 220KV_BARWAHA | NON-OCCM-MP | S/D for Hot point attending work | 08-10-2025 09:00:00 | 08-10-2025 15:00:00 | Er.Imran Beg | 9425805200 | Deferred due to high OSP generation and ISP gates opened
10 | 2025-10-07 11:18 | MR2510/0159 |  | 220KV_220kV Barwahaâ¿¿ Nimrani Tap Omkareshwar feeder | 220KV_BARWAHA | NON-OCCM-MP | for Main-2 DPR Relay Testing and Commissioning wor | 08-10-2025 09:00:00 | 08-10-2025 17:00:00 | Er.Imran Beg | 9425805200 | Deferred due to high OSP generation and ISP gates opened
11 | 2025-10-07 12:28 | MR2510/0169 |  | 132KV_20 MVA GEC_X-mer | 220KV_BETUL | NON-OCCM-MP | Erection work of new 63 MVA TAL X-mer | 08-10-2025 09:00:00 | 08-10-2025 17:00:00 | Vishal Kumar Malviya | 9425804955 | sub ld
12 | 2025-10-06 16:55 | MR2510/0149 |  | 132KV_132KV Bhonra - Raghogarh line | 132KV_BHONRA | NON-OCCM-MP | For Df/O replacement & other line maint. work | 08-10-2025 10:00:00 | 08-10-2025 17:00:00 | Akhilesh Singh | 8586865656 | sub ld
13 | 2025-10-01 12:35 | MR2510/0007 | Continuous | 400KV_315 MVA X-MER NO-3BHEL | 400KV_BHOPAL4 | NON-OCCM-MP | Post Monsoon Maintenance & Testing work | 08-10-2025 09:00:00 | 09-10-2025 18:00:00 | Er. Akram Khan | 9425804695 | ok, through sub ld
14 | 2025-10-07 14:45 | MR2510/0187 |  | 132KV_132 KV Bina-Sironj Ckt | 220KV_BINA | NON-OCCM-MP | F/O disc insulator replacement & other line mainte | 08-10-2025 10:00:00 | 08-10-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | sub ld
15 | 2025-10-07 14:59 | MR2510/0191 |  | 132KV_132 KV Bina-Khurai Ckt-1 | 220KV_BINA | NON-OCCM-MP | For line maintenance work. | 08-10-2025 10:00:00 | 08-10-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | ok
16 | 2025-10-07 14:08 | MR2510/0180 |  | 220KV_220kV Bina -Pichhore ckt. | 400KV_BINA4 | NON-OCCM-MP | B phase wave trap damaged jumper replacement work | 08-10-2025 10:00:00 | 08-10-2025 17:00:00 | Mr.P.N.Namdeo | 7587951092 | ok, through sub ld
17 | 2025-10-07 14:37 | MR2510/0186 |  | 220KV_220/132 160 MVA X-MER NO I | 220KV_CHAPDA | NON-OCCM-MP | post monsoon maintanace | 08-10-2025 10:00:00 | 08-10-2025 17:00:00 | Er. S.K. SHARMA | 9425801315 | ok, through sub ld
18 | 2025-10-07 12:58 | MR2510/0176 |  | 220KV_160 MVA X-MER (BBL)-Ist | 220KV_DALODA | NON-OCCM-MP | Post mansoon Maintenance & testing work | 08-10-2025 10:00:00 | 08-10-2025 17:00:00 | sailendra boarasi | 9907246485 | Deferred due to Jaora, neemuch x-mer s/d
19 | 2025-09-18 17:16 | MR2509/0453 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 06-10-2025 09:00:00 | 11-10-2025 18:00:00 | SHRI M. M. BAIG | 9425805067 | Deferred
20 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
21 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
22 | 2025-10-07 15:12 | MR2510/0193 |  | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | F/o disc stringing replacement and other line main | 08-10-2025 10:00:00 | 08-10-2025 17:00:00 | Jitendra Tiwari | 9425805298 | ok
23 | 2025-10-07 12:28 | MR2510/0168 |  | 132KV_40 MVA X-MAR, TALK | 132KV_GARHAKOTA | NON-OCCM-MP | POST MANSOON MAINTINANCE | 08-10-2025 09:00:00 | 08-10-2025 17:00:00 | SK HAJARI | 9425620010 | o&m consent required
24 | 2025-10-07 11:29 | MR2510/0161 |  | 132KV_132 KV Garoth - Suwasara line | 132KV_GAROTH | NON-OCCM-MP | Flashover disc Replcement & Other Maintenance work | 08-10-2025 10:00:00 | 08-10-2025 17:00:00 | Ravindra Kumar Marsole | 9425814080 | sub ld
25 | 2025-10-07 13:46 | MR2510/0178 |  | 220KV_220KV ITARSI-HANDIA CKT-I | 220KV_HANDIYA | NON-OCCM-MP | FLASH OVER DISC REPLACMENT WORK | 08-10-2025 09:00:00 | 08-10-2025 13:00:00 | R N PARTE | 9425804701 | Deferred due to s/d on Barwaha main bus
26 | 2025-10-07 14:02 | MR2510/0179 |  | 220KV_220KV ITARSI-HANDIA CKT-2 | 220KV_HANDIYA | NON-OCCM-MP | FLASH OVER DISC REPLACEMENT WORK | 08-10-2025 14:00:00 | 08-10-2025 17:00:00 | R N PARTE | 9425804701 | Deferred due to s/d on Barwaha main bus
27 | 2025-10-04 12:27 | MR2510/0086 | Daily | 220KV_220 KV Hoshangabad-Adampur | 220KV_HOSHANGABAD | NON-OCCM-MP | Resagging work b/w loc.no. 20 of lilo to 71 | 05-10-2025 09:00:00 | 10-10-2025 17:00:00 | Ashutosh Rai | 9425806902 | as opportunity s/d
28 | 2025-10-05 17:47 | MR2510/0122 |  | 220KV_220KV INDORE-PITHAMPUR SEC-1 | 400KV_INDORE4 | NON-OCCM-MP | POST MONSOON MAINTANANCE WORK | 08-10-2025 09:00:00 | 08-10-2025 17:00:00 | ATUL PARADKAR | 9425804929 | ok, through sub ld
29 | 2025-10-07 12:46 | MR2510/0175 |  | 132KV_63 BBL TRANSFORMER | 220KV_JABALPUR | NON-OCCM-MP | OIL LIKEG ATTAND &MAINTENEC | 08-10-2025 08:00:00 | 08-10-2025 18:00:00 | D.N PODDAR | 9425805034 | ok, o&m shall be informed
30 | 2025-10-07 10:08 | MR2510/0152 |  | 220KV_160 mva - II | 220KV_JAORA | OCCM-MP | POSTMANSOON MAINTANCE WORK | 08-10-2025 09:00:00 | 08-10-2025 18:00:00 | RAKESH BADGOTYA | 7587951143 | ok, through sub ld
31 | 2025-10-07 12:37 | MR2510/0174 |  | 132KV_20 MVA bbl-make transformer | 132KV_JATARA | NON-OCCM-MP | Post maansoon | 08-10-2025 16:00:00 | 08-10-2025 19:00:00 | Pushpendra Kumar soni | 9425806398 | ok
32 | 2025-10-07 11:02 | MR2510/0157 |  | 220KV_220/132 KV 160 MVA X-mar â¿¿ II, make BBL | 220KV_JULWANIYA | NON-OCCM-MP | Post Monsoon maintenance work | 08-10-2025 10:00:00 | 08-10-2025 17:00:00 | G.P. Mishra Sir | 9425806931 | ok, through sub ld
33 | 2025-10-06 13:37 | MR2510/0131 |  | 40MVA_132/33KV_BBL_Xmer | 132KV_KARAKBEL | NON-OCCM-MP | post monsoon maintenance work | 08-10-2025 10:30:00 | 08-10-2025 18:00:00 | Dinesh Kumar kushwaha | 9425801319 | ok
34 | 2025-10-07 12:29 | MR2510/0170 |  | 132KV_40 MVA ABB X-MER | 132KV_KATNI | NON-OCCM-MP | POST MONSOON MAINTENANCE AND TESTING WORK | 08-10-2025 10:00:00 | 08-10-2025 17:00:00 | ABHISHEK MISHRA | 9425801440 | ok
35 | 2025-10-07 12:24 | MR2510/0167 |  | 220KV_220 KV KATNI MAIHER | 400KV_KATNI4 | NON-OCCM-MP | LINE MAINTINANCE | 08-10-2025 10:00:00 | 08-10-2025 18:00:00 | PANKAJ YADAV | 9406713326 | ok
36 | 2025-09-18 12:55 | MR2509/0410 | Continuous | 400KV_400KV DAMOH - KATNI LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 06-10-2025 09:00:00 | 11-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deferred
37 | 2025-10-07 14:27 | MR2510/0183 |  | 132KV_50MVA Transformer-III (BHEL) | 220KV_KUKSHI | NON-OCCM-MP | Post monsoon maintenance work | 08-10-2025 10:00:00 | 08-10-2025 18:00:00 | Manoj Randha | 9425820034 | sub ld
38 | 2025-10-06 13:35 | MR2510/0130 |  | 132KV_40 MVA X-MER | 132KV_MADHOTAL | NON-OCCM-MP | 132/33 KV 40 MVA X-Mer Post mansoon maintenance | 08-10-2025 10:00:00 | 08-10-2025 17:00:00 | A.K. Pandey | 9424645081 | o&m consent required
39 | 2025-10-07 14:49 | MR2510/0188 |  | 40MVA_132/33KV_BHEL_X'mer_1 | 220KV_MALANPUR | NON-OCCM-MP | post monsoon maintenance work | 08-10-2025 10:30:00 | 08-10-2025 17:30:00 | shri vikram ahirwar | 9425805415 | sub ld
40 | 2025-10-05 10:37 | MR2510/0101 | Daily | 132KV_132KV Neemuch Manasa Line | 132KV_MANASA | NON-OCCM-MP | Re sagging and line maintanence work | 06-10-2025 08:00:00 | 12-10-2025 18:00:00 | Gaurav goyal | 9425805120 | sub ld
41 | 2025-10-07 12:31 | MR2510/0171 |  | 220KV_160MVA XMER-2 IMP MAKE | 220KV_MANDIDEEP | NON-OCCM-MP | POST MONSOOM MAINT. & RESTING WORK | 08-10-2025 09:00:00 | 08-10-2025 18:00:00 | A.K. VERMA | 9425801324 | ok, through sub ld
42 | 2025-10-07 14:28 | MR2510/0184 |  | 220KV_160MVA TRANSFORMER -I (BHEL) | 220KV_MUGALIYACHAAP | NON-OCCM-MP | POST MONSOON MAINTENANCE WOR AND TESTING WORK | 08-10-2025 10:00:00 | 08-10-2025 18:00:00 | ANIL ACHARKATE (AE) | 7587951086 | ok, through sub ld
43 | 2025-10-07 12:36 | MR2510/0173 |  | 132KV_63 MVA (IMP) X-MER | 132KV_MUNGAOLI | NON-OCCM-MP | Post Monsoon Maintenance work | 08-10-2025 10:00:00 | 08-10-2025 17:00:00 | Lalit singh | 9425806845 | ok, through sub ld
44 | 2025-10-07 14:56 | MR2510/0190 |  | 220KV_160 MVA AREVA TRANSFORMER 220/132/33 KV | 220KV_NAGDA | NON-OCCM-MP | POST MANSOON MAINTENANCE WORK | 08-10-2025 10:00:00 | 08-10-2025 17:00:00 | VIKRAM DEHARIYA | 7000276050 | Deferred due to s/d on Jaora, Ujjain, Badod x-mer
45 | 2025-10-02 15:27 | MR2510/0050 | Continuous | 220KV_220/132 Kv 160MVA BHEL 3 X-mer | 220KV_NARSINGHPUR | NON-OCCM-MP | Replacement of CB,PI&Mainbus isolator erection | 03-10-2025 09:00:00 | 08-10-2025 17:00:00 | Dinesh Kumar Kushwaha | 9425182413 | Continuous
46 | 2025-10-07 14:35 | MR2510/0185 |  | 220KV_220 KV Narsinghpur-Pipariya Line | 220KV_NARSINGHPUR | NON-OCCM-MP | Flashover disc replacement work at loc.No.281/R-Ph | 08-10-2025 10:00:00 | 08-10-2025 18:00:00 | Ashish Kumar | 9425805935 | ok
47 | 2025-10-07 11:42 | MR2510/0162 |  | 220KV_220/132KV CGL MAKE TRANSFORMER-II | 220KV_NEEMUCH | NON-OCCM-MP | Post monsoon maintenance and Testing work | 08-10-2025 09:00:00 | 08-10-2025 17:00:00 | VIVEK MOJASIA | 9425806921 | ok, through sub ld
48 | 2025-10-07 11:54 | MR2510/0164 |  | 132KV_63 MVA "X"-mer 132/33 KV BBL | 220KV_PANDHURNA | OCCM-MP | Post Mansoon Maintenance work. | 08-10-2025 10:00:00 | 08-10-2025 17:00:00 | Sanjay Shende | 9425811447 | ok
49 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
50 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
51 | 2025-10-07 10:13 | MR2510/0154 |  | 220KV_160 mva - II | 220KV_SAILANA2 | OCCM-MP | POSTMANSOON MAINTANCE WORK | 08-10-2025 09:00:00 | 08-10-2025 18:00:00 | RAKESH BADGOTYA | 7587951143 | ok, through sub ld
52 | 2025-10-07 14:14 | MR2510/0181 |  | 132KV_132KV SIDHI-DEOSAR CKT-II | 220KV_SIDHI | NON-OCCM-MP | B PHASE CT REPLACEMENT WORK DUE TO HAIGH TEN DELTA | 08-10-2025 09:00:00 | 08-10-2025 18:00:00 | RAMBAHOR SINGH | 9907230394 | ok, o&m shall be informed
53 | 2025-10-07 13:43 | MR2510/0177 |  | 40MVA_132/33KV_IMP_X'mer | 220KV_SIRMOUR | NON-OCCM-MP | Post monsson maintenance work. | 08-10-2025 10:00:00 | 08-10-2025 17:00:00 | Mr. Indrajeet Singh | 9424734033 | ok
54 | 2025-10-07 12:32 | MR2510/0172 |  | 220KV_160mva 3rd CGL make transformer | 220KV_TIKAMGARH | NON-OCCM-MP | Post mansoon maintenance | 08-10-2025 09:00:00 | 08-10-2025 15:00:00 | Pushpendra Kumar soni | 9425806398 | ok
55 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
56 | 2025-10-06 14:32 | MR2510/0138 |  | 220KV_220kv MAIN BUS-Ist shutdown | 400KV_UJJAIN4 | NON-OCCM-MP | 220kv main bus -Ist maint.work | 08-10-2025 10:00:00 | 08-10-2025 18:00:00 | Santosh Chavrasia | 9425804677 | ok, through sub ld
57 | 2025-10-07 10:55 | MR2510/0156 |  | 132KV_40 MVA X-mer -1 (BBL) | 132KV_WARASEONI | NON-OCCM-MP | post monsoon maint. work. | 08-10-2025 09:00:00 | 08-10-2025 17:00:00 | Swati Bisen | 9425801737 | ok
58 | 2025-10-07 10:55 |  |  | 400KV/220KV JABALPUR-ICT-1 |  |  | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 08-Oct-2025 | 09:00 | 09-Oct-2025 | 17:00 | real time
59 | 2025-10-07 10:55 |  |  | 400KV-INDORE-UJJAIN-2 |  |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 08-Oct-2025 | 08:00 | 08-Oct-2025 | 18:00 | real time
60 | 2025-10-07 10:55 |  |  | 400KV-BHOPAL-MP-ITARSI-1 |  |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 08-Oct-2025 | 09:00 | 08-Oct-2025 | 18:00 | real time
61 | 2025-10-07 10:55 |  |  | 220KV-KHANDWA-CHHANERA-1 |  |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 08-Oct-2025 | 08:00 | 08-Oct-2025 | 18:00 | real time
62 | 2025-10-07 10:55 |  |  | 220KV-SHUJALPUR-SHUJALPUR-MP-1 |  |  | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 08-Oct-2025 | 08:00 | 08-Oct-2025 | 18:00 | real time
63 | 2025-10-07 10:55 |  |  | 220KV-SATNA-MAIHAR-1 |  |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 08-Oct-2025 | 10:00 | 08-Oct-2025 | 17:00 | real time
64 | 2025-10-07 10:55 |  |  | GWALIOR-II - 220KV - BUS 2 |  |  | AMP Works | 08-Oct-2025 | 09:00 | 08-Oct-2025 | 18:00 | ok, through sub ld
65 | 2025-10-07 10:55 | [10 empty] | S/I, SLDC MPPTCL JABALPUR.