## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-29 |  |  | 2025-07-29
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
2 | 2025-07-28 15:14 | MR2507/0445 |  | 220KV_220kV Chhatarpur-Ajaygarh (TBCB) Ckt. 1st Line | 220KV_CHATARPUR | NON-OCCM-MP | Missing/Slip VD Attending & other Line maintenance | 29-07-2025 10:00:00 | 29-07-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
3 | 2025-07-28 16:05 | MR2507/0448 |  | 132KV_132Kv Guna Bhonra ckt. Ist | 220KV_GUNA | NON-OCCM-MP | DF/O replacement & line maint. work | 29-07-2025 10:00:00 | 29-07-2025 17:00:00 | Anup Kumar Dange | 9425814073 | sub ld
4 | 2025-07-25 16:41 | MR2507/0414 | Daily | 400KV_125 MVAr SHUNT REACTOR | 400KV_INDIRASAGAR | NON-OCCM-WR | MAINTENANCE WORK OF SAID ITEM | 29-07-2025 10:00:00 | 31-07-2025 17:00:00 | SHRI VINAI MISHRA | 9575074321 | as per voltage profile
5 | 2025-07-28 13:05 | MR2507/0437 |  | 220KV_220KV Main Bus No.2 | 220KV_ITARSI | NON-OCCM-MP | M.B.No.2 for connecting 7th section M.B.No.2 | 29-07-2025 10:00:00 | 29-07-2025 16:00:00 | J.D.Khoria | 9425804975 | ok, through sub ld, 220kv Itarsi--Sarni ckt 3 will also be under outage.
6 | 2025-07-28 15:19 | MR2507/0446 |  | 132KV_132 KV KATNI PANAGAR LINE | 132KV_KATNI | NON-OCCM-MP | LINE MAINTENANCE WORK | 29-07-2025 10:00:00 | 29-07-2025 18:00:00 | PANKAJ YADAV | 9406713326 | ok
7 | 2025-06-30 15:05 | MR2506/0621 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 28-07-2025 09:00:00 | 02-08-2025 18:00:00 | SHRI PANKAJ YADAV | 9406713326 | Deffered, not in WR list
8 | 2025-06-30 15:54 | MR2506/0630 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 28-07-2025 09:00:00 | 02-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
9 | 2025-07-27 14:12 | MR2507/0430 | Continuous | 132KV_132 KV Khurai- Sagar ckt | 132KV_KHURAI | NON-OCCM-MP | For modification work of above line | 27-07-2025 07:00:00 | 03-08-2025 18:00:00 | Sanjay singh thakur | 9425806936 | Continuous
10 | 2025-07-28 15:13 | MR2507/0444 |  | 132KV_132 kv Maihar â¿¿ Maihar (Cement) line. | 220KV_MAIHAR | NON-OCCM-MP | Switch yard maintenance | 29-07-2025 11:30:00 | 29-07-2025 15:30:00 | Mr.M.M. Baig | 9425805067 | ok
11 | 2025-07-24 12:24 | MR2507/0380 | Continuous | 400KV_400 KV Main Bus-2nd | 400KV_MANDSOUR4 | NON-OCCM-MP | Overhead stringing work | 29-07-2025 09:00:00 | 05-08-2025 18:00:00 | J.P. Parmar | 9425806919 | Deffered, not in WR list
12 | 2025-07-22 13:19 | MR2507/0315 | Continuous | 132KV_132KV Neemuch-Budha Line | 220KV_NEEMUCH | NON-OCCM-MP | For OPGW Testing & OPGW Splicing | 23-07-2025 08:30:00 | 30-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | sub ld
13 | 2025-07-27 16:04 | MR2507/0434 | Continuous | 220KV_220KV Neemuch Mandsaur circuit IInd | 220KV_NEEMUCH | NON-OCCM-MP | OPGW work | 27-07-2025 18:00:00 | 30-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | Continuous
14 | 2025-07-27 16:08 | MR2507/0435 | Daily | 220KV_220KV Neemuch-Mandsaur ciucuit Ist | 220KV_NEEMUCH | NON-OCCM-MP | Only hot line permit | 28-07-2025 08:00:00 | 30-07-2025 19:00:00 | Gaurav Goyal | 9425805120 | ok, line to be in service
15 | 2025-07-05 17:07 | MR2507/0079 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Insatallation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
16 | 2025-07-05 16:59 | MR2507/0078 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) LIne | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
17 | 2025-07-28 13:27 | MR2507/0438 |  | 220KV_Pithampur sec-3 to Rajgarh (PGCIL) ckt | 220KV_PITHAMPUR (SEC-III) | OCCM-MP | For line maitenance work | 29-07-2025 10:00:00 | 29-07-2025 18:00:00 | V.R. Panadia | 9425802330 | ok, through sub ld
18 | 2025-07-25 16:33 | MR2507/0413 | Continuous | 400KV_400 kv main bus-2 | 400KV_SAGAR | OCCM-MP | for extension of 400 kv main bus-2 | 28-07-2025 08:00:00 | 29-07-2025 17:00:00 | Anil mahor | 9425805149 | Deffered, by WRLDC due to BINA PG bus s/d
19 | 2025-07-26 13:57 | MR2507/0418 | Daily | 132KV_132kV Seoni Nainpur Ckt-IInd | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section | 28-07-2025 10:00:00 | 29-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
20 | 2025-07-26 13:59 | MR2507/0419 | Daily | 132KV_132kV Seoni Keolari Line | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section | 28-07-2025 10:00:00 | 29-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
21 | 2025-07-28 15:53 | MR2507/0447 |  | 220KV_220KV PGCIL Ckt-1 & 220 KV Bus Tie Bay | 220KV_SEONI | OCCM-MP | 220KV Auxiliary Maintenance &Filling of SF6in CB | 29-07-2025 10:00:00 | 29-07-2025 17:00:00 | Shri C.S.Sanodiya | 9009798506 | forward the proposal to WRLDC, if any emergency
22 | 2025-07-16 11:19 | MR2507/0211 | Continuous | 220KV_63MVA 220KV/11&6.6 kV Station Trf-5A | 400KV_SGTPS | NON-OCCM-MP | Relay testing,DCRM,CT test,Aircell replacemen | 28-07-2025 08:00:00 | 30-07-2025 18:00:00 | Pramod Mishra | 8989973149 | Continuous
23 | 2025-07-16 10:56 | MR2507/0205 |  | 400KV_400 KV BRS KATNI-1 (BAY -407) | 400KV_SGTPS | NON-OCCM-MP | DPR testing , DCRM of bkr, CT testing | 29-07-2025 08:02:00 | 29-07-2025 18:00:00 | PRAMOD MISHRA | 8989973149 | ok
24 | 2025-07-28 14:12 | MR2507/0441 |  | 220KV_220 kV Birsinghpur TPH-Shahdol Circuit | 220KV_SHAHDOL | NON-OCCM-MP | F/o disc stringing replacement & other line maint. | 29-07-2025 10:00:00 | 29-07-2025 17:00:00 | Jitendra Tiwari | 9425805298 | ok
25 | 2025-07-23 17:12 | MR2507/0374 | Continuous | 400KV_90MVA STATION TRANSFORMER-2 | 400KV_SINGHAJI TPS | NON-OCCM-MP | OVERHAULLING OF 90MVA STATION TRANSFORMER-2 | 28-07-2025 09:30:00 | 06-08-2025 17:30:00 | Yogesh Chouhan | 7999328631 | Continuous
26 | 2025-07-26 14:59 | MR2507/0422 |  | 400KV_400KV Singaji Pithampura-II feeder | 400KV_SINGHAJI TPS | NON-OCCM-MP | Relay testing,CT testing,CVT testing etc. | 29-07-2025 10:00:00 | 29-07-2025 19:00:00 | Deepak Sharma | 8005696855 | ok, through sub ld
27 |  | 259112 |  | BINA - 400KV - BUS 2 |  |  | Simultaneous ouatge of 765KV/400KV BINA-ICT-1 & BINA - 400KV - BUS 2 has been required for Bay-424 LBB Testing | 29-07-2025 09:00:00 | 29-07-2025 15:00:00 |  |  | ok All elements to be in service with bus-1. In case of n-1, Satna-1, Bina-MP-2, Bina-4 will be out. No other S/D to be allowed at Bina-MP, Shujalpur/Sagar. Utmost care to be taken. SLDC MP to be informed.765KV/400KV BINA-ICT-1 is also required simultaneously
28 |  | 253357 |  | 220KV-PITHAMPUR-RAJGARH-1 |  |  | LINE MAINTENANCE WORK | 29-07-2025 08:00:00 | 29-07-2025 18:00:00 |  |  | ok through sub ld All other lines at Pithampur to be in service. SLDC MP to be informed. Load to be managed by SLDC MP
29 |  | 252587 |  | 220KV-SATNA-MP-SATNA-2 |  |  | AMP Work & Line Terminal Equipment Tightness; | 29-07-2025 09:00:00 | 29-07-2025 18:00:00 |  |  | ok All other 220KV ckts to be in service at Satna MP with A/R enabled. no other element affected. Load will be managed by SLDC MP.
30 |  | 257845 |  | 132KV-DHARNI-NEPANAGAR-1 |  |  | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 29-07-2025 08:00:00 | 29-07-2025 17:59:00 |  |  | ok A/R in NA, Line to be in service