## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-14
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-30 16:24 | MR2506/0639 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA | 400KV_ASHTA4 | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
2 | 2025-06-30 16:26 | MR2506/0640 | Daily | 220KV_220 KV BAIRAGARH-ASHTA | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-06-30 16:13 | MR2506/0635 | Daily | 220KV_220 BHOPAL-BAIRAGARH CKT-3 | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
4 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
5 | 2025-07-13 14:57 | MR2507/0181 |  | 132KV_40 MVA X-MER (NGEF) | 220KV_BINA | NON-OCCM-MP | 33 KV Side C&R Panel Replacement work | 14-07-2025 09:30:00 | 14-07-2025 17:00:00 | LALIT SINGH | 9425806845 | o&m consent required
6 | 2025-07-11 14:16 | MR2507/0149 |  | 220KV_220KV BUDHNI -PGCIL(ITARSI) CKT-2ND | 220KV_BUDHNI | NON-OCCM-MP | EMERGENCY SHUTDOWND FOR RELAY AND OTHER WORK | 14-07-2025 11:00:00 | 14-07-2025 17:00:00 | SHRI SATYA PAL SINGH TOMAR | 9425801629 | ok, through sub ld
7 | 2025-06-23 17:09 | MR2506/0482 | Daily | 220KV_220 KV South Zone - Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
8 | 2025-07-13 12:55 | MR2507/0176 |  | 400KV_400KV Indore - ISP-II line | 400KV_INDORE4 | NON-OCCM-MP | For jumpering or new isolator for 50MVAR reactor | 14-07-2025 08:00:00 | 14-07-2025 18:00:00 | Sandeep Umredkar | 9425820035 | s/d time allowed is 8-15hrs, max 5-6 ISP machines allowed during s/d, loading on other ckts of ISP to be monitored
9 | 2025-06-23 17:04 | MR2506/0481 | Daily | 220KV_220KV Indore (400KV) - Mangliya line | 400KV_INDORE4 | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
10 | 2024-11-20 16:49 | MR2411/0436 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 14-07-2025 09:00:00 | 19-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | ok
11 | 2024-11-20 16:54 | MR2411/0437 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 14-07-2025 09:00:00 | 19-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | ok
12 | 2025-07-09 19:11 | MR2507/0133 |  | 220KV_220 KV KATNI MAIHER | 400KV_KATNI4 | NON-OCCM-MP | MAINTENANCE WORK | 14-07-2025 10:00:00 | 14-07-2025 18:00:00 | PANKAJ YADAV | 9406713326 | ok
13 | 2025-07-12 10:50 | MR2507/0161 | Continuous | 132KV_132 KV Khurai-Sagar Ckt | 132KV_KHURAI | NON-OCCM-MP | Extension of continous Sd for Modification work | 12-07-2025 07:00:00 | 18-07-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | Continuous
14 | 2025-07-12 15:28 | MR2507/0171 |  | 220KV_Mandsaur-Neemuch ckt-2 | 400KV_MANDSOUR4 | OCCM-MP | additional DPR-2 connecting work. | 14-07-2025 10:00:00 | 14-07-2025 17:00:00 | RAJESH BHURIYA | 9425806920 | ok, through sub ld
15 | 2025-06-30 16:20 | MR2506/0638 | Daily | 220KV_220 KV BHOPAL-MUGALIYACHAP | 220KV_MUGALIYACHAAP | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
16 | 2025-07-13 13:30 | MR2507/0179 |  | 220KV_220KV Neemuch-Mandsaur ciucuit IInd | 220KV_NEEMUCH | NON-OCCM-MP | For line maintenance work | 14-07-2025 10:00:00 | 14-07-2025 17:00:00 | Gaurav Goyal | 9425805120 | as opportuntiy s/d
17 | 2025-07-05 17:07 | MR2507/0079 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Insatallation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
18 | 2025-07-05 16:59 | MR2507/0078 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) LIne | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
19 | 2025-07-11 16:30 | MR2507/0154 | Daily | 220KV_Omkareshwar-Nimrani Line#1(Tap Barwaha) | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual Maintenance | 14-07-2025 09:00:00 | 17-07-2025 18:00:00 | PANKAJ SHARMA | 7898703187 | ok, through sub ld, from 15th -July s/d to be normalised by 16hrs
20 | 2025-07-12 11:08 | MR2507/0162 |  | 220KV_220 kV Panagar- Amarkantak | 220KV_PANAGAR | NON-OCCM-MP | Disc Replacement at loc. 286 M Ph | 14-07-2025 10:00:00 | 14-07-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
21 | 2025-07-12 16:15 | MR2507/0173 |  | 132KV_132kV Gopalganj Pench Line | 132KV_PENCH | NON-OCCM-MP | Replacement of flashover disc insulator | 14-07-2025 14:00:00 | 14-07-2025 17:00:00 | S.K. Nadekar | 9425806848 | ok, if required for system operation , only 1 machine of pench allowed during s/d, 2nd machine to be run after normalisation of s/d
22 | 2025-07-11 16:12 | MR2507/0153 |  | 400KV_400 kV Pithampur -SSTPS Ckt-III | 400KV_PITHAMPUR4 | NON-OCCM-MP | Relay testing work | 14-07-2025 11:00:00 | 14-07-2025 18:00:00 | Sh. Ankit Prajapati | 9131296643 | ok, through sub ld
23 | 2025-07-11 15:47 | MR2507/0152 |  | 400KV_Rajgarh (PGCIL) to SSP ckt-2 | 400KV_RAJGARH-PG | OCCM-MP | For line maintenance work | 14-07-2025 10:00:00 | 14-07-2025 18:00:00 | V.R. Panadia | 9425802330 | ok, through sub ld
24 | 2025-07-13 13:09 | MR2507/0177 |  | 132KV_132 KV RATLAM-BILPANK feeder | 220KV_RATLAM | NON-OCCM-MP | Pre-Monsoon Maintenance and Testing Work | 14-07-2025 09:00:00 | 14-07-2025 12:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
25 | 2025-07-13 13:10 | MR2507/0178 |  | 132KV_132 KV RATLAM- KHACHROD feeder | 220KV_RATLAM | NON-OCCM-MP | Pre-Monsoon Maintenance and Testing Work | 14-07-2025 13:00:00 | 14-07-2025 17:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
26 | 2025-07-12 17:01 | MR2507/0174 |  | 132KV_132kv Sabalgarh jora ckt | 220KV_SABALGARH | NON-OCCM-MP | Line maintenance work | 14-07-2025 09:00:00 | 14-07-2025 17:00:00 | suraj pawar | 9425814079 | sub ld
27 | 2025-07-12 12:54 | MR2507/0164 |  | 220KV_220kv Damoh-Sagar 1st ckt. line (PGCIL) | 400KV_SAGAR | OCCM-MP | Line Maintenance work | 14-07-2025 09:00:00 | 14-07-2025 18:00:00 | pankaj yadav | 9406713326 | ok
28 | 2025-07-12 16:11 | MR2507/0172 |  | 132KV_132kV Seoni Pench Ckt-IInd | 132KV_SEONI1 | NON-OCCM-MP | Replacement of flashover disc insulator | 14-07-2025 09:00:00 | 14-07-2025 13:00:00 | S.K. Nadekar | 9425806848 | ok, if required for system operation, only 1 machine of pench allowed during s/d
29 | 2025-07-13 10:10 | MR2507/0175 |  | 132KV_132 kV Tikamgarh - Prithvipur line | 220KV_TIKAMGARH | NON-OCCM-MP | F/o disc replacement and other Line maint. woek | 14-07-2025 10:00:00 | 14-07-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
30 | 2025-07-13 14:20 | MR2507/0180 |  | 220KV_220KV Ujjain-Nagda Ckt. IInd | 400KV_UJJAIN4 | NON-OCCM-MP | DPR relay wiring and installation work and Bay mai | 14-07-2025 10:00:00 | 14-07-2025 17:00:00 | Mr.Santosh Chavrasia | 9425804677 | ok, through sub ld
31 |  | 258855 |  | 220KV-ITARSI-BUDNI-2 | MP_SLDC | WR | FOR TCS RELAY REPLACEMENT WORK AND ISOLATOR ALIGNMENT WORK AT BUDHNI | 11:00 | 16:59 |  |  | ok, through sub ld
32 |  | 253281 |  | 400KV-DAMOH-KATNI-1 | MP_SLDC | WR | TOWER STRENGTHENING WORK | 09:00 | 18:00 |  |  | ok
33 |  | 253294 |  | 400KV-BHOPAL-MP-BINA-MP-1 | MP_SLDC | WR | FOR BAY MAINTENANCE & TESTING WORK | 09:00 | 18:00 |  |  | real time
34 |  | 253295 |  | 400KV-SSP-RAJGARH-2 | MP_SLDC | WR | FOR LINE MAINTENANCE WORK | 08:00 | 18:00 |  |  | ok, through sub ld
35 |  | 253326 |  | 220KV-DAMOH-SAGAR-1 | MP_SLDC | WR | FOR LINE MAINTENANCE WORK | 09:00 | 18:00 |  |  | ok
36 |  | 253327 |  | 220KV-SEONI-MP-SEONI-PG-2 | MP_SLDC | WR | FOR LINE MAINTENANCE WORK | 09:00 | 18:00 |  |  | real time
37 |  | 253328 |  | 220KV-GWALIOR-MAHALGAON-1 | MP_SLDC | WR | FOR BAY MAINTENANCE & TESTING WORK | 09:00 | 17:00 |  |  | real time
38 |  | 253329 |  | 220KV-BETUL-SARNI-1 | MP_SLDC | WR | FOR LINE MAINTENANCE WORK | 08:00 | 18:00 |  |  | real time