## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-02
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-09-26 10:45 | MR2509/0704 | Daily | 132KV_132kV Balaghat Baihar Line | 132KV_BALAGHAT | OCCM-MP | Hand Trip Due to load Manage | 28-09-2025 08:00:00 | 02-10-2025 17:00:00 | S.K. BHALADHARE | 9425807264 | Deffered for 2nd October
2 | 2025-10-01 16:21 | MR2510/0012 | Continuous | 220KV_220 kV Bus bar | 220KV_BHOPAL | NON-OCCM-MP | Repeated False alarm in Busbar Pannel | 01-10-2025 16:30:00 | 03-10-2025 15:00:00 | A K Jain | 9425806899 | work completed
3 | 2025-09-29 18:00 | MR2509/0783 | Continuous | 132KV_132KV bus coupler | 220KV_HANDIYA | NON-OCCM-MP | Safety Purpose | 30-09-2025 10:00:00 | 02-10-2025 17:00:00 | K R Dongre | 9424430754 | sub ld
4 | 2025-09-29 17:48 | MR2509/0782 | Continuous | 220KV_220KV Bus Coupler | 220KV_HANDIYA | NON-OCCM-MP | Safety Purpose | 30-09-2025 10:00:00 | 02-10-2025 17:00:00 | K.R. Dongre | 9424430754 | Continuous
5 | 2025-10-01 12:28 | MR2510/0004 |  | 132KV_132 KV Hoshangabad-SPM | 220KV_HOSHANGABAD | NON-OCCM-MP | Attending Hot point on CT | 02-10-2025 10:00:00 | 02-10-2025 13:00:00 | Ashutosh Rai | 9425806902 | sub ld
6 | 2025-10-01 09:35 | MR2510/0001 | Daily | 132KV_132 kV Jabalpur Bargi (MPPTCL) | 220KV_JABALPUR | NON-OCCM-MP | Installation of Joint Box at loc no 29/4 | 02-10-2025 08:00:00 | 04-10-2025 19:00:00 | Jitendra Tiwari | 9425805298 | ok
7 | 2025-09-26 11:48 | MR2509/0709 | Daily | 132KV_132kV Balaghat Kirnapur Ckt-IInd | 400KV_KIRNAPUR | NON-OCCM-MP | Re-sagging of section Loc 465 to 478 & 529 to 547 | 28-09-2025 08:00:00 | 02-10-2025 17:00:00 | Shridhar Kumar Bhaladhare | 9425448642 | Deffered for 2nd October
8 | 2025-09-30 16:46 | MR2509/0801 | Continuous | 220KV_220 /132 kv 160 Bhel X-mer3 | 220KV_NARSINGHPUR | NON-OCCM-MP | Sd for replacement Cb ,pi erection isolator | 01-10-2025 09:00:00 | 06-10-2025 17:00:00 | Dinesh kushwaha | 9425182413 | Deffered for 2nd October
9 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | OK, FTC TO BE SUBMITTED