## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-29
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-09-28 16:45 | MR2509/0759 |  | 220KV_220KV BADNAWAR -BARNAGAR LINE | 400KV_BADNAWAR | NON-OCCM-MP | FOR INSTALLATION OF DOUBLE DPR AND TESTING WORK | 29-09-2025 10:00:00 | 29-09-2025 17:00:00 | Er. Abhishek verma | 9340855901 | ok, through sub ld
2 | 2025-09-25 10:17 | MR2509/0670 | Daily | 132KV_132kV Balaghat Baihar Line | 132KV_BALAGHAT | NON-OCCM-MP | Hand Trip due To load Manage | 27-09-2025 08:00:00 | 30-09-2025 17:00:00 | S.K. BHALADHARE | 9425807264 | ok
3 | 2025-09-20 18:35 | MR2509/0513 | Daily | 220KV_220KV DAMOH - DAMOH IC IIIRD CKT | 220KV_DAMOH | OCCM-MP | FOR OPGW INSTALLATION WORK | 23-09-2025 07:00:00 | 30-09-2025 19:00:00 | M.M. BAIG | 9425805067 | Deferred , not in WR list
4 | 2025-09-28 15:26 | MR2509/0755 |  | 220KV_160 MVA Telk | 220KV_DEWAS | NON-OCCM-MP | Post monsoon maintenance work | 29-09-2025 10:00:00 | 29-09-2025 17:00:00 | Arvind Kumar Joshi | 9425801305 | ok, through sub ld
5 | 2025-09-28 15:26 | MR2509/0754 |  | 132KV_40 MVA BBL TRANSFORMER | 132KV_GARHAKOTA | NON-OCCM-MP | POSTMANSOON MAINTENANCE AND TESTING WORK. | 29-09-2025 11:00:00 | 29-09-2025 17:00:00 | SK HAZARI | 9425801421
6 | 2025-09-28 11:12 | MR2509/0743 |  | 132KV_63 MVA X-mer - 1st make BBL | 220KV_GUNA | NON-OCCM-MP | Post monsoon maintenace work | 29-09-2025 10:30:00 | 29-09-2025 18:00:00 | Sagar Singh Dhakad | 9589205697 | sub ld
7 | 2025-09-28 08:33 | MR2509/0740 |  | 132KV_63 MVA X-mer no.I make BBL | 132KV_HARDA | NON-OCCM-MP | Postmonsoon maintanance & Testing | 29-09-2025 10:00:00 | 29-09-2025 17:00:00 | sh.J.D .Khoria | 9425804975 | sub ld
8 | 2025-09-07 13:02 | MR2509/0161 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-2 | 220KV_INDORE NORTH | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
9 | 2025-09-07 12:51 | MR2509/0159 | Daily | 132KV_132KV North Zone- Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
10 | 2025-09-07 12:45 | MR2509/0158 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
11 | 2025-09-27 15:47 | MR2509/0734 |  | 220KV_220/132 KV 160MVA X-MER-III (TELK) | 220KV_INDORE-SZ | NON-OCCM-MP | Post monsoon maint. and apply fire wage conection | 29-09-2025 10:00:00 | 29-09-2025 17:00:00 | Dharmendra Kushwaha | 9425802801 | ok, through sub ld
12 | 2025-09-26 11:48 | MR2509/0709 | Daily | 132KV_132kV Balaghat Kirnapur Ckt-IInd | 400KV_KIRNAPUR | NON-OCCM-MP | Re-sagging of section Loc 465 to 478 & 529 to 547 | 28-09-2025 08:00:00 | 02-10-2025 17:00:00 | Shridhar Kumar Bhaladhare | 9425448642 | ok, 132kv Balaghat-Bihar to be opened for load management
13 | 2025-09-28 15:47 | MR2509/0758 |  | 220KV_160MVA X-MER IMP | 220KV_KOTAR | OCCM-MP | OIL TOPPING IN CONSERVATOR TANK | 29-09-2025 13:00:00 | 29-09-2025 15:00:00 | ARUN KUMAR KOL | 8319677721 | ok
14 | 2025-09-28 15:34 | MR2509/0756 |  | 220KV_160 MVA -II Transformer | 220KV_KUKSHI | NON-OCCM-MP | For Post Monsoon maintenace work | 29-09-2025 10:00:00 | 29-09-2025 18:00:00 | Er I.S,Chungad | 9425803496 | ok, through sub ld
15 | 2025-09-26 16:44 | MR2509/0726 |  | 132KV_132KV Lakhnadon - Seoni Bay | 132KV_LAKHNADONE | NON-OCCM-MP | To attend oil leakage problem | 29-09-2025 11:00:00 | 29-09-2025 14:00:00 | Seema Dongre | 9425807247 | ok, line to be in service through TBC
16 | 2025-09-26 15:31 | MR2509/0719 |  | 132KV_40MVA BBL Transformer No. 1 | 132KV_LAKHNADONE | NON-OCCM-MP | Post Mansoon Maintenance | 29-09-2025 10:00:00 | 29-09-2025 17:00:00 | Seema Dongre | 9425807247
17 | 2025-09-28 12:14 | MR2509/0745 |  | 160MVA_220/132KV_BHEL_Xmer_1 | 400KV_MANDSOUR4 | NON-OCCM-MP | Post Monsoon Maintenance & Testing Work. | 29-09-2025 09:00:00 | 29-09-2025 17:00:00 | RAJESH BHURIYA | 9425806524 | ok, through sub ld
18 | 2025-09-28 10:58 | MR2509/0742 |  | 400KV_315MVA ICT-1 transformer make-BHEL | 400KV_NAGDA4 | NON-OCCM-MP | Post monsoon maintenance and testing work | 29-09-2025 09:00:00 | 29-09-2025 18:00:00 | Sunil Bamniya | 9425820045 | Deferred , due to s/d on Ujjain ICT
19 | 2025-09-07 12:39 | MR2509/0157 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line. | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
20 | 2025-09-07 12:57 | MR2509/0160 | Daily | 132KV_132KV Niranjanpur - Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
21 | 2025-09-09 16:49 | MR2509/0219 | Continuous | 132KV_PENCH-MANSAR_Ckt | 132KV_PENCH | NON-OCCM-WR | Overhauling of CB & replacement of one faulty CVT | 29-09-2025 09:00:00 | 30-09-2025 16:00:00 | Arun Mungole | 8329756200 | ok
22 | 2025-09-28 12:34 | MR2509/0749 |  | 132KV_132 kv Rewa-Mangawan Ckt-I | 220KV_REWA | NON-OCCM-MP | for load managment | 29-09-2025 11:00:00 | 29-09-2025 18:00:00 | Kanishka Singh | 9425804656 | real time, as per the load management
23 | 2025-09-28 12:42 | MR2509/0751 |  | 132KV_132 KV Rewa-RewaII (Sagra) Ckt | 220KV_REWA | NON-OCCM-MP | For Load Management | 29-09-2025 11:00:00 | 29-09-2025 18:00:00 | Kanishka Singh | 9425804656 | real time, as per the load management
24 | 2025-09-28 12:38 | MR2509/0750 |  | 132KV_132 kv Rewa-Mangwan Ckt-II | 220KV_REWA | NON-OCCM-MP | For load Management | 29-09-2025 11:00:00 | 29-09-2025 18:00:00 | Kanishka Singh | 9425804656 | real time, as per the load management
25 | 2025-09-28 12:31 | MR2509/0748 |  | 220KV_160mva x-mer BHEL | 220KV_REWA | NON-OCCM-MP | post monsoon maint | 29-09-2025 11:00:00 | 29-09-2025 18:00:00 | Kanishka Singh | 9425804656 | real time, as per the load management
26 | 2025-09-20 18:32 | MR2509/0512 | Daily | 220KV_220KV DAMOH - SAGAR PGCIL IIND CKT. | 400KV_SAGAR | OCCM-MP | FOR OPGW INSTALLATION WORK | 23-09-2025 07:00:00 | 30-09-2025 19:00:00 | M.M. BAIG | 9425805067 | Deferred , not in WR list
27 | 2025-09-28 14:53 | MR2509/0753 |  | 220KV_220 kV Satna Maanpur | 220KV_SATNA | NON-OCCM-MP | Attending Y phase line isolator clamp | 29-09-2025 10:00:00 | 29-09-2025 16:00:00 | Ravi Pandey | 9425805296 | ok
28 | 2025-09-22 11:49 | MR2509/0539 |  | 220KV_220 kv Satna (PGCIL) â¿¿ Kotar line | 220KV_SATNA | NON-OCCM-MP | Line maintenance work | 29-09-2025 11:00:00 | 29-09-2025 17:00:00 | Mr R.K. Prajapati | 9407070182 | Deferred , not in WR list
29 | 2025-09-28 10:12 | MR2509/0741 |  | 220KV_160 MVA XMER-II | 220KV_SHAJAPUR | NON-OCCM-MP | POST MONSOON MAIN.WORK. | 29-09-2025 09:00:00 | 29-09-2025 17:00:00 | Er VIJAY OJHA | 9755836908 | Deferred , due to s/d on Ujjain x-mer
30 | 2025-09-28 14:29 | MR2509/0752 |  | 220KV_160 MVA 2nd BBL-Make Transformer | 220KV_TIKAMGARH | NON-OCCM-MP | Post mansoon maintenance | 29-09-2025 10:00:00 | 29-09-2025 17:00:00 | Pushpendra Kumar soni | 9425806398 | ok
31 | 2025-09-26 13:41 | MR2509/0716 |  | 220KV_160 MVA X-MER-IIIrd (Make BHEL-IInd) | 220KV_UJJAIN | NON-OCCM-MP | Post monsoon maintenance and testing work | 29-09-2025 09:00:00 | 29-09-2025 17:00:00 | B.C JOSHI | 7587951137 | ok, through sub ld
32 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
33 | 2025-09-28 04:44 | MR2509/0738 |  | 400KV_315MVA X-MER-II | 400KV_UJJAIN4 | NON-OCCM-MP | X-MER TESTING AND MAINT.WORK | 29-09-2025 10:00:00 | 29-09-2025 17:00:00 | Santosh chavrasia | 9425804677 | ok, through sub ld
34 | 2025-09-28 15:43 | MR2509/0757 |  | 132KV_WAIDHAN-NCL NIGAHI_Ckt_1 | 132KV_WAIDHAN | NON-OCCM-MP | defective energy meter replacement work | 29-09-2025 13:00:00 | 29-09-2025 15:00:00 | G.S. Khairwar | 9584321714 | ok, ABT consent required while charging for meter replacement