## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-06-28 |  |  | 2025-06-28
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-16 18:55 | MR2506/0355 | Daily | 220KV_220 KV BAIRAGARH MUGALIYACHAP LINE | 220KV_BAIRAGARH | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
2 | 2025-06-16 19:00 | MR2506/0357 | Daily | 220KV_220 KV BHOPAL BAIRAGARH LINE-3 | 220KV_BAIRAGARH | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-06-23 09:45 | MR2506/0456 | Daily | 220KV_220 kv Bairagarh Ashta | 220KV_BAIRAGARH | NON-OCCM-MP | OPGW MAINTENANCE WORK | 23-06-2025 09:00:00 | 30-06-2025 09:00:00 | Nitin Reshwal | 9425804890 | ok, line to be in service
4 | 2025-05-02 13:52 | MR2505/0038 | Continuous | 132KV_20 MVA Emco-i | 132KV_BARWANI | NON-OCCM-WR | augmentation of new 63 MVA transformer | 03-05-2025 11:00:00 | 30-06-2025 19:00:00 | vijay chand saiyam | 9425820043 | sub ld
5 | 2025-06-26 14:17 | MR2506/0554 | Daily | 220KV_220 KV Bina-Guna Ckt & 220 KV Bina-Ashoknagar Ckt | 400KV_BINA4 | NON-OCCM-MP | Hot line PTW for OPGW resagging work BY M/s ZTT | 26-06-2025 07:00:00 | 10-07-2025 19:00:00 | Sanjay singh thakur | 9425806936 | ok, line to be in service
6 | 2025-06-27 16:05 | MR2506/0577 | Daily | 132KV_132 kV Bijawar -Badamalhera line | 220KV_CHATARPUR | NON-OCCM-MP | OPGW installation work in line | 28-06-2025 07:00:00 | 29-06-2025 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
7 | 2025-04-28 13:05 | MR2504/0766 | Continuous | 20MVA_132/33KV_BHEL_X'mer_4 | 220KV_DAMOH | OCCM-MP | augmantation of 20 MVA transformer by 63 mva trans | 28-04-2025 14:00:00 | 30-06-2025 16:00:00 | MK Choubey | 8959559657 | sub ld
8 | 2025-05-07 15:18 | MR2505/0133 | Continuous | 160MVA_220/132KV_BHEL_X'mer_1 | 220KV_HANDIYA | NON-OCCM-MP | for Replacement of Transformer | 08-05-2025 10:00:00 | 08-07-2025 17:00:00 | J.D.Khoria | 9425804975 | Continuous
9 | 2025-06-17 21:54 | MR2506/0387 | Continuous | 400KV_UNIT - 7 | 400KV_INDIRASAGAR | NON-OCCM-WR | ANNUAL MAINTENANCE | 18-06-2025 06:00:00 | 30-06-2025 18:00:00 | Vinay Mishra | 9575074321 | as per system requirement
10 | 2025-06-20 19:03 | MR2506/0431 | Continuous | 400KV_400 KV BUS 2 | 400KV_INDIRASAGAR | NON-OCCM-MP | SF 6 CB maintenance work | 24-06-2025 10:00:00 | 28-06-2025 17:00:00 | SANJAY PATEL | 9424050443 | Continuous
11 | 2025-06-23 17:09 | MR2506/0482 | Daily | 220KV_220 KV South Zone - Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
12 | 2025-06-23 17:04 | MR2506/0481 | Daily | 220KV_220KV Indore (400KV) - Mangliya line | 400KV_INDORE4 | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
13 | 2025-06-27 13:26 | MR2506/0571 |  | 220KV_220 KV Sarni-Itarsi Ckt- III | 220KV_ITARSI | NON-OCCM-MP | Resagging work b/w loc.no. 199-218 | 28-06-2025 09:00:00 | 28-06-2025 18:00:00 | Ashutosh Rai | 9425806902 | ok, through sub ld
14 | 2024-11-20 16:32 | MR2411/0430 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 23-06-2025 09:00:00 | 28-06-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | ok, 220kv Tikamgarh-Chattarpur ckt to be opened for load management
15 | 2024-11-20 16:36 | MR2411/0431 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 23-06-2025 09:00:00 | 28-06-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | ok, 220kv Tikamgarh-Chattarpur ckt to be opened for load management
16 | 2025-06-27 15:56 | MR2506/0575 | Continuous | 132KV_132 kv katni kymore line ckt 1st | 400KV_KATNI4 | NON-OCCM-MP | maintenance work | 27-06-2025 18:00:00 | 28-06-2025 18:00:00 | pankaj yadav | 9406713326 | please clear the timings of outage requested
17 | 2025-06-27 15:18 | MR2506/0572 |  | 132KV_132 KV Khurai-Sagar | 132KV_KHURAI | NON-OCCM-MP | F/o Disc insulator replacement & other line maint | 28-06-2025 10:00:00 | 28-06-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | ok
18 | 2025-06-24 12:30 | MR2506/0492 | Continuous | 220KV_220 KV Main Bus-Ist | 400KV_MANDSOUR4 | NON-OCCM-MP | Stringing work of 220 KV side. | 27-06-2025 09:00:00 | 28-06-2025 18:00:00 | J.P. Parmar | 9425806919 | Continuous
19 | 2025-06-16 18:57 | MR2506/0356 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA LINE | 220KV_MUGALIYACHAAP | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | communication consent required for data outage
20 | 2025-06-20 11:59 | MR2506/0420 | Daily | 220KV_220 KV BHOPAL MUGALIYACHAAP | 220KV_MUGALIYACHAAP | NON-OCCM-MP | OPGW MAINTENANCE WORK | 21-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
21 | 2025-06-26 14:57 | MR2506/0557 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | OCCM-WR | Hotline work For Installation OPGW by replace E/W | 26-06-2025 08:00:00 | 10-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
22 | 2025-06-26 15:04 | MR2506/0558 | Daily | 132KV_132 kV Nepa - Pipalpani | 220KV_NEPANAGAR | NON-OCCM-MP | Hotline work Installation OPGW Replaced by E/W | 26-06-2025 08:00:00 | 10-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
23 | 2025-05-08 17:07 | MR2505/0173 | Continuous | 400KV_400kV SSTPH-Pithampur Line Ckt-2 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deferred
24 | 2025-05-08 16:57 | MR2505/0172 | Continuous | 400KV_400kVSSTPH-Pithampur Ckt-1 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deferred
25 | 2025-06-27 11:50 | MR2506/0569 |  | 132KV_132kv Sagar-Gourjhamar 1st Ckt. Line | 400KV_SAGAR | NON-OCCM-MP | Line maintenance work | 28-06-2025 09:00:00 | 28-06-2025 18:00:00 | JP Asati. | 9424445533 | ok
26 | 2025-06-13 14:42 | MR2506/0295 | Daily | 132KV_132kv SAGAR-SAGAR IC 3 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | Work installation of OPGW | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
27 | 2025-06-13 14:38 | MR2506/0294 | Daily | 132KV_132KV SAGAR-SAGAR IC 1 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | OPGW Work installation (Hot Line Permit | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
28 | 2025-05-03 11:32 | MR2505/0054 | Continuous | 220KV_100 MVA X-mer Make CGL | 220KV_SARNI | NON-OCCM-MP | X-mer Augmentation work by 160 MVA X-mer AREVA | 05-05-2025 10:00:00 | 10-07-2025 17:00:00 | Er K.K. Choure | 9425801357 | Continuous
29 | 2025-06-27 16:09 | MR2506/0578 |  | 132KV_132kV Sidhi - Sagra (Rewa-2) Ckt | 220KV_SIDHI | NON-OCCM-MP | OPGW Stringing And line maintenance work. | 28-06-2025 10:00:00 | 28-06-2025 14:00:00 | G.L sahu | 9425805102 | ok
30 | 2025-06-27 15:38 | MR2506/0574 |  | 33KV_33 kV Main Bus | 220KV_SIRMOUR | NON-OCCM-MP | For Damage conductor Replacement | 28-06-2025 08:00:00 | 28-06-2025 10:00:00 | Mr. Indrajeet Singh | 9424734033 | ok
31 | 2025-06-27 11:42 | MR2506/0568 |  | 220KV_220 KV Badod - Suwasara Ckt.- II line | 220KV_SUWASRA2 | NON-OCCM-MP | Flashover disc replacement & other Maint. work | 28-06-2025 10:00:00 | 28-06-2025 17:00:00 | Ravindra Kumar Marskole | 9425814080 | ok, through sub ld
32 | 2025-06-17 17:47 | MR2506/0373 | Daily | 132KV_132 kV Tikamgarh-Badamalhera line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW installation work | 20-06-2025 07:00:00 | 30-06-2025 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
33 | 2025-06-17 17:49 | MR2506/0374 | Daily | 132KV_132 kV Tikamgarh IC 1st line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW installation work | 20-06-2025 07:00:00 | 30-06-2025 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
34 |  | 253854 |  | INDORE - 400KV - BUS 2 |  |  | Replacement of the density monitor work | 09:00 | 18:00/30.06.25 |  |  | ok
35 |  | 250029 |  | 220KV-RAJGARH-DHAR-1 |  |  | LINE MAINTENANCE WORK | 08:00 | 18:00 |  |  | deffered by site
36 |  | 253695 |  | 132KV-DHARNI-NEPANAGAR-1 |  |  | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 08:00 | 17:59 |  |  | ok