## Sheet1
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-07
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-07-06 14:06 | MR2507/0084 |  | 132KV_132KV KUKSHI-ALIRAJPUR-II LINE | 132KV_ALIRAJPUR | NON-OCCM-MP | RELAY TESTING AND MAINTENANCE WORK | 07-07-2025 12:00:00 | 07-07-2025 17:00:00 | MANOJ RANDA | 9425820034 | sub ld
2 | 2025-06-30 16:24 | MR2506/0639 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA | 400KV_ASHTA4 | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-06-30 16:26 | MR2506/0640 | Daily | 220KV_220 KV BAIRAGARH-ASHTA | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
4 | 2025-06-30 16:13 | MR2506/0635 | Daily | 220KV_220 BHOPAL-BAIRAGARH CKT-3 | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
5 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
6 | 2025-07-05 22:26 | MR2507/0080 | Continuous | 400KV_400 KV BHOPAL -ITARSI CKT.-1&2 | 400KV_BHOPAL4 | NON-OCCM-MP | TEN DELTA &CAPACITANCE,DPR RELAY TESTING WORK. | 07-07-2025 10:00:00 | 08-07-2025 18:00:00 | AKRAM KHAN | 9425804695 | ok, through sub ld
7 | 2025-06-26 14:17 | MR2506/0554 | Daily | 220KV_220 KV Bina-Guna Ckt & 220 KV Bina-Ashoknagar Ckt | 400KV_BINA4 | NON-OCCM-MP | Hot line PTW for OPGW resagging work BY M/s ZTT | 26-06-2025 07:00:00 | 10-07-2025 19:00:00 | Sanjay singh thakur | 9425806936 | ok, line to be in service
8 | 2025-06-30 15:05 | MR2506/0620 | Continuous | 132KV_132KV Budha Mandsaur | 132KV_BUDHA | NON-OCCM-MP | in OPGW OTDR Testing and OPGW Splicing | 01-07-2025 08:30:00 | 08-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | sub ld
9 | 2025-05-07 15:18 | MR2505/0133 | Continuous | 160MVA_220/132KV_BHEL_X'mer_1 | 220KV_HANDIYA | NON-OCCM-MP | for Replacement of Transformer | 08-05-2025 10:00:00 | 08-07-2025 17:00:00 | J.D.Khoria | 9425804975 | Continuous
10 | 2025-06-23 17:09 | MR2506/0482 | Daily | 220KV_220 KV South Zone - Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
11 | 2025-06-23 17:04 | MR2506/0481 | Daily | 220KV_220KV Indore (400KV) - Mangliya line | 400KV_INDORE4 | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
12 | 2025-07-06 11:17 | MR2507/0081 |  | 220KV_JULWANIYA4-JULWANIYA_Ckt_2 | 400KV_JULWANIYA4 | NON-OCCM-MP | for line differential relay wiring & Testing work | 07-07-2025 10:00:00 | 07-07-2025 18:00:00 | Ravindra Patil | 8305612190 | ok, through sub ld
13 | 2024-11-20 16:45 | MR2411/0434 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 07-07-2025 09:00:00 | 12-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | ok, 220kv Tikamgarh-Chattarpur to be opened for load managemnet
14 | 2024-11-20 16:47 | MR2411/0435 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 07-07-2025 09:00:00 | 12-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | ok, 220kv Tikamgarh-Chattarpur to be opened for load managemnet
15 | 2025-07-01 15:42 | MR2507/0010 | Continuous | 132KV_132 KV Khurai-Sagar | 132KV_KHURAI | NON-OCCM-MP | Modification/Shifting of 132 KV Khurai-Sagar | 02-07-2025 07:00:00 | 12-07-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | Continuous
16 | 2025-06-30 16:20 | MR2506/0638 | Daily | 220KV_220 KV BHOPAL-MUGALIYACHAP | 220KV_MUGALIYACHAAP | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
17 | 2025-06-26 14:57 | MR2506/0557 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | OCCM-WR | Hotline work For Installation OPGW by replace E/W | 26-06-2025 08:00:00 | 10-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
18 | 2025-06-26 15:04 | MR2506/0558 | Daily | 132KV_132 kV Nepa - Pipalpani | 220KV_NEPANAGAR | NON-OCCM-MP | Hotline work Installation OPGW Replaced by E/W | 26-06-2025 08:00:00 | 10-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
19 | 2025-07-05 10:47 | MR2507/0069 |  | 132KV_132 KV Pipariya-Sohagpur line | 132KV_PIPARIYA1 | NON-OCCM-MP | Installation of wedge connector | 07-07-2025 10:00:00 | 07-07-2025 17:00:00 | Ashutosh Rai | 9425806902 | sub ld
20 | 2025-07-05 16:34 | MR2507/0077 |  | 400KV_Rajgarh (PGCIL) to SSP ckt-1 | 400KV_RAJGARH-PG | OCCM-MP | For line maintenance work | 07-07-2025 10:00:00 | 07-07-2025 18:00:00 | V.R. Panadia | 9425802330 | ok
21 | 2025-07-06 14:30 | MR2507/0085 |  | 220KV_220KV Neemuch-Ratangarh circuit Ist | 220KV_RATANGARH | NON-OCCM-MP | For maintenance work | 07-07-2025 10:00:00 | 07-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | ok, through sub ld
22 | 2025-06-30 14:20 | MR2506/0616 | Daily | 132KV_132kv sagar-sagar ic ic 1st ckt. | 400KV_SAGAR | NON-OCCM-MP | OPGW stringing work ( hot Line permit) | 01-07-2025 07:00:00 | 08-07-2025 19:00:00 | Er. Pankaj Yadav. | 9406713326 | ok, line to be in service
23 | 2025-06-30 14:13 | MR2506/0612 | Daily | 132KV_132kv Sagar-sagar ic 3rd ckt. | 400KV_SAGAR | NON-OCCM-MP | opgw stringing Work (hot line permit) | 01-07-2025 07:00:00 | 08-07-2025 19:00:00 | Er. pankaj yadav | 9406713326 | ok, line to be in service
24 | 2025-05-03 11:32 | MR2505/0054 | Continuous | 220KV_100 MVA X-mer Make CGL | 220KV_SARNI | NON-OCCM-MP | X-mer Augmentation work by 160 MVA X-mer AREVA | 05-05-2025 10:00:00 | 10-07-2025 17:00:00 | Er K.K. Choure | 9425801357 | Continuous
25 | 2025-07-05 16:24 | MR2507/0076 |  | 220KV_220kv Shivpuri Sabalgarh Ckt IInd | 220KV_SHIVPURI | NON-OCCM-MP | Line Maintenance work | 07-07-2025 10:00:00 | 07-07-2025 17:00:00 | SURAJ PAWAR | 9425814079 | ok, through sub ld
26 | 2025-07-06 14:03 | MR2507/0083 |  | 132KV_132KV SIDHI-MAUGANJ CKT-II | 220KV_SIDHI | NON-OCCM-MP | Flsh over disc replacement | 07-07-2025 10:00:00 | 07-07-2025 17:00:00 | G.L SAHU | 9425805102 | ok
27 | 2025-07-06 13:27 | MR2507/0082 |  | 400KV_400 kV Bus Coupler Bay | 400KV_UJJAIN4 | NON-OCCM-MP | Bay test charge routine healthiness test | 07-07-2025 11:00:00 | 07-07-2025 12:00:00 | Mr.Santosh Chavrasia | 9425804677 | ok, through sub ld
28 | 2025-07-05 15:44 | MR2507/0075 |  | 132KV_132 KV JBP NO 01 | 132KV_VFJ | NON-OCCM-MP | RELAY TESTING WORK AND MAINTANANCE | 07-07-2025 10:00:00 | 07-07-2025 17:00:00 | AMIT KUMAR DAHIYA | 9425806926 | o&m consent required
29 | 2025-07-04 15:50 | MR2507/0067 |  | 132KV_132KV WAIDHAN-VSTPP CKT-I | 132KV_WAIDHAN | NON-OCCM-MP | found Majha rope hanging from Earth | 07-07-2025 11:00:00 | 07-07-2025 17:00:00 | G.L SAHU | 9425805102 | send for wrldc emergency approval
30 | 220 | 252539 |  | 220KV-ANNUPUR-KOTMIKALA-1 | Main Bus-I jumpering work of 220 kV Bus tie bay at 220 KV S/s Kotmikala |  | 11:00 | 07-Jul-2025 | 15:00 | SLDC MP consent required. SLDC CG to submitted load management plan and contingency plan. 220KV-ANNUPUR-KOTMIKALA-1 &2 outages are planned simultaneously. All other lines at Annuppur/Kotmikala to be in service. SLDC CG to be informed. Load to be managed by SLDC CG/MP |  | ok
31 | 220 | 252540 |  | 220KV-ANNUPUR-KOTMIKALA-2 | Main Bus-I jumpering work of 220 kV Bus tie bay at 220 KV S/s Kotmikala |  | 11:00 | 07-Jul-2025 | 15:00 | SLDC MP consent required. SLDC CG to submitted load management plan and contingency plan. 220KV-ANNUPUR-KOTMIKALA-1 &2 outages are planned simultaneously. All other lines at Annuppur/Kotmikala to be in service. SLDC CG to be informed. Load to be managed by SLDC CG/MP |  | ok
32 | 400 | 254021 |  | 400KV-BHOPAL-MP-ITARSI-1 | for Tan Delta Measurement & DPR relay testing work at Itarsi PG end |  | 10:00 | 07-Jul-2025 | 17:59 | Ok, Both circuit are under forced outage. |  | ok, through sub ld
33 | 400 | 254022 |  | 400KV-BHOPAL-MP-ITARSI-2 | for Tan Delta Measurement & DPR relay testing work at Itarsi PG end |  | 10:00 | 08-Jul-2025 | 17:59 | Ok, Both circuit are under forced outage. |  | ok, through sub ld
34 | 400 | 252944 |  | SATPURA - 400KV - BUS 2 | For replacemnet of Bus-2 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400KV-SATPURA-ITARSI-1 is required) |  | 09:00 | 10-Jul-2025 | 20:00 | SLDC MP consent is required. 400KV-SATPURA-ITARSI-1 outage is also planned. All other elements to be in service with bus-1. In case of N-1, all elements will be out. Load to be managed by SLDC MP. |  | ok
35 | 400 | 252945 |  | 400KV-SATPURA-ITARSI-1 | For replacemnet of Bus-2 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400kV Bus-1 is required at Sarni S/S of MPGENCO) |  | 09:00 | 10-Jul-2025 | 20:00 | SLDC MP consent is required. All other lines at Satpura / Itarsi to be in service. Load to be managed by SLDC MP. 400KV-BHOPAL-MP-ITARSI- 1 &2 are under forced outage. |  | ok
36 | 400 | 253287 |  | 400KV-SSP-RAJGARH-1 | FOR LINE MAINTENANCE WORK |  | 08:00 | 07-Jul-2025 | 18:00 | All other lines from SSP to be in service. Ckt-2 (29% sensitivity) to be in service. WR2/NCA/SLDC MH/Guj to be informed. |  | ok
37 | 400 | 253280 |  | 400KV-DAMOH-KATNI-1 | TOWER STRENGTHENING WORK |  | 09:00 | 12-Jul-2025 | 18:00 | All other lines at Damoh/Katni to be in service with AR enabled. No other element shall be effected. care to be taken. WR2 to be informed |  | ok, 220kv Tikamgarh-Chattarpur to be opened for load managemnet
38 | 400KV/220KV | 253285 |  | 400KV/220KV JABALPUR-ICT-2 | FOR BAY MAINTENANCE & TESTING WORK |  | 09:00 | 08-Jul-2025 | 17:00 | ICT-1,3(29 % sensitivity) to be in service with complete did. Load to be managed by SLDC MP. |  | real time
39 | 220 | 253311 |  | 220KV-MORENA-SABALGARH-1 | FOR LINE MAINTENANCE WORK |  | 09:00 | 07-Jul-2025 | 17:00 | All other lines at Sabalgarh to be in service with AR enabled. Morena to be informed. Load to be managed by SLDC MP |  | real time
40 | 220 | 253312 |  | 220KV-SATNA-MAIHAR-1 | FOR LINE MAINTENANCE WORK |  | 10:00 | 07-Jul-2025 | 17:00 | All other 220kV circuits from Satna PG shall be in service with A/r enabled. |  | real time
S/I SLDC MPPTCL JABALPUR