## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-21
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-07-18 11:16 | MR2507/0248 |  | 220KV_220KV BAIRAGARH- BHOPAL CKT NO. I | 220KV_BAIRAGARH | NON-OCCM-MP | REPLACEMENT OF DAMAGE CONDUCTOR | 21-07-2025 09:30:00 | 21-07-2025 18:00:00 | AMBARISH SHRIPAD JOSHI | 7587951085 | ok, through sub ld
2 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
3 | 2025-07-20 14:27 | MR2507/0282 |  | 220KV_220 KV PGCIL ITARSI CK-2 | 220KV_BUDHNI | NON-OCCM-MP | Load Transfer From main bus to TBC continued | 21-07-2025 11:00:00 | 21-07-2025 17:00:00 | S.P.S TOMAR | 9425801629 | ok, line to be in service through TBC
4 | 2025-07-20 12:07 | MR2507/0274 |  | 220KV_160 MVA X-MER-II, MAKE- BBL | 220KV_CHANERA | NON-OCCM-MP | IV R-phase CT Hot point attending work | 21-07-2025 13:00:00 | 21-07-2025 15:00:00 | Sukhram Badkhane | 8462074203 | ok, through sub ld
5 | 2025-07-20 14:05 | MR2507/0280 |  | 132KV_132KV Inter Connector No.I | 132KV_CHHINDWARA1 | NON-OCCM-MP | 132KV CT Ten-Delta & Capacitance measurement work | 21-07-2025 10:00:00 | 21-07-2025 12:00:00 | Er. Anju Dhurve | 9425804752 | ok
6 | 2025-07-20 11:25 | MR2507/0273 |  | 132KV_CHHINDWARA-CHHINDWARA1_Ckt_2 | 132KV_CHHINDWARA1 | NON-OCCM-MP | 132KV CT Ten-delta & Capacitance measurement work | 21-07-2025 14:00:00 | 21-07-2025 16:00:00 | Er. Anju Dhurve | 9425804752 | ok
7 | 2025-07-16 18:05 | MR2507/0231 |  | 400KV_400 KV ISP-SARNI FEEDER | 400KV_INDIRASAGAR | NON-OCCM-WR | ANNUAL MAINTENANCE | 21-07-2025 10:00:00 | 21-07-2025 17:00:00 | SHRI VINAI MISHRA | 9575074321 | Deffered due to high ISP generation
8 | 2025-06-30 14:52 | MR2506/0617 | Continuous | 400KV_400KV KATNI-DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 21-07-2025 09:00:00 | 26-07-2025 18:00:00 | SHRI PANKAJ YADAV | 9406713326 | Deffered, not in WR list
9 | 2025-06-30 15:42 | MR2506/0629 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 21-07-2025 09:00:00 | 26-07-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
10 | 2025-07-20 13:25 | MR2507/0278 |  | 132KV_40 MVA ECE XMER | 132KV_KHAJURAHO | NON-OCCM-MP | OIL TOPPING WORK | 21-07-2025 11:00:00 | 21-07-2025 13:00:00 | CL MALI | 9425806724 | ok
11 | 2025-07-18 16:14 | MR2507/0262 | Continuous | 132KV_132 KV Khurai- Sagar Ckt | 132KV_KHURAI | NON-OCCM-MP | For modification of 132 Khurai-sagar line | 18-07-2025 07:00:00 | 27-07-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | Continuous
12 | 2025-07-20 10:41 | MR2507/0272 |  | 220KV_220kV Mandsaur-Gujarkhedi Ckt-1 | 400KV_MANDSOUR4 | OCCM-MP | additional DPR -2 Relay connecting work | 21-07-2025 10:00:00 | 21-07-2025 17:00:00 | RAJESH BHURIYA | 9425806920 | ok, through sub ld
13 | 2025-07-05 17:07 | MR2507/0079 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Insatallation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | Deffered, not in WR list
14 | 2025-07-05 16:59 | MR2507/0078 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) LIne | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
15 | 2025-07-11 16:44 | MR2507/0157 | Daily | 220KV_Omkareshwar-Khandwa Line (Line#5) | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual Maintenance | 21-07-2025 09:00:00 | 23-07-2025 18:00:00 | PANKAJ SHARMA | 7898703187 | Deffered due to high OSP generation
16 | 2025-07-20 15:04 | MR2507/0285 |  | 132KV_132 KV PANAGAR DHEEMARKHEDA | 220KV_PANAGAR | NON-OCCM-MP | FO DISC REPLACEMENT WORK | 21-07-2025 11:00:00 | 21-07-2025 18:00:00 | Pankaj yadav | 9406713326 | o&m consent required
17 | 2025-07-19 11:49 | MR2507/0265 |  | 132KV_132 KV Pichhore Chanderi Line | 220KV_PICHHORE | NON-OCCM-MP | Flash over and Broken disc replacement work | 21-07-2025 10:00:00 | 21-07-2025 17:00:00 | Satish Kumar Bhagat | 9425806916 | sub ld
18 | 2025-07-20 12:58 | MR2507/0276 |  | 132KV_132 kv Ratlam-Jaora ckt-1st both end | 220KV_RATLAM | NON-OCCM-MP | pre monsoon maintenance & testing work | 21-07-2025 09:00:00 | 21-07-2025 15:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
19 | 2025-07-20 15:22 | MR2507/0286 |  | 132KV_132 KV Ratlam - Jaora Ckt - 1st | 220KV_RATLAM | NON-OCCM-MP | For line maintenance work | 21-07-2025 09:00:00 | 21-07-2025 15:00:00 | Kumar Vishal | 9425805018 | sub ld
20 | 2025-07-20 12:58 | MR2507/0275 |  | 132KV_132 kv Bus Coupler | 220KV_RATLAM | NON-OCCM-MP | pre monsoon maintenance & testing work | 21-07-2025 09:00:00 | 21-07-2025 17:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
21 | 2025-07-20 13:55 | MR2507/0279 |  | 132KV_132 kV Main bus 2 | 220KV_SATNA | NON-OCCM-MP | For attending damaged flyover jumper | 21-07-2025 11:00:00 | 21-07-2025 17:00:00 | Ravi Pandey | 9425805296 | ok, o&m shall be informed
22 | 2025-07-19 16:20 | MR2507/0268 |  | 132KV_132kV Seoni Nainpur Ckt-IInd | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line Section 31-37 | 21-07-2025 09:00:00 | 21-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
23 | 2025-07-19 16:25 | MR2507/0269 |  | 132KV_132kV Seoni Keolari Line | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section 31-37 | 21-07-2025 09:00:00 | 21-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
24 | 2025-07-20 13:16 | MR2507/0277 |  | 220KV_220KV SIDHI-BARGAWAN(TBCB) CKT-I | 220KV_SIDHI | NON-OCCM-MP | FLASH OVER DISC REPLACEMENT | 21-07-2025 11:00:00 | 21-07-2025 17:00:00 | G.L SAHU | 9425805102 | ok, adani shall be informed
25 | 2025-07-01 16:42 | MR2507/0016 |  | 400KV_400KV Singhaji-Pithampura circuit-1 | 400KV_SINGHAJI TPS | NON-OCCM-MP | Relay testing work of Pithampura-I during AOH | 21-07-2025 10:00:00 | 21-07-2025 19:00:00 | Deepak Sharma | 8005696855 | ok, through sub ld
26 | 2025-07-19 14:47 | MR2507/0267 |  | 220KV_220 KV Sukha-Narsinghpur line Ckt-II | 220KV_SUKHA | NON-OCCM-MP | Flashover disc replacement work at loc.No.85/Y-Pha | 21-07-2025 10:00:00 | 21-07-2025 18:00:00 | Ashish Kumar | 9425805935 | ok
27 | 2025-07-20 14:12 | MR2507/0281 |  | 132KV_132/33KV 40MVA X-MER BHEL | 132KV_TEJGARH | NON-OCCM-MP | RELAY TESTING AND PANEL WIRING WORK | 21-07-2025 12:00:00 | 21-07-2025 17:00:00 | RAHUL GAJBHIYE | 9425801304 | ok
28 | 2025-07-18 14:58 | MR2507/0257 |  | 132KV_132KV DIGODA 1 LINE,132 KV DIGODA 2 LINE | 220KV_TIKAMGARH | NON-OCCM-MP | FOR JUMPERING WORK AT 132 KV DIGODA 2 LINE | 21-07-2025 10:00:00 | 21-07-2025 14:00:00 | SAMEER PARTE | 9575673359 | real time
29 |  | 252958 |  | ITARSI - 400KV - BUS 1 | 400 | POWERGRID_WR2 | for attending COE Compliance | 21-Jul-2025 | 09:00 | 21-Jul-2025 | 20:00 | ok
30 |  | 253302 |  | 400KV-BHOPAL-MP-ITARSI-1 | 400 | MP_SLDC | FOR BAY MAINTENANCE & TESTING WORK | 21-Jul-2025 | 09:00 | 21-Jul-2025 | 18:00 | real time
31 |  | 253343 |  | 220KV-GWALIOR-MALANPUR-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK | 21-Jul-2025 | 09:00 | 21-Jul-2025 | 17:00 | real time
32 |  | 253344 |  | 220KV-INDORE-INDORE-MP-2 | 220 | MP_SLDC | LINE MAINTENANCE WORK | 21-Jul-2025 | 08:00 | 21-Jul-2025 | 18:00 | real time
33
34
35
36
37
38
39