## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-17
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-11 17:24 | MR2508/0154 | Daily | 220KV_220 kV Anuppur- Kotmikala ckt-I | 220KV_ANUPPUR | NON-OCCM-MP | For Re-sagging work at loc. 424-425 | 16-08-2025 08:00:00 | 19-08-2025 18:00:00 | Jitendra Tiwari | 9425805298 | Not approved for 17th
2 | 2025-08-16 12:57 | MR2508/0202 |  | 132KV_132 kV Chhatarpur â¿¿ Khajuraho Ckt-1 Tap Lovkushnagar Line | 220KV_CHATARPUR | NON-OCCM-MP | AH/VD Tightening & other line maintenance work | 17-08-2025 10:00:00 | 17-08-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
3 | 2025-08-12 17:39 | MR2508/0176 | Daily | 220KV_220KV South Zone (Indore) â¿¿ Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
4 | 2025-08-12 17:23 | MR2508/0175 | Daily | 220KV_220KV Mangliya -Jaitpura Line. | 220KV_MANGLIA2 | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
5 | 2025-07-22 16:42 | MR2507/0344 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Installation of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | sub ld
6 | 2025-07-22 16:47 | MR2507/0345 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installatin of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
7 |  | 261909 |  | 132KV-DHARNI-NEPANAGAR-1 | 132 | MP_SLDC | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 17-Aug-2025 | 07:00 | 17-Aug-2025 | 18:59 | ok
8
9
10
11
12
13